Document of

The World Bank

Report No:

Project Brief

ON A

PROPOSED CREDIT

IN THE AMOUNT OF USD 176 Million equivalent

AND

A PROPOSED GRANT

from the global environment facility trust fund

IN THE AMOUNT OF USD 9.8 Million equivalent

TO THE

SOCIALIST REPUBLIC OF VIETNAM

FOR A

HANOI URBAN TRANSPORT DEVELOPMENT PROJECT

April 26, 2006

CURRENCY EQUIVALENTS

(Exchange Rate Effective {Date})

| Currency Unit | = | Vietnamese Dong |
| --- | --- | --- |
|  | = | US$1 |
| US$ | = | SDR 1 |

FISCAL YEAR

| January 1 | – | December 31 |
| --- | --- | --- |

ABBREVIATIONS AND ACRONYMS

| AQM | Air Quality Management |
| --- | --- |
| BRT | Bus Rapid Transit |
| CBD | Central Business District |
| CEETIA | Hanoi Urban and Industrial Environment Research Center |
| CIDA | Canadian International Development Agency |
| CITEC | Center of Information Technology and Engineering Consulting Services (of TEDI) |
| DAPM | Department of Architecture & Planning Management |
| DARD | Department of Agriculture and Rural Development |
| DCI | Department of Culture & Information |
| DOC | Department of Construction |
| DOI | Department of Industry |
| DONRE | Department of Natural Resource, Environment, Land & Housing |
| DPI | Department of Planning and Investment |
| EIA | Environmental Impact Assessment |
| EMP | Environmental Management Plan |
| EPZ | Export Processing Zone |
| EU | European Union |
| GEF | Global Environmental Facility |
| GIS | Geographical Information System |
| GOV | Government of the Socialist Republic of Vietnam |
| HAIDEP | Comprehensive Urban Development Program in Hanoi Capital City |
| HAPI | Hanoi Planning & Investment (Department) |
| HCGC | Hanoi Cartographic and Geotechnical Company |
| HCCRDP | Hanoi Capital City Regional Development Project |
| HPC | Hanoi People’s Committee |
| HUPI | Hanoi Urban Planning Institute |
| HUTDP | Hanoi Urban Transport Development Project |
| LIS | Land Management Information System |
| LRT | Light Rapid Transit |
| LURC | Land Use Right Certificates |
| MOC | Ministry of Construction |
| MONRE | Ministry of Natural Resource, Environment, Land & Housing |
| MOT | Ministry of Transport |
| MPI | Ministry of Planning and Investment |
| NMT | Non-Motorized Transport |
| NMTMS | Non-Motorized Transport Management Study |
| PAX | Passengers |
| PT | Public transit |
| PTA | Public Transport Agency |
| PMU | Project Management Unit |
| PPIAF | Public Private Infrastructure Advisory Facility |
| RAP | Resettlement Action Plan |
| SEDP | Socio-economic Development Plan |
| SEMLA | Strengthening Environmental Management & Land Administration |
| SIDA | Swedish International Development Agency |
| SOE | State Owned Enterprise |
| TEDI | Transport Engineering Design Incorporation |
| TRAMOC | Transport and Management Operation Centre |
| TUPWS | Transport and Urban Public Works Service |
| UTIP | Urban Transport Improvement Project |
| VBC | Vietnam Building Code |
| VCS | Vietnam Construction Standards |
| WB | World Bank |

| Vice President: |  | Jeffery Gutman (Acting) |
| --- | --- | --- |
| Country Manager/Director: |  | Klaus Rohland |
| Sector Director: |  | Jitendra N. Bajpai |
| Task Team Leader: |  | Shomik Raj Mehndiratta |

Vietnam

VN-Hanoi Urban Transport Project

Contents

Page

A.	STRATEGIC CONTEXT AND RATIONALE	1

1.	Country and sector issues	1

2.	Rationale for Bank involvement	2

3.	Higher level objectives to which the project contributes	3

B.	PROJECT DESCRIPTION	4

1.	Lending instrument	4

2.	Project development objective and key indicators	4

3.	Project components	5

4.	Lessons learned and reflected in the project design	10

5.	Alternatives considered and reasons for rejection	12

C.	IMPLEMENTATION	13

1.	Partnership arrangements	13

2.	Institutional and implementation arrangements	13

3.	Monitoring and evaluation of outcomes/results	14

4.	Sustainability and Replicability	14

5.	Critical risks and possible controversial aspects	16

6.	Loan/credit conditions and covenants	17

D.	APPRAISAL SUMMARY	18

Annex 1: Country and Sector or Program Background	21

Annex 2: Major Related Projects Financed by the Bank and/or other Agencies	38

Annex 3: Results Framework and Monitoring	40

Annex 4: Detailed Project Description	43

Annex 5: Project Costs	58

Annex 6: Implementation Arrangements	59

Annex 7: Financial Management and Disbursement Arrangements	61

Annex 8: Procurement Arrangements	62

Annex 9: Economic and Financial Analysis	63

Annex 10: Safeguard Policy Issues	67

Annex 11: Project Preparation and Supervision	68

Annex 12: Documents in the Project File	69

Annex 13: Statement of Loans and Credits	70

Annex 14: Country at a Glance	72

Annex 15: Incremental Cost Analysis and Global Environmental Benefits	74

Annex 16: STAP Expert Review and Response	81

Annex 17: GEF Secretariat and other Agencies’ Comments and IA/ExA Response	82

Annex 18: Maps	83

Annex 19: Stakeholder Participation Plan	84

STRATEGIC CONTEXT AND RATIONALE

Country and sector issues

Vietnam will urbanize rapidly over the next 30 years, with about one million people added annually to Vietnam’s urban areas before the year 2020. As a consequence the cities, particularly, Hanoi and Ho Chi Minh City, the two largest cities are experiencing increased traffic congestion. Both cities have very high population densities in their cores and road networks are limited in capacity. Bottlenecks are particularly severe at the edges of central business districts, and in suburban and peri-urban areas where modern industrial economies are being built on essentially rural infrastructure. Public transport is growing but still nascent.

Hanoi, North Vietnam’s key economic node and the country’s capital, is a rapidly growing city of around 3 million people.  Projections indicate that the population may double by 2020, largely through rural migration (Vietnam’s urbanization level is presently 23%).  Hanoi People’s Committee (HPC) is trying to balance the conflicting pressures of preserving the city’s character, particularly a very attractive central area, while meeting the demands posed by high levels (over 10% p.a.) of continuing economic growth.  Infrastructure and basic services, particularly in transport, are struggling to keep up.  The urban road network is relatively limited (7% of the land area), and congestion is widespread.  Primary links in the City’s road network are missing or inadequate. Capacity is particularly strained on the major East-West corridor as well as the major South and South-West corridors.

Transport is currently dominated by motorcycles, which account for over 60% of vehicular trips. In 2001, there were only 100,000 four wheelers in Hanoi, compared with 1.5 – 1.6 million motorcycles and a rather smaller number of bicycles. The poor still depend on bicycles, and non-motorized modes account for a quarter of the vehicular trips.  Less than 4% of trips in 2001 were made by bus, the only form of public transport (except taxis).

Presently, automobile ownership and use levels are relatively low, but ownership is increasing rapidly at over 10% per year.   The City is dense and new construction in built-up areas is difficult; the City has neither the resources nor the space to sustain private vehicle use (particularly automobile use) at levels significantly higher than the present. Although car ownership is mostly official and company, forecasts suggest that by 2010 per capita incomes will reach the threshold at which rapid automobile-based motorization is likely to occur.

(a) Role of buses

The HPC views increasing congestion and high road accident rates as one of the city’s most serious problems, and views public transport (PT) to be key to its urban transport strategy: HPC Resolution No. 13 calls for a 25 percent public transport share of all vehicular trips by 2005, rising to more than 50 percent by 2015. These targets are ambitious:  despite recent growth, public transport’s share of vehicular trips is currently about 10 percent.

The city’s plans call for a combination of improvements in bus based transport and future investments in urban rail. The main mode of public transport in Hanoi at present is bus. There has been significant growth in bus ridership and operations since 2001. ( ridership has increased from 1.2 million/month in 2001 to about 15 million/month in 2005 ( as a result of supplementing new buses with an innovative combination of operational (new routes, better schedule adherence) and fare policy (comprehensive tickets) changes.

Despite the recent upsurge in bus ridership, the HPC recognizes the limitations to potential public transport growth. Without the reallocation of scarce road space to give priority to public transport, traffic congestion will preclude the running of additional buses, raising their speeds, and improving their finances, at a time when operational and capital subsidies for the public sector bus company have grown to unsustainable levels.

The HPC is also looking to continue reform in public transport industry.  Until 2005, a single State Owned Enterprise (SOE) was responsible for all bus operations. HPC Decision No.34 adopted in February 2003 called for provisions to permit non-governmental companies to enter the bus transport sector. In part supported by a study financed by the Public Private Infrastructure Advisory Facility (PPIAF), Hanoi has concessioned six new routes to two private operators chosen in a competitive manner.  The City plans to extend this process to other new and existing routes.  In light of this reform there is a recognition of the need  for an independent strong regulatory agency that could take primary responsibility for regulation and planning of all public transport, including all city bus operations as well as future rail systems.

(b) Facilitating growth

Further, the City is expanding rapidly. Given the already exceedingly high densities in Hanoi’s existing urban districts (272/hecatare in the urban districts and up to 404/hectare in the central Hoan Kiem district)  all the urban growth is targeted in the newly urbanizing areas west of West lake, north of the red river and west of the third ring road south of the red river.  The Master Plan envisions extensive greenfield development in the Northwest section of the City, South of Red River and subsequently, North of the river (by 2020) to accommodate projected growth.   City authorities are working to facilitate this expansion. Development plans exist, as do plans for new roads to provide access to these areas.  The need for enhancing the capacity of the institutions responsible for land-use development and integration with transport and other infrastructure plans, and delivery is pressing.

Rationale for Bank involvement

The Bank is well positioned to support Hanoi address these challenges both in terms of the Bank’s competitive advantages in financing and policy advice as well as in terms of a strong relationship with the City.  The Bank has been working with Hanoi on urban transport issues since the mid-nineties.  This has included:

- Investments as part of the Urban Transport Improvement Project (UTIP; Cr. 3125) in Hanoi and HCMC (approximately US$20 million each) which was the Bank’s first urban transport operation in Vietnam.  UTIP focused primarily on introducing traffic management and enhancing related capabilities in local institutions. It has generally been a success in Hanoi, where authorities have implemented the traffic management schemes and complemented them with significant enforcement leading to seemingly lower accident rates and more orderly traffic.

- A study financed by the Public Private Infrastructure Advisory Facility (PPIAF) that examined institutional issues in the bus sector and supported the successful; allocation of operating franchises on 6 new routes to two new bus operators based on open competitive tendering.

To build on the recent improvements in the bus system and ongoing a series of initiatives to promote public transport, and to facilitate the expansion of the City, Hanoi proposes the Urban Transport Development Project (HUTDP), as a follow-on to the Hanoi component of UTIP.  The proposed project intends to support construction of critical sections of road infrastructure to facilitate future city development, development of a Bus Rapid Transit (BRT) system and capacity building in transport and planning/implementing institutions. The proposed HUTDP is strategically founded on the recommendations of the Bank’s Vietnam urban transport sector review (completed in 2002) and a recently undertaken Hanoi transport strategy. This project has been added to the Bank’s lending program at the request of the Government of Vietnam. The HPC has already established a working group (including a PMU) to guide preparation. The HPC has officially endorsed the proposed BRT and has formally submitted a pre- Feasibility Study (a critical step in Vietnamese processing) that includes all the key elements of the project (including the BRT, institutional changes related to public transport and air quality) to the Prime Minister for approval.

The project is well positioned to make a material contribution to poverty alleviation in Vietnam.  It will play a central role in sustaining economic growth and physical development of Hanoi.  Moreover, the project targets improvements in sustainable transport modes (PT, bicycles and walking) to upgrade the urban environment and the mobility needs of the urban poor.  Given the good working relationship established under UTIP, and extensive experience with similar projects (e.g. BRT systems in Bogotá, five other Colombian cities and Santiago), as well as sustainable transport projects in Mexico City, Lima and Santiago, the Bank is ideally placed to support this project.  The Bank can also help coordinate the efforts of other donors active in transport related issues in Hanoi.

Higher level objectives to which the project contributes

The proposed project also supports all three Country Assistance Strategy (CAS) Objectives.  It supports

- high growth through a transition to a market economy;

- adoption of a modern public administration, legal and governance system by supporting reform of the bus system, and enhancement of the City’s development planning capabilities, and

- an equitable, socially inclusive and sustainable pattern of growth: in the development of a sustainable high-quality PT system that provides accessibility to all users, and by promoting integration of land-use and transport planning in ways that fosters a shift away from private vehicles to public transport.

PROJECT DESCRIPTION

Lending instrument

The project is requesting financing by a Global Environment Facility (GEF) grant in the amount of US$ 9.80 million, with co-financing from (i) the Government of Vietnam’s resources (US$ 153.00 million), and (ii) an IDA Credit of (US$ 175 million).

Project development objective and key indicators

The development objectives of the HUTDP are to help Hanoi City to (a) increase the efficiency and cost-effectiveness of its transport system, and (b) develop public transport-compatible urban growth plans.  Its GEF strategic objectives are to promote a shift to more environmentally-sustainable transport modes and urban development plans, and to promote the replication of these approaches in the country and region. Its global environment objective is to lower Hanoi’s transport-related greenhouse gas emissions, relative to a business-as-usual scenario.

Rationale for GEF Funding

GEF co-financing is being requested for small, yet key, strategic components (proposed GEF financing is less than 3 percent of project cost) to complement the primary funds being provided by IDA and Hanoi.  GEF co-financing is being proposed for a set of strategic initiatives that either reduce barriers to implementation of the project or maximize the global environmental benefits from the project investments.

The project is consistent with the objectives of the GEF Operational Program 11 on “Promoting Environmentally Sustainable Transport”.  The project is also consistent with the GEF climate change strategic priority related to Sustainable Transport as defined in the GEF Business Plan for FY04-06 (GEF/C.21/9).  In particular, this project will address modal shifts to sustainable transport modes through emphasis on BRT, non-motorized transport (bicycles and pedestrian areas), and organizational measures (such as traffic demand management and economic incentives).  The project will also build institutional and technical capacity at the local level, support policy development and public outreach initiatives.

In particular, the project seeks to increase the potential global and local environmental benefits of the city’s strategy in four fundamentally ways:

- Ensuring and accelerating a modal shift away from personal motorized vehicles to bus transport; by generating support for the implementation of the planned IDA-supported bus rapid transit system (removing public perception and education barriers), by promoting a quicker, bigger shift to buses through enhancing the attractiveness of the service (improving non-motorized transit (NMT) access and enhancing the attractiveness of BRT stations);

- Assisting in the development of a strategy to encourage and sustain bicycle use and walking and activities that make these activities safer and more convenient;

- Assisting development of an urban transport policy that is environmentally-sustainable from a global perspective; which promotes public transport by developing a parking policy, policies discouraging ownership and use of motorized vehicles, and by enhancing the capacity of planning and enforcement institutions; and,

- Assisting development of an environmentally sustainable urban development strategy that promotes integration of transport and land-use planning.

From both local and global environmental perspectives, an IDA-GEF transport operation in Hanoi provides the rare opportunity for transport planners to be ahead of the curve.  Rather than fighting the tough (and often losing) battle against the automobile once it is ubiquitous in an urban infrastructure that favors (and often requires) a car, in Hanoi there exists an opportunity to work with the Peoples’ Committee to create a sustainable, public transport-oriented city by coordinating urban transport infrastructure investments, the city’s development strategy, and its transport policy before widespread adoption of the automobile.  It also provides a rare opportunity to avoid the gradual extinction of bicycle use before all non-motorized movement has been pushed aside by growing motorization – as has happened in many developing countries before the GEF OP11 objective was formulated and GEF transport funding was available.

Further, the project sets in place an approach to replicate the experiences of Hanoi throughout the country and in the region.  This approach consists of awareness-raising and active information transfer, including transferring of lessons learned from the Hanoi experience to other cities within Vietnam, as well as to nearby countries facing similar urban transportation issues.

It is worthwhile to note that through the preparatory activities (PDF-B phase), the GEF has already made a significant contribution to the project’s design. Indeed, without the availability of the GEF PDF-B funding, it is quite likely that the full-scale BRT system currently proposed would not have been considered by Hanoi.  The original request from Hanoi was for a combination of simple bus priority measures along a set of unspecified roads in the city, with the expectation that this would be a relatively small investment without significant impact.  Through the PDF-B, Hanoi’s leadership gained an enhanced understanding of the BRT concept, the appropriateness for Hanoi and the success of BRT elsewhere. In other words, by virtue of the PDF-B funding alone, the GEF has already played a catalytic role in the generation of the current project, a full-scale 24.5 km BRT system on two major corridors in the city, accounting for over US$80 million of the proposed IDA credit.

Refer to Annex 3 for Results Framework and Monitoring Plan, including key indicators.

Project components

The project has three components and several environmentally-oriented subcomponents for which GEF incremental cost financing is requested to remove the barriers associated with them:

(1) Development of a Bus Rapid Transit System (BRT)

- BRT System Design and Implementation, including Pedestrian and NMV Improvements

- BRT Stations, Interchanges and Terminals

- BRT Public Consultation, Communications and Media Strategy

(2) Strategic Road Infrastructure and Sustainable Urban Planning

- Strategic Road Implementation

- Integrated Sustainable Urban Land Development and Transport Planning

(3) Program to Support Air Quality, Traffic Safety, the Public Transport Authority, Transport Policy and Replication

- Air Quality Management Program

- Traffic Safety

- Public Transport Authority Strengthening

- Transport Policy Development

- National and Regional Replication and Information Dissemination

(1) Development of a Bus Rapid Transit System (BRT) [total US$87.29 million, IDA US$75.29 million, Government of Vietnam US$8.0 million, GEF$4.0 million] – The first intermediate outcome of the HUTDP will be the completed BRT works and commencement of operations, including pedestrian and NMV improvements.

This component includes civil works, consulting services for design and supervision, and advisory services for project management. It will support the development of segregated busways and bus priority on a selection of new and existing roads, the construction of BRT stops, interchange stations, terminals and maintenance facilities. It will also support the establishment of a modern BRT management system, including bus ticketing and financial controls.    Lastly, the component will finance the implementation of a public consultation, communications and media strategy for disseminating information on the BRT system.

- BRT System Design and Implementation, including pedestrian and NMV improvements to increase access to the proposed BRT system

(total financing US$67.99 million; IDA co-financing US$66.69 million; proposed GEF co-financing US$1.30 million)

The baseline BRT component already includes the development of inclusively designed stations designed to facilitate pedestrian access.  The proposed incremental improvements in pedestrian and non-motorized transport (NMT) access proposed for GEF co-financing will target improvements to enhance the pedestrian environment in the vicinity of BRT stations, in a 250 meter radius around the stations to increase station accessibility. International experience suggests that such improvements in accessibility can have a very high return in attracting trip makers. If a trip maker must use a motorized private vehicle (motorcycle or car) to access public transport then it is significantly more difficult to convince them to not use their private vehicle for the entire trip. GEF co-financing of this sub-component will support an increase in non-motorized modes of transport, including bicycles and pedestrians, and will also reduce GHG emissions by making the BRT system more accessible to trip makers who would otherwise have used a private motorized vehicle.

- BRT stations, terminals and interchanges to promote a modal shift to public transit for consumers with choice (total financing US$ 18.0 million; IDA co-financing US$16.6 million; proposed GEF co-financing US$1.4 million)

GEF co-financing for the BRT stations, terminals and interchanges is sought to develop stations that are more attractive than the basic functional forms that would be financed by the IDA Credit.  International experience indicates that the appeal of stations that have a clear identity lead to two kinds of benefits that induce a mode shift towards BRT: (1) successful systems such as Bogotá, Curitiba, and Quito have all developed station designs that users take pride in and become part of the system’s ‘brand identity’; and, (2) the appeal of stations are also a key factor in the decision-making for trip-makers who have the choice of other modes.  GEF co-financing of this sub-component will enhance the overall competitiveness of the BRT and specifically target consumers who have the choice of private vehicle modes (auto and motorcycle) and need to be persuaded that public transport offers an equal or better travel experience.

- BRT Public Consultation, Communications and Media Strategy

(total financing US$1.3 million; proposed GEF co-financing US$1.3 million)

The public consultation, communications and media strategy is critical to retaining political commitment and implementing the BRT system as planned. GEF co-financing of this sub-component will reduce the risks related to successful project implementation by increasing the understanding of BRT’s implementation and benefits by key stakeholders and by ensuring that the needs of diverse stakeholder groups are addressed on an ongoing basis.

(2) Strategic Road Infrastructure and Sustainable Urban Planning [total US$236.8, IDA co-financing US$90 million, proposed GEF co-financing US$1.8 million] – The intermediate outcomes of this component will be completed physical works and the beginning of operations of the strategic roadways, and the adoption of integrated sustainable urban land development and transportation planning in Hanoi.

- Strategic Road Implementation

(total financing US$235 million; proposed GEF co-financing US$0)

This component will involve the construction of two new road segments: (i) a section of approximately 7 km in length for the proposed second Ring Road between the proposed new bridge across the Red River (at Nhat Tan and Cau Giay); and (ii) the Hoang Quoc Viet Western extension (approximately 3.4 km), from the Third Ring Road to South Thang Long Industrial Zone.  The implementation of the road infrastructure will be funded entirely by IDA and the Government.

- Integrated Sustainable Urban Land Development and Transport Planning

(total financing US$1.8 million; IDA co-financing US$0.05 million; proposed GEF co-financing US$1.75 million)

The GEF-funded activities under this component will focus on provision of technical assistance to support integrated sustainable urban land development and transport planning. This GEF intervention has been designed to address concerns that regardless of Vietnam’s strong planning tradition, the uniform medium-density spatial distribution characterizing recent urban growth in Vietnamese cities structurally renders public transport at a fundamental disadvantage.  With GEF financing, Hanoi has agreed to conduct (i) reviews of its existing planning regulations, standards and procedures and consider modifications that would result in facilitating urban growth that is more compatible with competitive public transport; (ii) reviews of existing plans for the newly urbanizing areas west of West Lake and north of the Red River from the same perspective; and (iii) case studies (tax incentives, zoning exceptions, feasibility studies) at particular locations that would make the recommendations of these reviews actionable.  GEF co-financing of this component will create models of effective interventions that make the urban planning process more responsive to transport and GHG emission concerns by creating spatial patterns less dependent on private motorized transport.

(3) Program to Support Air Quality, Traffic Safety, the Public Transport Authority, Transport Policy and Replication [total US$11.15 million, IDA co-financing US$7.55, proposed GEF co-financing US$3.60 million] – The intermediate outcomes of this third component will be local capacity to plan, manage, and implement public transport, and the awareness and understanding of the transport-related actions needed to achieve sustainable outcomes.

The Program has five subcomponents: (a) an Air Quality Management (AQM) program; (b) a Traffic Safety program; (c) strengthening of a newly established Public Transport Authority; (d) transport policy development; and, (e) replication activities that have been designed to address GEF’s priority on replication. Specifically:

- Air Quality Management Program

(total financing US$3.45 million; proposed GEF co-financing US$0)

The Air Quality Management Program will address: emissions inventory and air-quality monitoring; comprehensive motor vehicle emission control strategies; inspection and maintenance program and motorcycle clinics to raise awareness of the role of motorcycles in local air pollution; and development of economic instrument approaches to air quality management.  No GEF co-financing is sought for this sub-component.

- Traffic Safety

(total financing US$2.9 million; proposed GEF co-financing US$0)

The traffic safety subcomponent includes investment in traffic control equipment to support the traffic police and other Hanoi agencies control traffic in Hanoi more effectively.  No GEF co-financing is sought for this sub-component.

- Public Transport Authority Strengthening

(total financing US$2.4 million; IDA co-financing US$1.2 million; proposed GEF co-financing US$1.2 million)

A study reviewing the institutional structure governing Hanoi’s public transport concluded that, in light of the changing nature of the role of the City government (from playing the role of the operator in the past towards an evolving role as manager), the establishment of an Authority to coordinate planning, regulation and operations of different public transport modes was critical to maximize the benefits of, and ensure the sustainability of, enhancements in Hanoi’s public transport.  This finding is particularly important given GEF’s concerns related to bus system sustainability raised during pipeline entry of this proposal.  That Hanoi has decided to establish such a high-level authority directly under the HPC is a significant positive development. If effective, this agency can ensure that HUTDP and other related investments in public transport are synergistic, and thereby maximize the competitiveness of public transport and consequent local and global benefits.  Further, the establishment of an effective public transport authority has the potential for significant regional demonstration effects:  cities all across East and South Asia need models of effective authorities that have the mandate to coordinate across different public transport operations.  The IDA Credit will support this new authority with equipment, related hardware and support.  GEF co-financing is sought to support this authority with training and related activities that would (i) ensure sustainability of the HUTDP investments and help allay GEF’s stated concerns related to sustainability; and (ii) ensure that low cost coordination and planning measures that would maximize the effectiveness of the BRT and other complementary investments in public transport are properly implemented.

- Transport Policy Development

(total financing US$1.5 million; proposed GEF financing US$1.5 million)

Transport policy development is an important part of HPC’s mandate.  Consequently, Hanoi invests significant resources and managerial effort on the issue.  A JICA financed master plan that includes transport is near completion.  Issues related to restrictions on motorcycle and auto ownership, parking, and safety are important and constantly on the HPC’s agenda.  However, Hanoi’s attempts to enforce restrictions on the use of auto and motorcycle ownership to manage congestion, thus far, have been largely ineffective.  Additionally, the Bank’s assessment is that appreciation of the potential of economic instruments based on price as alternatives to command-and-control methods, to effectively manage the urban transport system is limited.

Properly implemented, such instruments have the potential to significantly reduce the amount of private motorized travel (and consequently GHG emissions), by inducing shifts to public transport and encouraging trip combination.  GEF co-financing is sought to supplement existing transport policy initiatives in Hanoi with studies, training and related activities to (i) raise awareness, understanding and comfort of decision-makers with economic instruments to manage/restrict  private vehicle use as a means to address congestion and related transport problems in Hanoi’s context; (ii) to support the development of an actionable long-term plan in this respect; (iii) specifically, examine the role parking policy can play and to assist the HPC to manage the transport system, focusing on the development of a parking and enforcement policy that can serve to manage demand rather than just accommodate it; (iv) support the development of a fuel use and CO2 inventory and promote the use of indicators related to total motorized travel/energy use in Hanoi’s transport policy development; (v) support an impact evaluation of the BRT; and (iv) support planning for subsequent phases of the BRT system. GEF co-financing for this sub-component will support the development of an urban transport policy that is more environmentally sustainable and will generate global benefits from a shift to public transport and a reduction in the volume of private motorized travel.

- National and Regional Replication and Information Dissemination

(total financing US$0.9 million; proposed GEF financing US$0.9 million)

GEF financing of this subcomponent is proposed to promote awareness raising, knowledge transfer and replication efforts in other Vietnamese cities and the region.  This component includes a combination of Hanoi-based activities and activities in other Vietnamese cities. The proposed Hanoi-based replication initiatives include:  hosting study tours from other Vietnamese and regional cities, conducting workshops, and facilitating other information dissemination activities such as lessons learned reports.  Additional replication initiatives, to finance initial BRT feasibility studies in other Vietnamese cities, interested in following up on Hanoi’s example are proposed to be executed via an appropriate central government agency.

Project Cost by Component

| Project Cost By Component | GoV | IDA | GEF | Total |
| --- | --- | --- | --- | --- |
|  | US $million | US $million | US $million | US $million |
| 1. Development of the BRT System |  |  |  |  |
| A. BRT System (except for stations, terminals and interchanges), and NMT and Pedestrian Access | 6.270 | 60.420 | 1.300 | 67.990 |
| B. BRT Stations, Interchanges, and Terminals | 1.730 | 14.870 | 1.400 | 18.000 |
| C. BRT Consultation, Communications and Media Strategy | 0.000 | 0.000 | 1.300 | 1.300 |
| 2. Strategic Road Infrastructure and Sustainable Urban Planning |  |  |  |  |
| A. Strategic Road Implementation | 145.000 | 90.000 | 0.000 | 235.000 |
| B. Integrated Sustainable Urban Land Development and Transport Planning | 0.000 | 0.050 | 1.7500 | 1.800 |
| 3. Program to Support Air Quality, Traffic Safety, the Public Transport Authority, Transport Policy and Replication |  |  |  |  |
| A. Air Quality Management | 0.000 | 3.450 | 0.000 | 3.450 |
| B. Traffic Safety | 0.000 | 2.900 | 0.000 | 2.900 |
| C. Public Transport Authority Strengthening | 0.000 | 1.200 | 1.200 | 2.400 |
| D. Transport Policy Development | 0.000 | 0.000 | 1.500 | 1.500 |
| E. National and Regional Replication and information dissemination | 0.000 | 0.000 | .0.900 | 0.900 |
| Project Management | 0.000 | 3.000 | 0.450 | 3.450 |
| Total Cost (excluding price contingencies) | 153.000 | 175.890 | 9.800 | 338.690 |

Lessons learned and reflected in the project design

- Project needs to have full ownership at the city level.  The Ministry of Transport (MoT), rather than the cities, was the primary counterpart for the earlier UTIP.  Even though the cities were consulted extensively during preparation, implementation was delayed because the cities had not explicitly approved all the project elements. This project was prepared with the full support of the HPC and the HPC’s explicit endorsement was required at crucial stages:  appropriateness of the BRT concept, selection of BRT corridors, project components and design, establishment of PTA, consolidation of existing air quality monitoring stations under the Department of Natural Resources and the Environment (DONRE), etc.

- The international experience suggests that to be successful a BRT needs not just technical preparation but political commitment, institutional acceptance and public support.  This lesson has framed the preparation of the project; the BRT feasibility study has been complemented by a series of actions including a study tour of successful BRT systems in Latin America for the existing leadership, and technical TUPWS staff, seminars highlighting the experiences of Bogotá (delivered by former Mayor Peñalosa) and Jakarta, and other studies validating the appropriateness of the BRT concept in Hanoi.

- For long-term sustainability of public transport, BRT depends on the right institutions.  A PPIAF-financed study focusing on long-term economic sustainability of bus transport was conducted as a pre-curser to project identification.  The recommendations of the study have been core to the design of both the IDA and GEF projects; the BRT has been designed to be operated by competitively procured operators who will be managed and regulated by a PTA.

- Subsidies are not in themselves unsustainable, and subsidies targeted at specific segments are most effective.  The international experience suggests that public transport is a vital public good and subsidies are not in themselves unsustainable as long as political commitment that facilitates a stable and growing system exists, and the levels of subsidy are affordable.  The experience also suggests that broad social goals are best served by targeted subsidies towards user groups rather than system-wide measures.  The PPIAF analysis in Hanoi suggests that a large share of the subsidy is due to the subsidized nature of the student monthly passes.  It was agreed that this is an appropriately designed subsidy (it is targeted towards a user group) that would be appropriate for the City to bear the cost of.  Also, in light of HPC’s demonstrated strong commitment to public transport, the focus of the Bank appraisal has been on ensuring that institutional arrangements to ensure efficient operations (competitively tendered operating concessions, independent regulatory and planning body) rather than eliminating subsidies altogether.

- The international experience suggests that in general, operators are best served by buying buses themselves.  However, in Hanoi, where a single SOE dominates operations despite successful recent effort to broaden participation to the private sector, the Bank’s judgment is that supporting the purchase of buses for the City, which would in turn lease them to all eligible operators on an equal footing, would actually help leveling the playing field in favor of new potential entrants.

- Without attention to land-use, development may well not be friendly to public transport. Very few cities internationally (Singapore, Curitiba, Stockholm, Hong Kong) have been able to consistently grow in a manner that is compatible with the future growth of the city’s public transport system.  The land planning TA component of the GEF program has been designed to support land use policy/regulation and its implementation to ensure that development is focused around nodes in a public transport.

- Institutional issues are critical to establishing a successful Air Quality (AQ) component.  It is critical that the agency responsible for monitoring air quality also has a role in devising and implementing emission control strategies.  In this project, supporting DONRE to broaden their mandate from monitoring to control has been an integral element of the work.

- Lessons from other Bank executed OP11 projects.  In the past, the World Bank has been involved in several projects aiming to address urban transport and green house gas (GHG) emissions by integrating improvements in public transport with land use planning, traffic management, support to non-motorized transport and other measures.  The most relevant GEF projects, from which important lessons or experiences have been drawn, are the (i) Sustainable Transport and Air Quality for Santiago (Chile), (ii) Introduction of Climate Friendly Measures in Transport for Mexico City, and (iii) Lima-Callao (Peru)  sustainable transport projects.

From the Santiago project, the most important experiences are related to bikeways and to land-use measures.  In the first case, it has been very important to intensively promote the use of bikes as an alternative transport method and not only by integrating pilot bike paths with important public transport stations and by providing safe and well maintained routes.  With regard to land-use planning, the objective of reducing vehicle-generated air pollution is being addressed by revitalizing historic and business centers, by coordinating land use development with public transport infrastructure, by ensuring safe and convenient walking conditions in high-density areas, and by defining approaches to reduce uncontrolled urban sprawl

The Mexico City project focuses mainly on institutional and regulatory measures as well as the elaboration of many preliminary studies. It has shown that coordinating different government agencies in order to achieve the expected objectives of integrating actions from different sectors, can be difficult if there is no strong political and social commitment.  Therefore preliminary studies have been instrumental to demonstrate the long term benefits, viability and sustainability of the proposed activities, which at the same time will lead to an improvement of the quality of life for the cities’ inhabitants. Thanks to the GEF support, the city has built its first BRT corridor on Avenida Insurgentes (operation started in mid-2005), and is now planning a second corridor along the East-West Axis.

The Lima-Callao project includes the construction and rehabilitation of pilot bikeways and a promotional strategy to increase bicycle use.  In addition, it complements the implementation of Lima’s first BRT line (financed by a parallel Bank loan) with additional measures aiming to reduce the current oversupply of old and polluting public transport vehicles.

The three ongoing GEF projects supporting sustainable transport in Latin American cities have been rated Satisfactory. Two aspects are worth mentioning regarding their non-motorized components: (i) there is a clear need for close supervision in the early phases of the project, and (ii) as the non-motorized transport agenda is becoming a priority in many cities of Latin America, the GEF projects have spurred a fruitful cross-fertilization among key actors, not only from the three project cities, but also with cities in Colombia, Ecuador and Brazil. Such South-South cooperation, among Asian cities, could also be generated from the proposed Hanoi project.

Alternatives considered and reasons for rejection

Two alternatives to a stand-alone SIL were considered, a repeater to UTIP and adding additional finance to the Hanoi component of UTIP. However, as opposed to UTIP which was rated an Environmental Category B project as per World Bank’s OP/BP 4.01 the proposed project is Environmental Category A and triggers World Bank’s OP/BP4.12.   For these reasons, the potential simplification benefits related to the use of repeaters and additional finance would not accrue.  For this reason a stand-alone SIL was finally chosen as the appropriate investment instrument.

In addition, the final design of each component was based on an extensive analysis of institutional, technical, economic and financial considerations.  Several alternatives were considered (details in appraisal summary and Annex 9) before a final decision was made.

IMPLEMENTATION

Partnership arrangements

A GEF grant of US$ 9.80 million will be requested to co-finance the IDA loan under the GEF’s Operational Program 11 (Promoting Environmentally Sustainable Transport).

Institutional and implementation arrangements

Hanoi People’s Committee will be fully responsible for executing the project. HPC will establish a Project Leading Group headed by the Vice Chairman of the HPC responsible for infrastructure (or higher) to facilitate project implementation.  To manage, coordinate and supervise the project, the HPC has established a PMU, under the Hanoi Transport and Urban Public Works Service (TUPWS), which has experience implementing the previous IDA-supported Urban Transport Improvement Project. (This will be finalized at appraisal – HPC is considering establishing this PMU directly under the HPC.) The PMU will be maintained at all times during the implementation period with adequate budget and qualified fulltime staff.

The PMU will sign all contracts on behalf of the HPC.  The PMU will be the executing agency managing the implementation of all civil works.  The Public Transport Authority (PTA) will manage the procurement of the buses and all equipment related to the BRT system.  The PMU and PTA together will manage the BRT concession processes.  The BRT concessions will likely be signed with the PTA on behalf of HPC.  The traffic police and traffic inspection board under TUPWS will be involved in the procurement of all equipment related to traffic management. The Department of Natural Resources and the Environment (DONRE) will manage the implementation of the air quality component.  The Department of Architecture and Planning Management (DAPM) will manage the implementation of the urban planning technical assistance. The PMU will coordinate with all relevant agencies including the HPC, TUPWS, the traffic inspection board of TUPWS, the traffic police, Department of Planning and Investment (DPI), the PTA and bus operators on the comprehensive planning TA.  The PMU will organize and manage all Hanoi based replication activities including workshops and hosted study tours.  Individual cities wishing to explore BRT demonstrations will execute study tours and feasibility studies for such activities, facilitated by the Ministry of Transport (MOT) (this arrangement will be finalized at appraisal).

The roads and BRT road infrastructure will be turned over to TUPWS after construction and will be maintained by TUPWS.  BRT buses, terminals, depots and other equipment will be owned by the City (with the PTA potentially representing the City) and leased out to operators as appropriate.  The operators will be selected based on competitive tendering.

DAPM will be responsible for any revisions in plans or planning regulations which will all likely need to be approved by HPC. DONRE will be responsible for processing air quality monitoring data.  An emission control policy will be finalized with DONRE coordinating with other related agencies including traffic police, Vietnam Register and TUPWS.

Project oversight. At the national level, the Ministry of Planning and Investment (MPI) provides overall sectoral guidance on investment policy and approves and monitors the progress of all large foreign-assisted projects. For sector-specific issues, MPI consults with the sector ministry, in this case the Ministry of Transport and Communications (MOT), the national agency responsible for developing and managing the transport sector. MOT plays an advisory and coordinating role for developing the urban transport sector in Hanoi. At the city level, HPC, in consultation with TUPWS, will guide, approve and monitor project-specific policy and investment decisions. The Stakeholder Participation Plan is provided in Annex 19.

Accounting, financial reporting and auditing arrangements. To ensure financial accountability, various steps will be taken: (a) The PMU will maintain a separate project account, including the special account; (b) the special account and project account, including documentation for SOEs, will be audited annually by independent external auditors acceptable to IDA and the Government, with the audit including a separate opinion on the SOEs used as a basis for disbursements; and (c) detailed audit reports will be submitted by the PMU to IDA annually, within six months after the end of the city government's fiscal year.

Monitoring and evaluation of outcomes/results

Annex 3 lists the main outcome indicators for the project, as well as the principal results indicators for each component.  Additional indicators are listed in the various documents in the project files (e.g., the Environmental Management Plan - EMP).  Both HPC and TUPWS will regularly collect the data required for monitoring and evaluation of outcomes and results.  HPC and TUPWS will review the results on the basis of various progress reports, and take appropriate corrective action where needed.

Sustainability and Replicability

Sustainability

The institutional and physical interventions in the bus system have been conceived to ensure sustainability of recent increases in bus usage by addressing the key limitations of the current paradigm for bus operations: a fast increasing fiscal burden and capacity limitations related to shared-use road space. A PPIAF financed study conducted prior to project identification identified the following issues:

- Fares.  The analysis suggested that monthly fares were too low and there was a need to differentiate fares, particularly for long trips.  Both have been implemented during project preparation after the PPIAF study was complete.

- Private participation and competition.  In order to ensure efficiency, the PPIAF report recommended that Hanoi concession new services to operators on an open competitive basis, using gross-cost tenders for new routes.  Support from the PPIAF consultancy was used to concession 6 new routes on that basis in 2005.  The franchises to operate the proposed BRT routes will also be concessioned.  The city is also planning to tender the routes operated by TRANSERCO, the dominant SOE on a phased basis.

- Strengthened regulatory and planning capacity in the City.   The PPIAF study highlighted the need to establish a high-level public transport authority independent of bus operators to plan, regulate, and manage public transport operations in Hanoi.  Hanoi has agreed to establish such an agency as part of project preparation (and submitted a formal request to the Central Government for approval).  This authority will have a significant role in the implementation of the BRT component.  The proposed IDA Credit and GEF project both support the development of this agency.

Similarly, sustainability is the key principle aligning the otherwise disparate elements of an urban transport policy:  there is a recognition of the need to address urban transport problems in a comprehensive manner, and a recognition that to attain the PT shares that HPC has targeted, public transport improvements need to be complemented with actions to address parking and the attraction of private vehicles.

Financial Sustainability – A financial analysis of the BRT investments (see Annex 9 of the Brief for details) determined that the BRT is financially sustainable.  It is anticipated to produce a net surplus of approximately US$2 million per year initially, rising to over US$5 million in 2015. From then onwards, credit repayments of approximately US$2.5 million per year have to be made, but the net surplus is still over US$2.8 million per year, rising to US$10 million in 2027.  Preliminary estimates suggest that the economic benefits of the BRT are even greater than the financial benefits.

Replicability

The BRT project in Hanoi has a strong potential for replication both in Vietnam and in the region. The proposed project seeks to actively promote replication, in other Vietnamese and Asian cities, by leveraging the demonstration nature of the project and disseminating information gathered during implementation.

As the implementation of Hanoi’s BRT line sets an example for other Vietnamese cities and in the larger region, the project replication activities, therefore, will actively target replication both within Vietnam and within the region through the following:

- BRT promotion for Vietnamese cities:  Replication within the country will be promoted by briefing the managers of other major Vietnamese cities on the project, keeping them appraised of its progress and impacts and financing BRT feasibility studies and associated activities for follow-on activities in interested cities (implementation arrangements for this activity are being finalized with the Ministry of Transport at the Central level).  Information will be made available on a regular basis through the production of public information announcements and other materials.  Meetings will be held to inform other cities about the benefits of BRT, the joint transport/urban planning process, and lessons learned as the project proceeds.

- Replication outside the country will be promoted through publications (e.g. lessons learned reports) on the Hanoi BRT; exhibits and presentations will be made by Hanoi at major transport fora in the region; and by hosting and promoting study tours to Hanoi for senior urban development and transport planners from other Asian cities.

- The Hanoi BRT website will be a central repository for information on the progress, achievements, lessons learned and contact information.

Based on experience from other successful systems such as Curitiba and Bogotá, other cities often express great interest in learning about BRT once the BRT systems begin implementation.  Recognizing this trend, the Hanoi project will facilitate the process both by organizing tours for interested parties and also by presenting information and lessons learned on BRT in a synthesized manner.

The Hanoi project is already having an impact through the demonstration effect of the planning process for BRT:  Ho Chi Minh City is following in Hanoi's steps and considering/planning a demonstration BRT line.

Critical risks and possible controversial aspects

The key assumption of the project is the continued support for its strategy from the decision-makers responsible for the urban development of Hanoi. Political will is key to the successful implementation of the BRT, which could be weakened by a change in leadership.  The technical assistance provided through this project, including study tours and media strategy to support Hanoi leadership, will serve to mitigate this risk. Additional risks, and how they are being mitigated by the project, include:

- Risks related to public nervousness and negative reaction of motorists to the BRT will all be mitigated through effective consultation, communications and media strategies, and by working to maintain the total number of bus jobs through expansion of the PT market through new routes and other opportunities.

- The potential risk of the benefits (including global benefits) of the BRT being undermined by ineffective coordination with other transport modes including NMT, feeder services and other bus services will be addressed by (i) the NMT improvements around BRT stations and provision of secure bicycle and motorcycle parking at major BRT terminals; and (ii) supporting the PTA, which will have the mandate to ensure coordination across modes and public transport services.

- The potential risk of the dominant state-owned enterprise undermining efforts to establish a sustainable bus system based on a properly regulated, efficient industry will be addressed by the establishment and support for the Public Transport Authority.

- The risk that the urban growth west of west lake and in Dong Anh north of the Red River will be unplanned growth not conducive with competitive public transport will be addressed by the provision of technical assistance on urban planning.  This technical assistance specifically addresses the urban plans and plan implementation in the newly urbanizing areas, and will include pilots to promote growth compatible with competitive urban transport.

- The risk that the project GHG benefits from the gains in public transport will be undermined by increases in incomes that could lead to increases in automobile ownership and use will be addressed by supporting the development of a comprehensive urban transport policy that (i) increases awareness of parking charges and other restrictions on private vehicle ownership and use on sustainable urban transport outcomes, (ii) support for the development of an transport air quality management plan to complement efforts to limit private vehicle use, and (iii) support for planning to extend the BRT network.

Loan/credit conditions and covenants

To be finalized at appraisal

Effectiveness conditions

  - Delivery of the financial management training to all staff and finalization (issuance) of the financial management manual.

  - The PMU will have adequate, qualified, full-time staff to prepare, implement and monitor the technical designs and enforcement requirements.

Counterpart funding

The Government will take necessary actions to ensure that the PMU receive counterpart funds in a timely manner from HPC for project implementation.

Reporting and Monitoring

- The PMU is to monitor the implementation of the EMP and RAP and submit twice-yearly monitoring reports to IDA, by February 15 and August 15 of each year, starting on February 15, 2007, covering the periods January-June and July-December respectively.

- The PMU will maintain separate project accounts, as well as monitor and report project progress, using project performance indicators;

- Progress reporting and mid-project review: The PMU is to submit, by February 15 and August 15 of each year, starting with February 2007 and until the project is completed, a semi-annual progress report on project implementation covering the period January-June and July-December respectively.

- The special account and project accounts for the PMU, including documentation for SOEs, will be reviewed annually by independent external auditors acceptable to IDA and the Government, with the audit including a separate opinion on the SOEs, which would then be used as a basis for disbursements;

- The detailed audit reports will be submitted to IDA within six months after the end of each fiscal year;

- The Government will hold annual implementation reviews (by June 30 of each year, beginning in 2007) and a mid-term review (by June 30, 2009)

Procurement

Detailed procurement arrangements are currently being finalized.  The Government will agree on all procurement arrangements including the use of the Bank's standard bidding documents for works and goods procured under ICB and for consultant services. The Borrower's local procurement procedures (Decree 43/CP dated July 16, 1996) will be used for national competitive bidding (NCB), with the required revisions and clarifications for purposes of consistency with Bank guidelines for NCB.

APPRAISAL SUMMARY

This is a Pre-appraisal document. To be finalized at Appraisal.

Economic and financial analyses

See Annex 9.

Technical

In the design of the BRT component, three kinds of alternatives were considered before the choice of a closed BRT system trunk and feeder BRT system with special-buses running primarily on a network of exclusive bus routes was chosen.  In addition to the chosen alternative simple bus priority measures (rejected because of their relatively little success in environments similar to Hanoi where there is the potential for significant problems of non-observance and enforcement) and open BRTs such as in Seoul, Kunming and Taipeh where a variety of buses and access and egress from the exclusive lane system (rejected because of the potential for control problems leading to excessive bunching) were considered.

In the design of the road component, particularly the second ring road a series of different alternatives were considered in view of significant technical, social, economic and financial constraints.  The final solution chosen has many features of interest.  First, the alignment of a reserve median for a future mass rapid transit (BRT or rail) was identified compatible with longer term growth proposals for the region north of red river and west of west lake.  Then there are significant reductions from the previously identified planning line at Buoi interchange and on the Hoang Hoa Tham spur to reduce involuntary resettlement and the cost associated with it.  The final design chosen for the section between Cau Gaiy and Buoi reflects an extensive analysis to provide forecast capacity needs in a very tightly constrained space bounded by the dyke and the drainage canal.

Institutional issues were a key focus of the preparation of the air quality subcomponent. In late 2005, the HPC decided to consolidate the management of all existing AQ stations under DONRE. This resolved the Bank’s prior concerns related to fragmentation in the management across DONRE, a university and other agencies.  Dialogue during preparation has also focused on issues related to implementing effective control strategies, and at this stage the HPC is fully cognizant of the need to extend the mandate of DONRE from monitoring to control. The sub-component has been designed in coordination with other aid agencies active in Vietnam and has been designed to complement and leverage bilateral interventions of the Swiss aid agency (Swisscontact), EMBARQ and Norwegian interventions in HCMC.  DONRE, coordinating as appropriate with TUPWS, traffic police, the Vietnam Register and other related agencies will lead the implementation of this component.  Preparation of a pilot motorcycle clinic is proceeding already in part using Norwegian trust funds, with the pilot clinic scheduled between April and July 2006. Local manufacturers have already agreed to participate in the process. Initial results from the clinic are expected before Appraisal is complete.

Fiduciary

To be finalized at appraisal.

Social

The project supports the development of public transport, pedestrian and bicycle facilities, all of which will have desirable distributional benefits. The project will have adverse impacts related to the need for land acquisition and involuntary resettlement.  A Resettlement Action Plan (RAP) is being finalized through full consultation process with local stakeholders and affected people, the preparation process is under closed supervision of the Bank social safeguard specialist. A Resettlement Policy Framework has been prepared following local laws and policies of the World Bank OP4.12 which has been submitted to Prime Minister for approval. According to an initial assessment and inventory the project would acquire about 54.7 ha of land to affect about 2,500 households (about 11,000 persons), about 1,200 of which would need to be relocated.

At the project designing stage, a great effort has been made to reduce the social impact through the changing design, realignment of the road routes and reducing the scale of the proposed roads and associated civil works.

Environment

The project is classified as a Category A project under OP.4.01 Environmental Assessment, due to the disruption caused by the construction of new roads in an urban setting, and the need for significant involuntary resettlement.  An International Consultant (MVA Asia) and the Hanoi Urban and Industrial Environment Research Center (CEETIA) have been engaged to prepare the Environmental Impact Assessment (EIA) and Environmental Management Plan (EMP) using a consultative process, as per Bank guidelines.  These documents will be disclosed locally and in the Bank’s Infoshop, as per the Bank policy on disclosure and OP4.01 on the Environmental Impact Assessment. The draft final report will be submitted to the Bank and disclosure before appraisal tentatively planned in June 2006.

The project will facilitate effective urban transport management in the city, and both the investment component and technical assistance component are designed to promote the environmentally desirable growth patterns. An Air Quality subcomponent has been designed to support Hanoi’s Air Quality Management program.

A final draft of the EIA is being prepared based on Bank review. The draft EIA identified negative environmental impacts associated with construction related disruption (temporary land occupation, generation of dust, soil erosion, spoil disposal, disruption of local traffic, sanitation of construction camps), noise (construction machinery and traffic), and the possibility of increased air pollution, and treatment of wastewater (primarily from the bus depot).  However, these impacts are not significant and can be mitigated to acceptable level through effective mitigation. It is concluded that the project will not have significant environmental impacts and all the adverse environmental impacts can be avoided, reduced and minimized provided the mitigation measures developed in EMP can be properly implemented. In addition, all of the project components have been designed to minimize any adverse impact on the physical environment; none of the components encroach on any environmentally sensitive areas.

Safeguard policies

| Safeguard Policies Triggered by the Project | Yes | No |
| --- | --- | --- |
| Environmental Assessment (OP/BP/GP 4.01) | [X ] | [ ] |
| Natural Habitats (OP/BP 4.04) | [ ] | [ ] |
| Pest Management (OP 4.09) | [ ] | [ ] |
| Cultural Property (OPN 11.03, being revised as OP 4.11) | [ ] | [ ] |
| Involuntary Resettlement (OP/BP 4.12) | [ X] | [ ] |
| Indigenous Peoples (OD 4.20, being revised as OP 4.10) | [ ] | [ ] |
| Forests (OP/BP 4.36) | [ ] | [ ] |
| Safety of Dams (OP/BP 4.37) | [ ] | [ ] |
| Projects in Disputed Areas (OP/BP/GP 7.60)* | [ ] | [ ] |
| Projects on International Waterways (OP/BP/GP 7.50) | [ ] | [ ] |

Annex 1: Country and Sector or Program Background

Vietnam:  VN-Hanoi Urban Transport Project

Hanoi, North Vietnam’s key economic node and the country’s capital, is a rapidly growing city of 3.2 million people (2005), with an average yearly population growth rate of about 3% in the last five years.  Projections indicate that the population may double by 2020, largely through rural migration (Vietnam’s urbanization level is presently only 23%).

In the last years, Hanoi’s economy has been growing at double-digit yearly growth rates, reaching a gross regional domestic product growth rate of 15% in year 2003. Such high levels of economic growth are putting tremendous pressure on the city’s physical infrastructure. In ten years, the number of daily trips (excluding walking) has doubled, reaching 6.5 million in 2005 (compared to 3.1 million in 1995) – a yearly growth rate of almost 8%. Hanoi People’s Committee (HPC) is trying to balance the conflicting pressures of preserving the city’s character (particularly a very attractive central area), while meeting the demands posed by high levels of continuing economic growth.

Motorcycles are the primary mode of transport accounting for 62.3% of vehicular trips (2005 figures). Bicycles carry about a quarter of trips (at 24.4%).  Automobiles and trucks account for 4.5% of trips and ownership is relatively low but growing rapidly (13 cars / 1000 people in 2005, compared to 8 cars / 1000 people in 2001 – the majority of existing cars being owned by Government or joint venture companies). Public transport was neither a central government nor a municipal priority in the initial years after the Doi Moi and by the end of the 1990’s, buses accounted for only about 2% of all trips. This has changed significantly in the last few years, with buses accounting for 5.8% of vehicular trips in 2005. Because of the high continuous economic growth, Hanoi has concerted its efforts to promote public transport as a key element of its urban transport strategies.

As transport demand rises, Hanoi is faced with numerous issues ranging from traffic management, to congestion, traffic safety, air quality, city planning and transport sector financing. In order to keep up with its economic growth and develop a sustainable transport system, the strategic foci for Hanoi should be to:

- Promote sustainable public transport system

- Develop an efficient management of the existing street system

- Initiate demand management framework

- Manage transport sector externalities (safety and air pollution)

- Promote cohesive transport and land development

- Examine financing options for sustaining transport sector development.

1. Promote sustainable public transport system

From an urban transport perspective, the predominant challenge for the City of Hanoi in the coming decade will be to facilitate spatial growth for future urbanization.  Motorcycles, the dominant source of mobility at present, have serious limitations as trip lengths grow. The role of the private automobile as a provider of mobility will continue to be minor; only a small minority will have access to automobiles in the coming two decades.  Successful development of efficient, high capacity, public transport systems – bus based systems in the short term, with a role for urban rail in the longer term – that ensure high quality access to commercial areas and central business districts, will be critical to facilitate continued urban growth.

Over the course of a series of decisions (No. 34/2003 NQ/HD, and No. 72/2004/QD-UB following No. 71/2004/QD-TTg of the Prime Minister) HPC established priorities to promote public transport with mode share goals for 2010 and 2020 (30% in 2010 and 50% share for 2020), and to reform the public bus sector by encouraging the participation of the private sector in the provision of bus services into a sector erstwhile dominated by TRANSERCO, a public transport monopoly.

1.1 Characteristics and performances of the current public transport system in Hanoi

1.1.1 Bus fleet

Hanoi’s bus operators were merged in June 2001 into a company called TRANSERCO, a State Owned Enterprise (SOE), which has been placed under the direct control of HPC in April 2004. The company has witnessed a spectacular development in recent years. The bus fleet size has increased from 237 buses at the end of 2001 to 708 at the end of 2003 (see Table A1.1). Similarly the number of passengers has also increased dramatically from the 2001 figure of 34,000 passengers per day to over 500,000 in March 2004.

Table A1.1: TRANSERCO’s Bus Fleet Details

| End of 2001 | End of 2002 | End of 2003 |
| --- | --- | --- |
| Fleet | Capacity | Fleet | Capacity | Fleet | Capacity |
| 238 | 9,147 | 413 | 23,115 | 708 | 41,035 |

1.1.2 Ridership

From a consumer’s perspective, the most welcome trend in the last five years has been the improvement in the conditions of public transport in Hanoi.  As a result of new buses (about 500), route rationalization, introduction of integrated fare structures (including monthly passes) and increased quality of service (bigger buses, more frequent service running longer), bus ridership has increased tremendously in recent years (see Figure A1.1). It appears that average daily ridership in March 2004 broke the half million barrier for the first time.

Figure A1.1: Daily bus ridership

1.1.3 Revenues

Daily revenue has also increased. Figure A1.2 shows the monthly revenues since June 2002 and it can be seen that while rider-ship has increased by 500% since August 2002, revenue has only increased by about 300%. This is due to the relatively slower growth of the single journey ticket passengers who account for about 70% of total revenue.

Figure A1.2: Monthly Revenue from Single Journey Ticket and Monthly Passes

As displayed on figures 1.1 and 1.2, one can see that although the single journey ticket represents only 30% of the share of rider-ship, it accounts for 70% of the revenues. On the contrary, student and adult passes, with respectively 60% and 10% of the share of rider-ship, generate only 30% of the revenues.

Nonetheless the total monthly revenue in March 2004 of VND15.6bn ($0.98 million) is a very healthy figure and represents an average daily income per bus in service of VND955,000 ($60) per day.

1.1.4 Performances of Hanoi’s bus system

1.1.4.1 Daily bus operation figures

Table A1.2 shows the performance of Hanoi’s bus system in March 2004:

Table A1.2: Performance of Hanoi’s bus system (March 2004)

| Average Daily Ridership | 508,000 |
| --- | --- |
| Average passengers per bus in service per day | 964 |
| Average speed of bus in revenue service | 18 kph |
| Average revenue per bus per day | VND955,000 (US$ 60) |
| Average fare per passenger carried | VND1000 (US$ 6.3 cents) |

Average bus revenue per day is quite low at $60, although the average number of passengers per bus per day is high (964). This is due to very low bus fares (average fare per passenger carried: 6.3 US cents), which has since been increased.

1.1.4.2 Bus fleet availability rate

From the information supplied by TRANSERCO with details of the number of buses actually in service, the availability rate of the fleet is 74%. This is a very low percentage especially bearing in mind the fact that many of the buses are only one or two years old (many buses have been purchased since 2001, and the average age of the fleet at end 2003 was very low at 3.4 years). Given the average fleet age, a figure of 90% or above would be expected.

1.1.4.3 Structure of TRANSERCO’s staffing

Details of TRANSERCO’s staffing at the end of 2003 are as given in Table A1.3 hereunder:

Table A1.3: Details of TRANSERCO’s staffing at the end of 2003

| Staff type | Number | Percent of total | Staff per bus PVR | Staff per bus in Fleet |
| --- | --- | --- | --- | --- |
| Drivers | 1,587 | 41% | 3.01 | 2.24 |
| Conductors | 1,651 | 42% | 3.13 | 2.33 |
| Maintenance | 159 | 4% | 0.30 | 0.22 |
| Other traffic staff | 274 | 7% | 0.52 | 0.39 |
| Management & admin | 235 | 6% | 0.44 | 0.38 |
| Total | 3,906 | 100% | 7.41 | 5.52 |

In most bus systems in developed countries the buses are “driver only” or “one person operation”. Since there is no need for conductors, considerable savings can be achieved as a result. While in Hanoi the wages are low at present, it is certain that they will rise and the sooner the conductors are phased out the better. The number of other traffic staff is not unreasonable although perhaps slightly higher than might be expected.

Maintenance staff levels are low by international standards at 0.3 per bus on the road or 0.22 per bus in the fleet. A figure of about 0.4 per bus in the fleet would not be unreasonable for urban bus operations. While the low figure may be workable while the fleet is young, it is likely that additional maintenance staff will be needed as the fleet ages.

Management and administration levels are somewhat high by international standards but the need for staff depends on the amount of reporting and other tasks which they are required to do.

1.2 Financial position of TRANSERCO

TRANSERCO has been operating at a loss since its inception and details since 2002 are shown in Table A1.4. Although there may be some uncertainties in the cost reporting, such as the depreciation issue discussed above, it seems that the figures presented below give a reasonable picture of the overall position.

Table A1.4: TRANSERCO’s Financial Position

|  | 2002 | 2003 | 2004 |
| --- | --- | --- | --- |
| Revenues | 63.8 VNDbn US$ 4.02 m | 144.1 VNDbn US$ 9.07 m | 200.0 VNDbn US$ 12.59 m |
| Costs | 117.4 VNDbn US$ 7.39 m | 221.3 VNDbn US$ 13.93 m | 285.7 VNDbn US$ 17.98 |
| Profit - (Loss) | (53.6 VNDbn) (US$ 3.37 m) | (77.2 VNDbn) (US$ 4.86 m) | (85.7 VNDbn) US$ 5.39 |
| Cost Recovery Ratio | 54% | 65% | 70% |

In the future, operating costs will keep increasing because of the following factors:

- labor costs will keep growing (the wages are low at present, and it is certain that they will rise);

- bus productivity will decrease as bus speeds get reduced because of growing congestion;

- maintenance cost will keep growing as the bus fleet becomes older.

As a result of increasing operating costs, the cost recovery ratio will keep growing. As a consequence, in 2005, Hanoi decided to adopt a new fare structure, with higher fares.

1.3 Public transport operating structure

1.3.1 Reduce subsidies

The municipal government in Hanoi currently subsidizes bus service, both bus purchase and operations.  However, if the subsidies continue to grow at the rate ridership has grown and is forecast to continue to grow, this political will be sorely tested.

Subsidies are based on regular, detailed cost audits. Such a system has significant limitations:  (i) there is asymmetry of information in that the operator always knows much more information than the regulator and has no incentive to reveal their true costs; (ii) the operators have no incentives to increase efficiency and reduce their costs; and (iii) monitoring costs are very high for government.

International experience suggests that public fiscal and transport interests (minimizing the financial burden associated with a particular level-of-service and fare level) are best served when operations are based on fixed-term contracts established by competitive bidding.

1.3.2 Introduce competition

An attempt has been made to introduce competition with private operators. The official position of the Hanoi government was spelled out in Interim Regulation Decision 71/2004/QD-UB dated May 14th 2004. This regulation indicated substantive reform of the public bus sector as for the first time provisions were specified to break the monopoly held by TRANSERCO. The regulation stated that HPC wished to encourage the participation of the private sector in the provision of bus services in Hanoi and specified that six new bus routes would be put out to tender in the near future. The Decision indicated that both SOEs and private sector companies could bid on the routes.

The same year, the Bank helped Hanoi obtain PPIAF funding to hire an international consulting firm to prepare a study on the restructuring options for the municipal public transport sector, and to advise the city on the manner in which to put in concession six new bus routes. The study provided a practical toolkit to support city policy makers to develop procedures to implement contracting, regulating, institutional and financing options to secure a more market based approach for engaging the private sector in providing urban bus transport services.

The six routes were put out for tender in December 2004 and the evaluation was completed in early 2005. Two companies shared the six routes (five to one operator, one to another). The bidding was done using gross cost contracts (see Table A1.5).

Table A1.5: Bid evaluation methods: gross cost vs. net cost contracts.

| Gross Cost | Service specified precisely. Bid judged on lowest operating cost; all revenue accrues to government |
| --- | --- |
| Net Cost | Service specified precisely. Bid judged on lowest net cost, i.e., shortfall between costs and revenue; |

None of the enterprises under TRANSERCO submitted bids which avoided any debate about the achievement of the government policy to encourage the private sector through the tendering of the rights for the six routes.

The willingness to reform appears to be widely held and strongly supported by central government. This is an encouraging start although two issues are still at stake:

- The level playing field with TRANSERCO needs to be solved. Incentives have to be provided for TRANSERCO to bid without having to risk that the rates get any lower in the short term. Indeed, if TRANSERCO were to bid for new routes and offer fares any lower than the current ones, the city would need to reduce the overall fare structure. At the same time, TRANSERCO should not be given an unfair advantage in the bidding process.

- Hanoi expressed interest to move to net cost contracts. There is an urgent need for the city to develop a revenue allocation system between routes.

1.3.3 Develop an independent regulatory and planning authority

Until 2004, Hanoi’s bus system was operated by a single, state-owned undertaking, Transerco. Transerco was largely responsible for planning and supervising its services. As a result, the planning body Transport and Management Operation Centre (TRAMOC) had a limited planning and regulatory role, and has not developed high-level capability in these fields. However, the public transport sector in Hanoi is now undergoing fundamental reform. The first private bus operators were selected by competitive tender in 2004 and have recently commenced operation; and the project-financed BRT system, light rail lines are under consideration. A common electronic fare collection system is being developed.

These changes will require a more systematic and sophisticated approach to government’s key roles of monitoring the public transport system, planning an integrated network and services, and imposing plans and strategies on the operators through their operating contracts. In addition, the current practice of subsidizing public transport services will continue; revenue will be collected by the authority and disbursed to the operators in accordance with their contracts.

The recommendations from previous studies proposed the creation of a high level Public Transport Authority (PTA) to take over the functions of TRAMOC and a series of measures designed to gradually reduce the involvement of the state owned bus operator in favor of more private sector involvement.

The introduction of a BRT system in the near future has increased the urgency to strengthen institutions and make progress with the tendering of bus routes. The initial thinking on the provision of services on the BRT system is that the bus services themselves will be selected through tender and that the private sector should be involved. Thus there is a need to have an agency to manage the BRT infrastructure and operation, a need to specify services and tender for the procurement of these services – and ultimately all other services in Hanoi, to monitor and regulate all tendered and negotiated services and to generally take full charge of public transport in Hanoi.

Such a regulatory and planning authority would need to be properly budgeted, independent of operators as well as public sector road infrastructure agencies, and be able to perform the following functions:

  - Long term public transport planning

  - Co-ordination of all existing and new schemes in conformity with the plan

  - Procurement of service providers on a contractual basis

  - Control of common infrastructure (e.g. terminals)

  - Control of finance, including ticketing and revenue collection

Hanoi recently decided to create such an independent authority under TUPWS.

1.4  Key challenges relating to public transport addressed in the current project

- Development of a BRT system on two major corridors in Hanoi to address the problems of increasing capacity in the public transport system in a cost effective manner.  The BRT also preserves the speeds of the bus system amid growing congestion.  Indeed, as incomes rise and motorization increases, congestions on the mixed-use lanes will also increase the attractiveness and competitiveness of the BRT.

- Support the newly established Public Transport Authority with training, capacity building and support needed to coordinate between different operators and different modes of travel.

- Support further reform in the bus transport industry.  The BRT lines will be operated by operators chosen by a competitive concession.  Hanoi plans to continue to award new and eventually existing routes using competitive tenders.  Hanoi is also looking to develop revenue sharing mechanisms that will allow the city to sign net cost rather than gross cost tenders in a multiple-operator environment.

- Technical assistance to develop subsequent phases of the BRT system.

2. Develop an efficient management of the existing street system

2.1 Create a culture of traffic management

Poor traffic organization remains a critical issue contributing to accidents, congestion and consequently air pollution, despite concerted efforts in Hanoi focusing on safety and traffic management.  There is a perception that international good practice is not completely transferable.  This is partially justified; some of the standard tools of international traffic management (round-abouts, junction channelization etc.) need to be modified for a predominantly motorcycle traffic stream before they can be effective in the Vietnamese context. However, properly adapted, the adoption of these and other tools (traffic lights, medians, an enhanced focus on a properly maintained secondary road system) will significantly enhance efficiency and safety.  There is a need to create a culture of traffic management, based on pilots, and a willingness to experiment. The issue is not only to reduce accidents but to improve traffic order.

2.2 Enforcement: the problem of fragmentation of responsibilities

Such a culture of traffic management is currently inhibited by excessive fragmentation of responsibilities between five agencies with different yet overlapping responsibilities as follows:

(1)	Traffic Police: responsible for operations and most enforcement, more precisely: responsible for everything occurring "curb to curb" on the carriageway; mainly concerned with moving vehicles, although they will also deal with illegal on-street parking.

(2)	Local Regulation Police: responsible for stationary vehicles and activities including off-street public parking, hawkers and stockpiling of goods.

(3)	Public Works Department (TUPWS): its function is "to protect transport infrastructure" and they are responsible for activities in off-street private areas; dealing with illegal activities including parking and stockpiling of goods. They are also responsible for planning, designing, and implementation of road works.

(4)	Military Police under the Ministry of Defense: override all the others when necessary.

(5)	Volunteer civilians: supporting the other agencies.

Hanoi needs to find solutions to the problem of fragmentation of responsibilities.  The concept of natural enforcement by good physical design would minimize the enforcement required by the traffic police.

  - Key challenges relating to traffic management addressed in the current project

- The project will support extensive on-street traffic management measures to complement the proposed BRT system.  The measures will be designed to minimize the disruption to other traffic from the BRT and to facilitate safe and convenient access to and from the BRT for pedestrians and cyclists,

- The project will continue the support to the traffic command center initiated in the Hanoi component of the previous Bank financed Vietnam urban transport improvement project.  This will include the retroactive financing of an ATC system as well as additional traffic control equipment.

3. Initiate demand management framework

3.1 Ownership restrictions

Besides promoting public transport, thus far, efforts to control congestion, which is rapidly increasing, have focused on limiting motorcycle ownership in the urban districts of Hanoi by fiat.  Such controls are neither equitable nor effective (the rules have proved to be easily circumvented by registering vehicles outside the restricted districts).  There is a need for Hanoi to develop a comprehensive policy on managing congestion that includes consideration of restrictions on ownership and use of both motorcycles and cars, a parking policy, promotion of non-motorized modes for short trips and more effective traffic management.

3.2 Car ownership

Though car ownership is low (13 cars per 1000 people in 2005, compared to 8 cars per 1000 people in 2001) in part because of high auto taxes levied by the Central Government, and some municipal regulations, such as a requirement in Hanoi to demonstrate availability of parking before an auto can be registered, there is a urgent need to focus on auto use restrictions:  motorization levels are rising (the number of registered cars has been growing at roughly 16% per annum in the last four years), and even a small increase in auto traffic will significantly increase congestion.   In the longer term, the cities need to consider market-based methods to manage private vehicle ownership (auctioning titles) and use (congestion charges, parking charges). In this context, the development of a current vehicle registration system for all vehicles including motorcycles which requires users to update their registration regularly (annually, every two years) will be key to enforcement efforts.  Such a system is a basic tool that will also be a cornerstone of any attempts to manage traffic compliance, safety and air quality.

3.3  Key challenges relating to demand management addressed in the current project

- Technical assistance to examine the use of economic instruments as alternatives to command-and-control policies to manage use and ownership of motorized vehicles.  The assistance will also examine the potential of parking policy in combination with a parking enforcement policy to support congestion management.

- The project will support the Traffic Inspection Board under TUPWS, partially responsible for parking enforcement, with equipment and training.

4. Manage transport sector externalities - Safety and air pollution

4.1 Safety

High levels of motorcycle-related accidents remain a significant problem (though Hanoi has achieved significant reductions in accident rates in recent years with an enhanced focus on traffic compliance and stricter licensing/insurance procedures).  The most egregious problem in this context is a waiver from the obligation to wear helmets inside city limits in the national law.  In the coming years there will be a need to develop multi-institutional strategies that focus on driver training and other education/outreach, vehicle testing and enforcement, coordination with health and emergency response, promoting seat belt use etc.  In the longer term, a well-functioning competitive insurance sector that ties premiums to safety/compliance records may have a significant role to play.  At present cities’ ability to effective enforce/monitor compliance with traffic rules is limited by the absence of a regular vehicle registration requirement/system.

4.2 Air quality

Though Vietnam has successfully phased out lead from gasoline, Hanoi still has air quality problems. The majority of the vehicle stream is motorcycles.  2-stroke motorcycles have been banned for some years and the indications are that most of the current fleet consists of relatively clean 4-stroke engines.  Analysis of available data from Hanoi suggests that transport is a significant contributor to particulates (PM10 and PM2.5), Ozone formation and locally to Carbon Monoxide (CO) and old motorcycles and diesel trucks are the biggest polluters in aggregate.  Hanoi needs to do additional work to refine its understanding of transport’s contribution to pollution and as appropriate develop control strategies including promotion of non-motorized modes for short trips and the development of inspection and maintenance programs.  Institutional fragmentation limits the effectiveness of air pollution control efforts at present.  Until recently, the 5 air quality monitoring stations in Hanoi were operated by 3 different agencies and no integrated monitoring reports are available.  Further, DONRE the lead agency responsible for air quality monitoring till recently did not consider emission control a core element of its mandate.

4.3  Key challenges relating to safety and air quality addressed in the current project

- Safety.  The project will support training and enforcement related equipment for the traffic police and support the development of traffic management measures that would create a safer traffic environment particularly for pedestrians and NMVs.

- Air quality.  A comprehensive air quality management plan has been developed that includes additional monitoring equipment, the development of an air quality inventory, development of a comprehensive emission controls strategy and the examination of economic instruments to address air quality issues.  Motorcycle clinics are planned to understand and raise awareness of the role of motorcycles in ambient air quality.  During preparation much of the focus has been on institutional issues related to air quality management.  Hanoi’s recent decision to consolidate the management of existing air quality stations in the City allayed some of the Bank’s concerns related to institutional fragmentation.  There is also an increased appreciation of the need to extend DONRE’s mandate to include both air quality monitoring and control in order to obtain any benefits from air quality management investments.  During implementation there will be a continued effort to address these institutional challenges through continued dialogue.

5. Facilitating growth with cohesive transport and land development

Given the extremely high population densities in urban Hanoi (about 272/hectare for the inner districts rising as high as 400 for Hoan Kiem district), growth in the urban area will require spatial growth.  Hanoi has an ambitious spatial growth plan based on leading investments in road infrastructure.

However, to maximize their benefits, investments in public transport and road infrastructure will need to be coordinated with, and complemented with, an enhanced focus on urban planning to ensure that growth is coordinated along high density corridors. Much work is still needed to transform a planning tradition based on a centrally planned economy to a more flexible process, responsive to the demands of a market economy, with the implementation and monitoring capabilities to manage urban growth effectively.  Also important is a need to develop metropolitan/regional institutions that can coordinate between local governments to minimize the incentives for jurisdictional boundaries to distort development.  Additionally, currently, the process of land takes for public infrastructure is hindered by the absence of a well functioning market in land.  Though the current land law comes closer than its predecessors to recognizing market values of land, land values in the major cities remain excessive relative to income levels due to a variety of market-distortions, and exercising eminent domain still requires a process of complicated (and often very lengthy) negotiations. Additional reforms are still needed to normalize urban land title and tie compensation levels to market valuations of land so that the land-take process can be streamlined (though care needs to be taken that the process protects the interests of those from whom the land is taken).

Similar efforts are needed to support the transport planning mechanisms in the major cities.  First, responsibilities are excessively fragmented:  Hanoi has different agencies planning and implementing rail and bus systems with minimal coordination.  It is critical that all elements of the public transport system are coordinated, integrated and present the ‘customer’ a seamless experience.  Unified responsibilities should also help the process of prioritizing; existing transport master plans for the major cities include very expensive investment ‘wish-lists’ formulated without budget constraints.  Until resource constrained plans clarify that some investments (such as urban metro systems), however beneficial, need to be deferred to the future, it will be difficult for city authorities to focus on what are often perceived to be ‘second-best’ though financially affordable solutions (such as bus-based systems), in the short term.

5.1  Road infrastructure expansion to facilitate growth

Master plan calls for no more growth in the inner city.  Regardless of the realism of that expectation, it is likely that once road infrastructure is available, significant new growth can be expected in newly urbanizing areas west of the third ring road (south of red river), Tay ho district west of West Lake and in Dong Anh district north of the red river.

5.2 The urban planning system in Vietnam

The term “urban planning” as used in western countries for the design and integration of urban functions is not readily applicable to Vietnam.  Three types of plans, each the responsibility of different ministries, apply to urban areas: socio-economic development, sector development, and spatial design (also called construction or master plans):

- Socio-economic development plans – are development strategies, but also set precise development and investment targets and combine (often without prioritizing) proposals contained in sector plans (e.g. transport, industry, education, health). They are prepared at all levels of government including wards and communes and consolidated at higher levels.

- Spatial plans – present the proposed spatial arrangement of land uses, building footprints and infrastructure for a province, city, district, or development site in progressively greater detail. Physical plans in Vietnam are variously translated into English as “spatial plans”, “master plans”, or “construction plans”.

- Sector development plans – are production targets and strategies for output of individual sectors e.g. water supply, urban transport industries, etc.

Table 1.6: Preparation process for each of the three types of plans applying to

urban planning in Vietnam

| Types of plans | Preparation process |
| --- | --- |
| Socio-economic development plans | Based on the five-year socio-economic development plan (SEDP). SEDP are prepared after formal consultation within government and Party structures. The Ministry of Planning and Investment (MPI) has the primary role in coordinating and ultimately producing the SEDP. At the provincial level, the Departments of Planning and Investment (DPI) take the lead role. A bottom up approach is adopted. Each level of sub-national government (communes, districts, provinces) submits proposals to the next level where they are consolidated and passed on up eventually to MPI where they are consolidated for the whole country. |
| Spatial plans | Most plans are prepared by the National Institute of Urban and Rural Planning Institute (NIURPI), or its sister organization in the south, NAGECO. Both are subsidiaries of MOC. Only the three largest cities have their own planning institutes. Spatial plans are prepared in four levels of detail: orientation plans (national policy), regional plans, general plans (province or city), and detailed area plans (ward, industrial zone, or project). Most are prescriptive for specific land uses in specific locations, rather than permissive as in Western land use planning. This lack of coordination is probably exacerbated by the fact that the planning institutes tend to overlook economic and social dimensions, while the economic planners (equivalent institutes affiliated with MPI) seem to overlook the spatial and environmental implications of investment programs. The result is that spatial plans are too abstract with insufficient attention given to the “real world”. General spatial plans are required to include long and medium term direction for physical development and the arrangement of urban space and infrastructure networks and facilities. They also cover the characteristics of urban areas, population size, land use, resettlement, redevelopment, conservation, and zoning. The technical master planning specifications that drive plan design, city investment priorities, and city classification reduce local flexibility. The Prime Minster approves the general plans for Special, Class I and Class II cities. Detailed area plans are prepared under the guidance of sub-national People’s Committee. They predetermine the specific uses of urban space and include the quality, quantity, and position of each development type and building footprint. Spatial plans (general and detailed plans) are not generally converted into specific short-term programs and budgets and are not dependent on anticipated resources. They do not include identified strategies for reaching their vision. |
| Sector development plans | The overall goal of sector planning is the maintenance of the socialist market-oriented economy, particularly for major industries and agriculture. Sector plans are also prepared for infrastructure. The main planning functions are divided between ministries at the national level, departments at the provincial level, and the State Owned Enterprises (SOEs). Sector plans and spatial plans for the same location may not be linked in phasing, finance or implementation. |

5.2.1 The new Land Law

Government made the new Land Law a new priority. It went into effect on July 1, 2004, but will take several years to become fully effective. Under the law, all land continues to be owned by the State, but land regulation and management will become more market oriented.

In the past, allocation of land use right certificates by Government to SOEs, companies, organizations, and individuals has created problems in providing adequate and timely infrastructure. The sequencing of land allocation did not necessarily follow the development proposed in spatial plans, the provision of infrastructure, or the timing of the financial allocations for state sector activity. Significant differences between the price of land set administratively by the government, and the price on the informal, but vibrant, real estate market, contributed to speculative development that was not synchronized with the provision of infrastructure. The price distortion promoted corruption and also created significant delays to investment projects arising from protracted negotiations of compensation for land acquisition. The new Land Law should improve coordination, governance, planning, management, and the ability to provide infrastructure. Key improvements include:

- Modernization of state land ownership and administration

- Use of market values for establishing compensation, taxes, and fees (given the imperfect mechanics of the current market, it is however difficult to identify a true “market” rate)

- Recognition of real estate markets

- Devolution of responsibility to local levels for land administration and registry and promulgation of uniform standards and local single points of contact for land registration

- Greater availability of land registration information

- Public participation in planning and public notification of approved plans

- Consolidation of land use right certificates into a single type

- Improvements in compensation procedures for expropriated land

- Local officials to become more accountable

- Long term leases for foreigners and overseas Vietnamese to become transferable.

5.2.2 The new Construction Law

The most significant changes introduced by the new Construction Law (2004) are incorporated within the new Decree on Planning and in Construction Investment Project Management, both of which were enacted in early 2005. The main new features of the Planning Decree are:

- Decentralization of the responsibility for preparing spatial plans to Peoples Committees for most cities and provinces.

- Decentralization of the approval of plans for Class III and IV cities to Provincial and District Peoples Committees respectively.

- Review of plans by elected Peoples Councils.

- Addition of broader brush “Orientation Plans” covering 20 year time periods for Special, Class I and Class II cities.

- Addition of regional planning requirements. This is a useful step towards helping deal with rapid urbanization. However, no guidance is given on the administrative structure that will be necessary to implement regional planning.

- Coverage of the redevelopment of existing urban areas (instead of just new construction). This is significant. It requires that spatial plans should take account of areas that can be upgraded rather than focusing only on re-development which has been the case in the past.

- The addition of an urban design component to detailed construction plans. This is intended to address the lack of an effective development control framework for the urban form, architectural patterns and landscapes.

- Introduces competition in the planning process – People’s Councils are required to review plans and the plans must be put on public display. However, there are still no specific requirements or mechanisms to promote active public participation in the process.

5.3 Planning issues and problems affecting infrastructure

There are a wide range of urban management and planning issues that affect the ability to provide infrastructure.  In the simplest terms, it is a question of the resources available for infrastructure.  However, even if there were sufficient resources, the institutional situation would not permit government to provide the required infrastructure efficiently and systematically. The main issues include the following:

5.3.1 Fragmentation and lack of coordination

Planning of all types tends to be centrally driven and top-down.  It is not yet affected by moves toward decentralization.  The planning systems are intricate and, in theory, socio-economic, sector, and physical (construction) planning are integrally interrelated.   In practice, physical planning is often isolated from reality and from the local social, economic and physical situation.  This increases the impracticality of the physical plans and reduces their relevance and local commitment to follow them.   Absence of public participation in planning also reduces plan’s acceptability and ultimate usefulness.

The physical planning system lacks the ability to insure the relevance of the plans and the ability to manage, enforce, or adhere to them.  In the practical world, even official development elements may not be tied together.  For example, the Ministry of Construction and departments of (MOC) in the provinces (usually through MOC’s Urban and Rural Planning Institute) are responsible for physical plans and the issuance of building permits, and in some cases actual construction by Ministry or department SOEs, but have not control over the provision of timing of off-site infrastructure or transportation systems.  There is a general inability to manage, implement, or enforce plans, particularly in the context of other urban activities and decisions including financing.

Plans at all levels are made without apparent reference to financial reality or cost.  For urban planning to be useful, financing and budgeting for state sector responsibilities and projects must be an integral part of the process

5.3.2 Idealized top-down spatial plans

The physical plans are purely spatial and are reminiscent of the “city beautiful” genre in Western urban planning.  The visions lack the phasing and the incremental development mechanisms to translate them to the reality of development in a market economy where development is likely to occur on a piecemeal and “unplanned” basis governed by the availability of land on the market and capital to the developer.

5.3.3 Rigid technical specifications

The rigid single purpose technical master planning specifications that drive plan design, investment, and city classification may effectively reduce efficiency and not meet demand.  They reduce local flexibility and creative or strategic thinking.  The technical standards should have only a limited and guiding role in a reformed planning system that will allow greater flexibility and adaptability to local situations and demand.  For example, technical standards must be modified through a formal and arduous process to officially allow infill development, urbanization of villages, or urban upgrading without requiring maximum (standard) street widths, specified floor area ratios, or standardized floor area per occupant.

5.3.4 Lack of strategic planning

The legacy of the socialist and top down command and control planning process has not permitted flexibility, particularly at the level of cities or provinces that would help them in determining their most pressing local needs, their comparative advantage, or their ability to influence their own future.   No metropolitan level planning agency exists and political and institutional issues related to jurisdictions lead to sub-optimal planning decisions.

5.4 Key challenges relating to road infrastructure and urban growth addressed in the current project

- The project is financing the section of the second ring road between Nhat Tan and Cau Gaiy, a technically challenging but important link in Hanoi’s road network, imperative to facilitate growth west of West lake and to link the city to the Nhat Tan Bridge over the red river being financed by JBIC (under construction).

- The project is financing the extension of Hoang Quoc Viet road west of the third ring road.  This road increases the city’s access to the fast developing Thang Long industrial zone and facilitates development west of the third ring road, a priority development zone for the city.

- The project is financing technical assistance relating to urban planning that will review existing plans, institutional arrangements, planning regulations and procedures.  The TA will support modifications in procedures, plans to ensure closer coordination between transport and urban planning and more effective plan implementation.  The technical assistance will support the DAPM to implement these recommended strategies in selected locations in the newly urbanizing areas to facilitate growth conducive to competitive public transport.

6. Examine financing options for sustaining transport sector development

Efforts are also needed to strengthen the tools available to Hanoi to finance infrastructure.  These include the development of instruments to tap the capital markets, other forms of borrowing, and the development of fee-based revenues from sources such as vehicle registration; parking etc.  A particular challenge is to develop effective strategies to govern the role of the private sector.  Presently, negotiations are underway with private/bilateral financiers in Hanoi to finance (and in some cases operate) urban rail links.  The challenge in such situations is to allocate/distribute risk in a manner that facilitates investments while limiting the city’s exposure and protecting public interests. International experience suggests that while the private sector has the potential to make a significant contribution to infrastructure finance, public benefits are maximized when transparent competitive processes are used.

Annex 2: Major Related Projects Financed by the Bank and/or other Agencies

Vietnam:  VN-Hanoi Urban Transport Project

| Bank-financed Projects |
| --- |
| Ongoing | Sector Issue | Supervision Ratings |
|  |  | IP* | DO† |
| Mekong Transport and Flood Protection (Cr.3448-VN) | Reform basic institutional aspects of road management and improve access in Mekong Delta | S | S |
| Inland Waterways and Port Rehabilitation Project (Cr.3000-VN) | Improve main inland waterway route in Mekong Delta and strengthen operations and management | S | S |
| Second Rural Transport Project (Cr.3306-VN) | Improve access to remote rural areas, sustain adequate maintenance | S | S |
| Urban Transport Improvement Project (Cr.3125-VN) | Strengthen decentralized authority, expand capacity, and improve operating conditions of urban transport | S | S |
| Road Network Improvement Project (Cr.3843-VN) | Improve road management and maintenance funding for national roads | S | S |
| Vietnam Road Safety Project |  |  |  |
| Completed | Sector Issue | OED Evaluation |
|  |  | Out-come | Sustain-ability | ID Impact |
| Rural Transport Project (Cr.2929-VN) | Improve access to remote rural areas, sustain adequate maintenance | S | S | S |
| Highway Rehabilitation Project (Cr.2549-VN) | Reduce rehabilitation backlog; build institutional capacity; review and improve regulation, standards, and traffic safety; strengthen road maintenance operations | S | S | S |
| Second Highway Rehabilitation Project (Cr.N013-VN) | Reduce rehabilitation backlog; increase the volume of periodic maintenance; build institutional capacity; improve regulation and improve traffic safety; improve rural access; strengthen environmental protection | S | S | S |
| Pipeline | Sector Issue |  |  |
| Mekong Transport Infrastructure Development Project | Develop multi-modal transport in the Mekong Delta through improved regulation and infrastructure |  |  |
| Hanoi Urban Transport Project | Promote Bus Rapid Transit in Hanoi and strengthen the institutional framework for public transport. |  |  |
| Northern Triangle Infrastructure Development Project | Develop multi-modal transport in the Red River Delta area |  |  |
| S = Satisfactory; L=Likely; SB = Substantial; M = Modest; NR = Not Rated *—Implementation progress; † — Development objective |

| Other Development Agencies |
| --- |
| Agency | Project | Status | Duration |
| ADB | Second Road Improvement | Completed | 1997–2003 |
|  | Third Road Improvement | Ongoing | 1998–2005 |
|  | GMS: Ho Chi Minh City–Phnom Penh Highway | Ongoing | 1998–2005 |
|  | GMS: East–West Corridor | Ongoing | 2000–2005 |
|  | Provincial Roads Improvement | Ongoing | 2001–2006 |
|  | Central Region Transport Network | Preparation Stage | 2005–2010 |
|  | GMS: Kunming-Haiphong Corridor | Preparation Stage | 2005–2010 |
|  | GMS: Southern Coastal Corridor | Concept Stage | 2006–2011 |
|  | Implementation of Sector Development Policy (Road Information and Management System) | Consultants presently being recruited | 2004–2005 |
| JBIC | National Highway No. 5 Improvement Project | Ongoing | 1996–2004 |
|  | National Highway No. 1 Bridge Rehabilitation Project | Ongoing | 1996–2005 |
|  | Hai Van Tunnel Construction Project | Ongoing | 1997–2007 |
|  | National Highway No. 10 Improvement Project | Ongoing | 1998–2007 |
|  | National Highway No. 18 Improvement Project | Ongoing | 1998–2008 |
|  | Second National Highway No. 1 Bridge Rehabilitation Project | Ongoing | 1999–2004 |
|  | Transport Infrastructure Development Project in Hanoi | Ongoing | 1999–2006 |
|  | Saigon East-West Highway Construction Project | Ongoing | 2000–2007 |
|  | Binh Bridge Construction Project | Ongoing | 2000–2007 |
|  | Red River (Thanh Tri) Bridge Construction Project | Ongoing | 2000–2008 |
|  | Bai Chay Bridge Construction Project | Ongoing | 2001–2008 |
|  | National Highway No. 1 Bypass Road Construction Project | Ongoing | 2001–2009 |
|  | Can Tho Bridge Construction Project | Ongoing | 2001–2009 |
|  | Third National Highway No. 1 Bridge Rehabilitation Project | Ongoing | 2003–2009 |
|  | National Highway No.3 Improvement Project | Proposed | 2005– |
| JICA | Traffic Safety Program | Ongoing | 2004–2005 |
| JBIC/DFID | Transport sector coordination | Ongoing | 2003- |
| NZ/DFID | Transport Safety Design Work | Design | TBC |

Annex 3: Results Framework and Monitoring

Vietnam:  VN-Hanoi Urban Transport Project

| Development and Global Environment Objectives | Project Outcome Indicators | Use of Project Outcome Information |
| --- | --- | --- |
| Development Objective: To support Hanoi in implementing sustainable strategies to increase the efficiency of the existing transport infrastructure and develop compatible urban growth plans. Global Environmental Objectives: Shift to more cost-effective and sustainable transport modes and compatible urban development plans in Hanoi and their replication in the region. Lower Hanoi transport-related greenhouse gas emissions. | Public transport mode share along project corridors and areas Number of public transport trips Herfindahl-Hirshman Index (HHI) for bus operations Population in (Dong Anh and west of west lake districts) within 500 m of bus stop with 40 minute service to Kim Ma (including wait times) Reduction of tons of CO2-equivalent over 15 years (to 2020) | Supporting decision-makers in the urban development of Hanoi on an ongoing basis. |
| Intermediate Outcomes | Intermediate Outcome Indicators | Use of Intermediate Outcome Monitoring |
| Component 1: Development of a Bus Rapid Transit System (BRT) Completed BRT works and commencement of operations, including pedestrian and NMV improvements | Progress rate of works Procurement progress Change in bus travel times on corridor relative to system wide travel times | Monitoring of implementation progress and action plan to address possible delays |
| Component 2: Strategic Road Infrastructure and Sustainable Urban Planning Completed physical works and the beginning of operations Adoption of integrated sustainable urban land development and transportation planning in Hanoi | Progress rate of works Implementation of pilots on land-use Staff of HPC Urban Sector Departments Trained | Monitoring of implementation progress and action plan to address possible delays |
| Component 3: Program to Support Air Quality, Traffic Safety, the Public Transport Authority, Transport Policy and Replication Local capacity to plan, manage, and implement public transport Awareness and understanding of the transport-related actions needed to achieve sustainable outcomes | Air Quality and GHG Emissions inventory, and monitoring system in place Comprehensive motor vehicle management and emission control strategies identified and adopted Number of staff trained, skills assessment National and international outreach and replication activities completed | Monitoring of implementation progress and action plan to address possible delays |

Arrangements for results monitoring

|  |  | Target Values (Years) | Data Collection and Reporting |
| --- | --- | --- | --- |
| Project Outcome Indicators | Baseline | 2007 | 2008 | 2009 | 2010 | 2011 | Frequency and Reports | Data Collection Instruments | Responsibility for Data Collection |
| Public transport mode share along project corridors and areas |  |  |  |  |  |  | Mid-term review and project completion | Surveys | PMU |
| 1a. BRT corridors | 10% |  |  |  |  | 15% |  |  |  |
| 1b. Dong Anh and West of west lake districts | 1% (finalized at appraisal) |  |  |  |  | 10% |  |  |  |
| Number of daily boardings |  |  |  |  |  |  | Annual | Surveys, PTA reports | PMU and PTA |
| 2a. BRT corridors | 97,200 |  |  |  |  | 200,000 |  |  |  |
| 2b. Dong Anh and West of West lake districts | Finalized at appraisal |  |  |  |  | 3000 |  |  |  |
| Herfindahl-Hirshman Index (HHI) for bus operations: sum of squares of market share of operators | Finalized at appraisal |  |  |  |  | Change reflecting 2 more operators with one having 10% share | Annual | Based on market share from PTA reports | PTA |
| Population in (Dong Anh and west of west lake districts) within 500 m of bus stop with 40 minute service to Kim Ma (including wait times) |  |  |  |  |  |  | Mid-term review and project completion | Calculations based on population (from DAPM and DPI) and bus service (from PTA) | PMU |
| 4a. Number | ? |  |  |  |  | 5,000 |  |  |  |
| 4b. Share | 0 |  |  |  |  | 30% |  |  |  |
| Hanoi GHG emissions | Calculated in Y1 |  |  |  |  |  | Year 1, mid-term review and project completion | Estimates based on surveys | PMU consultants |
| Intermediate Outcome Indicators |  |  |  |  |  |  |  |  |  |
| Component 1: Development of a Bus Rapid Transit System (BRT) |  |  |  |  |  |  |  |  |  |
| Progress rate of works | 0 | 15 | 40 | 70 | 100 | 100 | Semi-annual PPR | PMU, Supervision | PMU |
| Procurement Progress |  | 30 | 60 | 100 | 100 | 100 | Semi-annual PPR | PMU, Supervision | PMU |
| Change in BRT travel times relative to change in system wide travel times travel times of BRT corridors system wide travel times | Finalized at appraisal |  |  |  |  |  | Within 3 months of operation of BRT lines, mid-term review, project completion | Operator records | PTA, PMU |
| Component 2. Strategic Road Infrastructure and Sustainable Urban Planning |  |  |  |  |  |  |  |  |  |
| Percentage of civil works completed |  | 0 | 10 | 30 | 70 | 100 | Semi-annual PPR | PMU, Supervision | PMU |
| Completion of Land-use TA |  | 10 | 50 | 100 |  |  | Semi-annual PPR | PMU, Supervision | PMU, DAPM |
| Implementation of Pilots on transit friendly land-use |  |  | 10 | 50 | 100 |  | Semi-annual PPR | PMU, Supervision | PMU, DAPM |
| Number of Staff trained |  |  |  |  |  |  | Semi-annual PPR | PMU, Supervision | PMU, DAPM |
| Component 3. Program to Support Air Quality, Traffic Safety, the Public Transport Authority, Transport Policy and Replication |  |  |  |  |  |  |  |  | Strategic Planning TA facilitator |
| Progress rate of works |  | 10 | 30 | 60 | 90 | 100 | Semi-annual PPR | PMU, Supervision | PMU, TUPWS, Traffic Police, DONRE |
| Adoption of emission control plan based on monitoring system and associated data |  |  |  |  |  |  | Mid-term review | PMU, Supervision | PMU, DONRE |
| Number of staff trained |  |  |  |  |  |  | Semi-annual PPR | PMU, Supervision | PMU, TUPWS, Traffic Police, DONRE |
| Number of replication activities (workshops, studies in other Vietnamese cities, study tours hosted) |  |  |  | 1 | 3 | 7 | Semi-annual PPR | MoT, PMU (for Hanoi activities) |  |

Annex 4: Detailed Project Description

Vietnam:  VN-Hanoi Urban Transport Project

This section includes a description of all of the project components and sub-components of the Hanoi Urban Transport Development Project, as it is necessary to provide context for the GEF components that are particularly emphasized. The overall project has three main components, of which several sub-components are seeking GEF funding:

(1) Development of a Bus Rapid Transit System (BRT)

- BRT System Design and Implementation, including pedestrian and NMV improvements

- BRT Stations, Interchanges and Terminals

- BRT Public Consultation, Communications and Media Strategy

(2) Strategic Road Infrastructure and Sustainable Urban Planning

- Strategic Road Implementation

- Integrated Sustainable Urban Land Development and Transport Planning

(3) Program to Support Air Quality, Traffic Safety, the Public Transport Authority, Transport Policy and Replication

- Air Quality Management Program

- Traffic Safety

- Public Transport Authority Strengthening

- Transport Policy Development

- National and Regional Replication and Information Dissemination

The information provided below includes estimated costs for each sub-component.

Component 1:  Development of a Bus Rapid Transit System (BRT)

(total US$87.29, US$75.29 million from IDA; US$8.00 million from the Government; co-financing from GEF US$4.00 million)

This component includes civil works, consulting services for design and supervision, and advisory services for project management. Civil works will include the development of segregated busways and bus priority on a selection of new and existing roads, the construction of BRT stops, interchange stations, terminals and maintenance facilities. It will also support the establishment of a modern BRT management system, including bus ticketing and financial controls.    Lastly, the component will finance the implementation of a public communications and media strategy for disseminating information on the BRT system.  The GEF is requested to co-finance the following three key barrier-removal sub-components: incremental civil works and studies/consultations to improve pedestrian and NMV access to the proposed BRT system (proposed GEF co-financing US$1.5 million); co-financing BRT stations to enhance their attractiveness for consumers with choice (i.e. motorcycle and automobile users) (proposed GEF co-financing US$1.7 million).; and BRT public consultation, communications and media strategy (proposed GEF co-financing US$1.5 million). Costs for land acquisition and resettlement and operating costs of the project implementing agency are included below, and will not be financed by IDA but by the Government.

Component 1.A:   BRT System Design and Implementation, and NMT and Pedestrian Access

(total US$67.99 million; US$60.42 million from IDA; US$6.27 million from the Government; US$1.3 million requested from GEF)

The BRT System will include segregated busways, 52 BRT bus stations, two BRT terminals, and six interchange stations.  This component will also finance consultant services for the construction supervision of all civil works activities, and the relatively minor land acquisition and resettlement costs are also included.  The GEF Intervention will focus on pedestrian and NMV improvements in the overall BRT design.

- BRT Busways

The BRT busways will have one lane in each direction with extra passing lanes at most stations, operating from the periphery of Hanoi to the city center; the Lang Ha corridor (from Ha Dong – Lang Ha – Hoan Kiêm Lake), and the Gia Phong corridor (from Giai Phong – Le Duan – Hòan Kiém Lake). The following are the general characteristics of the BRT lines.

- Length of BRT routes: Giang Vo – Lang Ha: 13.0 km. Giai Phong: 11.5 km Total: 24.5 km

- Alignment of bus lanes: 12 km in median, 6 km in second right hand lane, 8 km in left hand side on one-way streets, 0.3 km on right hand side on one-way streets

- Circulation: 20 km on segregated busways, 4.5 km on general traffic lanes

- Number of stations: 1 terminal, 6 interchange, 52 regular stations – all with 90cm high platforms permitting level entry/exit into/from BRT buses

- Rolling stock: Articulated buses, 17-18 m length, 2.4 to 2.5 m width, 170 passengers (6 passengers per square meter). Initial fleet: 60 buses.

- Energy : Diesel with Euro II standards

- Speed: Maximum speed in urban site: 50 km/h. Commercial speed: 22-24 km/h

- Frequency in peak period (2010): 3 minutes.

The selection of the BRT corridors is based on a proposal approved by HPC (Notice No. 19/TB-UB of 26 January 2005):

- The corridors follow the major desired transport demand line, from the south and southwest of Hanoi to the downtown area;

- The corridors generally follow roads and streets that facilitate the insertion of the BRT liens, without the need of land takings or resettlement expenses, and with reduced negative impacts on existing traffic;

- Both routes will go to the downtown area and around Hoan Kiem Lake, where people want to go and, thus, is the major generators of trips; and,

- Easy passenger transfer will be provided from one route to the other, thus, making them more attractive to users.

- Non-Motorized Access to the BRT System (US$1.3 million requested from GEF)

Special pedestrian and bicycle facilities have been proposed to increase the attractiveness of the BRT, and will be integrated within the design of the overall BRT System.  The focus will be on improving access by creating a friendly environment for non-motorized modes, particularly focusing on issues related to enhancing the pedestrian environment and increasing convenience, with consideration of the special needs of the handicapped, etc.  Such improvements will enhance the BRT stations, interchange stations and terminals, provide better access paths, and include special features in the signaling system.

The preliminary design of the BRT junctions aims to provide adequate width of signalized pedestrian crossing – with a separated phase for pedestrians so they can cross the junction without conflicting with vehicular traffic. Drop curb and colored road markings (yellow strip) will be used to enhance for the environment for both pedestrian and disabled wheelchair users. Enhancements will be made to structures surrounding the proposed BRT station, including design changes between walkways and the BRT station to facilitate access. Clear routes for pedestrians will be suitably delineated with pavement textures, colors, planting and street furniture. At the detailed design stage, sight lines and visibility will be assessed to ensure that landscaping and trees do not block sight lines at at-grade crossing points. Pedestrian crossings at traffic signals will be segregated so that they have a separate signal wherever possible, but more often than not cross simultaneously. To maintain the capacity of the junction, some minor turning movements will run parallel to the pedestrian phase, however, the vehicular traffic should give way to pedestrian movement. Channelisation and staggered crossings will also be introduced in the junction design to reduce the length of the pedestrian crossing to facilitate pedestrian crossings.

Facilities for people with special needs will also be provided.  Drop curb will be widely used at all crossing points to assist wheelchair users and other people with walking disabilities. Access to BRT stations will be by ramp and staircase and the ramp gradient is in a range of between 1:12 and 1:20 to facilitate disabled access under various site constraints. As appropriate, traffic poles will be equipped with push button and audible unit to serve the pedestrian demand as well as for people with vision impairment. Tactile guide ways, which are widely used in Asia to guide the people with vision impairment, shall be included in the detail designs.  In addition, Braille maps will show the BRT station layout and all other information for the people with vision impairment. These have been discussed with the Disabled Group Representatives on 4th October 2005 and they support the proposal of adopting this equipment to assist persons with disabilities.

GEF co-financing is proposed for the following five initiatives related to increasing pedestrian and cyclist access to the BRT:

1. Improving access in areas around BRT stations (about 250 m from BRT station). This will include incremental improvements to the street and sidewalk network, that will enhance the quality of this network in a radius of 250 m around BRT stations beyond the baseline conditions that the general street network in Hanoi is maintained at.  Based on surveys of users, improvements will include design enhancements including changes in street cross-section to enhance conditions for cyclists and pedestrians.  A primary outcome sought will be to increase the post-rain performance (ensuring that rains to not impact the functionality of the street system) of the streets and sidewalks in this high-impact demonstration zone.  The GEF Initiative #1 is proposed for convenience of pedestrian (including handicapped) to access BRT line, and is intended to encourage use of public transport.  The following design principles have been agreed upon.

- For less than 4 m wide road with no sidewalk:  The integrity of the existing cross-section will be respected. The road will be used by all of vehicle (mainly motorbike and bicycle) and pedestrian. Road mark for reducing speed will be applied for street/alley with more than 100m length.

- For more than 4 m wide road with no sidewalk:  Street cross-sections will be modified to enhance the pedestrian environment.  Dedicated pedestrian walkways will be demarcated.

- For more than 4 m wide road with sidewalk: Width of sidewalk less than 0.8 m due to permanent obstacles.  Street cross-sections will be modified to provide at least 1 m wide dedicated pedestrian facilities.

- Width of sidewalk more than 0.8 m due to permanent obstacles: Ensure sidewalk can be used by pedestrians.

- Crossing at intersection:

- Supplement low curbs and/or ramp at zebra crossing for intersections.

- Low curbs and/or ramp are located to ensure accessibility of handicapped.

- Zebra crossing are supplemented at crossing of more than 3 m wide road / alleys.

- Legal solutions will be applied to clear away impermanent obstacles in sidewalk and reduce motorized transport means when and/or where necessary.

2. Supplementing and constructing service structures and devices to support non-motorized transport in areas accessing to BRT line, such as motorbike and bicycle parking.

- 2 NMV parking facilities with capacity up to 1000 places at BRT terminals in Ha Dong and Phap Van.

- 5 medium inside parking (200 place capacity) at BRT interchanges and  10 small ones ( 20 to 50 parking place capacity) at BRT stops/stations.

- 10 other small parking at the Ancient Quarter near walking streets.

  - Constructing pilot complex pedestrian street sections.

Pilot pedestrian streets are proposed in 8 precincts adjacent BRT line. 4 resident areas are selected for each precinct to build pilot pedestrian street. A 200 m long section is selected for a resident area. (Total length of pilot pedestrian streets = 4 resident areas x 8 precincts x 200 m= 6400 m). The proposed pilot pedestrian section will have direct access to BRT, and will include traffic and instructional signage.

4. Training Activity.  Training activities intend to inform key staff of Hanoi Department of Transport and Public Work on public transport and parking system management. The staff will be tasked with supporting the BRT and parking management activities.

5. NMT awareness raising and public relations.  Training activities intend to make the campaign to raise community awareness on encouraging non-motorized transportation and pedestrian and to increase public transport demand.

Component 1.B:  BRT Stations, Terminals and Interchange stations (GEF US$1.4 million) (total US$18.0, US$14.87 million from IDA; US$1.73 million from the Government; US$1.4 million requested from GEF)

Under Component 1B, GEF co-financing is requested to support an architectural competition for station design as well as incremental support for station interiors and as appropriate climate control at selected stations. GEF co-financing of this sub-component will enhance the overall competitiveness of the BRT and specifically target consumers who have the choice of private vehicle modes (auto and motorcycle) and need to be persuaded that public transport offers an equal or better travel experience. GEF co-financing is requested to support an architectural competition for station design as well as incremental support for station interiors and, as appropriate, climate control at selected stations.

BRT stations.  BRT stations will be located along BRT busways to provide passenger access and egress to/from the system.  Stations will be located on sites where existing travel demand is concentrated, and will consider characteristics that are conducive to attract passengers, such as cross roads, wide sidewalks, and alleys joining the corridor with adjacent neighborhoods. All sites were visually verified in the field by the project’s specialists during rush hours and regular hours. Another planning criterion is the intended average distance of 350-500 m between adjoining stations, except for low demand sections, where the stations will be farther apart than the average. Other circumstances, such as areas with a high demand, determined the placement of a number of stations in some blocks, resulting in different lengths. Three main station types are to be included:

- Terminal (at Quan Lia or Van Dien);

- Interchange stations (Khuat Duy Tien, Hoa Muc, Kim Ma, Hoan Kiem, Linh Dam, and Nga Tu Vong); and,

- Regular stations.

Regular BRT Stations will have high-level platforms (at about 900mm above the carriageway) which will be covered against the rain and linked with the sidewalk by ramps at gradients convenient for all passengers, including elderly and handicapped persons.  Access will only be possible via turnstiles located at one or both ends of the station.  Most stations in central Hanoi will be located on one-way streets and serve passengers going in one direction. In the outer parts of Hanoi, the stations will be located in the center of the road and serve buses in both directions.  The widths of the platforms will depend on expected passenger demand, and the availability of space.

In summary, the proposed BRT stations would meet the following criteria:

- To ensure the distance of stations is about 350 – 500m on average.

- To be located in crowded areas with high traffic density; to meet the existing and future travel demand of passengers.

- To be located near junctions and other access facilities so as to interchange passenger to feeder bus routes or other bus routes and to facilitate their access from surrounding neighborhoods.

- Can be expanded when passenger volume increases.

- Location is suitable to landscape, not to cut many green trees, to minimize the removal of underground and above-ground works.

- To minimize the impact on adjacent shops and people living near the stations.

BRT Terminals.  According to the proposed trunk-feeder operation of the BRT system, the terminal is the first departure and also the last station in a closed service routine of the trunk-line services.  Feeder bus services will converge at the terminals where sufficient space will be provided for the convenient transfer of passengers between trunk-line and feeder buses.  The BRT terminal platform areas will be approximately 45 meters wide and 100 meters long. The terminals will include the following facilities: terminal platform area; office and commercial space; car parking; motorcycle and bicycle parking; green area; reserved area. Normally, terminals are located in the periphery of the city or near ring roads to attract private-vehicle users and deter them from driving all the way into the center. The introduction of BRT, will encourage some travelers to shift from using private motorized vehicles to public transport.   .

BRT Interchange Stations.  An interchange station is a station that facilitates the transfer of passengers from BRT to/from other motorized transport modes, particularly regular and feeder buses.  Thus, an interchange station is a place for traffic management of BRT buses, feeder buses and for other activities such as ticketing, fare collection, control and supervision.  Interchange stations will comprise wide platforms, bays for trunk routes, bays for feeder and district routes, and parking for bicycles and motor cycles.  In some specific cases, they may also include administrative offices, commercial areas for passengers, and maybe parking for buses.

Seven interchange stations are proposed, two near Ring Road 2, two near to Ring Road 3, one at Kim Ma, one at Bo Ho and one to be decided in the area of Hang Bai and Ba Trieu streets. An interchange platform is proposed for Hoan Kiem Interchange, to allow transfer facilities for passengers between BRT and feeder bus. Linh Dam Interchange Station is located in the southeastern corner of intersection Giai Phuong and Phap Van where the existing Phap Van Bus Station is situated. This interchange aims to serve the transfer passenger from the Third Ring Road (3RR) of Phap Van. Truong Chinh Interchange Station is located at the southeastern side of the alignment and situated at the northern corner of intersection Truong Chinh and Giai Phuong under Nga Tu Vong flyover. This interchange aims to serve the transfer passenger from Second Ring Road (2RR) and Truong Chinh.

Signal System. An important element of a functional BRT will be traffic actuated signal systems which will provide BRT priority at intersections, and include signalization at pedestrian crossings to and from BRT stations, to allow access when signalized intersections are relatively far from the station.

Bus Patios and Maintenance Facilities. Patios will be built near the two BRT terminals, at Quang Lai and Me Tri.  The former will be located at Quang Lai Pond and will require reclamation of approximately 3.5 hectares of land for the bus servicing and bus parking area.  The Me Tri patio will be located on the southern side of the 3RR via the Lang Ha Extension.   Administrative offices and commercial space will include a canteen to provide catering services for BRT drivers and administration staff and a staff changing room.

Bus Maintenance Facilities will be provided to allow mechanical bus repairs, as well as a bus washing area.  The bus wash area will entail operation automatic cleaning machinery. Additional area in the facilities will be allocated for spare part storage.  Diesel pumping stations will be located within the Maintenance Facilities to supply fuel to the BRT bus units.

Bus Ticketing System. To be finalized at appraisal.

GEF co-financing will be used to finance two initiatives that will focus on increasing the attractiveness of the BRT for current motorcycle and auto users.

1.  Design Competition.  The Feasibility Study consultants have provided basic conceptual designs for BRT stations and terminals.  However, the draft feasibility study notes the critical role stations have had in creating an upscale brand identity for the most successful BRT systems, particularly those in Curitiba, Bogotá and Quito.  The GEF co-financing will be used to finance a architectural competition to choose an attractive station design that will reflect Hanoi’s distinct identity.  This process will also have the side-benefit of increasing awareness and excitement about the BRT in Hanoi.

2.  Climate control and station design features.  The baseline BRT system doe not include climate control in the terminals and stations.  This will compromise the passenger experience, particularly in the Hanoi summer.  Moreover, as stated above, the baseline calls very basic design for the stations and terminals.  However, international experience suggests that attractive waiting areas, particularly transfer areas are critical to attract passengers away from private modes.  This experience is reflected in the form of a ‘transfer penalty’ coefficient that reflects a lower level of attractiveness for the BRT relative to private alternatives in the demand analysis.  The GEF co-financing will be used to lower this ‘transfer penalty’ an will focus predominantly in enhancing the functionality of the BRT terminals and transfer stations with features such as:  climate control, choice of materials etc.

Component 1. C:  BRT Consultation, Communications and Media Strategy ($1.3 million GEF)

The subcomponent will support the implementation of a public awareness strategy of the BRT system.  The public involvement strategy is intended to enable public participation in key decisions related to the BRT System, to keep the public updated on the progress and key decisions related to implementation, and provide a framework for public feedback into all elements of system design and operation. In addition, the subcomponent is intended to support a media management strategy, which will provide media content and appropriate materials for TV, radio, print, and public billboards and facilitate the media’s ability to promote the BRT concept. Overall, this subcomponent will reduce risks associated with the acceptability of the BRT system by the public by increasing allowing for early awareness and understanding of BRT.

The estimated cost of developing and implementing the BRT Public Communications Strategy is US$1.5M and will be procured using QCBS methods.

- Public Consultation and Communication Strategy

| Sub-components of Public Relations Strategy | Sub-Component Description |
| --- | --- |
| (a) Series of stakeholder consultations targeting input from the general public and other key stakeholders | Additional focus groups, and consultations with street (neighborhood) communes and shopkeepers associations and guilds in affected areas will be held periodically. All of the above consultations will be used as key opportunities for awareness raising among concerned citizens. In addition, effort will be made to document the changes in public sentiment and understanding of BRT during the course of the project by the administration of surveys at the stakeholder consultations. |
| (b) Build up BRT Website Organize a “Design BRT Website” Contest | The website is a necessary tool to channel and disseminate information about the BRT project, and will address the following: Explanation of a new kind of public transport; Success cases studies in carrying out BRT model; Benefits or advantages gained from BRT implementation; The necessity for development of BRT system in Hanoi; BRT’s routes and lines; Regularly updates on project’s status; and, A forum between the project management unit (PMU), other stakeholders and the public to build up goodwill towards BRT system, exchange ideas and give answers to related issues raised by the public. The design of the BRT Website may be done through a contest, which is aimed at attracting the public’s attention as well as heightening their awareness of this new type of transportation service. Participants would be Vietnamese citizens, and the contest would be held in cooperation with local and national media (such as Voice of Vietnam, Hanoi TV, New Hanoi Daily or The Youngster, etc). The contest duration is estimated at 4 to 6 months, with awards provided. |
| (c) Organize Contests of “BRT’s Vietnamese Name”, “BRT’s Logo” and “BRT’s Slogan” | Contests’ goals are introducing a new transportation service as well as strengthening public exposure of the BRT system initial involvement of end-users in PMU’s community activities. The participants will be Vietnamese citizens, and the contest would involve cooperation with local and national media (such as Voice of Vietnam, Hanoi TV, New Hanoi Daily or The Youngster, etc) to mobilize the contest. |
| (d)“BRT - Accessible Transit” | In Vietnam, the needs of people living with disabilities (PLWD) are often overlooked in public planning. BRT is different, PLWD can use this system like other BRT passengers due to the following advantages “BRT station platform and bus floor are designed at the same height allowing disabled and wheel-chaired person to participate in this new type of public transport”. With this characteristic, it is possible to create a practical and friendly BRT image including provision of discounts (50%) for handicapped persons. |
| (e) Expand “Painting Traffic Lanes” model on BRT routes | To strengthen the awareness of traffic participants in driving in right lanes, some streets in Hanoi (like Kim Ma Street) would selected to paint traffic lanes (to differentiate lanes for automobile, motor or bicycle). To further enhance such awareness and support BRT operation, the PMU should widely apply this model on BRT routes. This activity is proposed based on a BRT feature which is “exclusive lanes”. |
| (f) Publicize “Bus Priority Signal System” | To create a seamless passage for BRT system, a bus priority signal system will be set up along the corridor at crossroads. Before and in the early stage of putting BRT system into practice, billboards introducing the new signal and BRT system should be placed at busy intersections. |
| (g) Mobilize “BRT Fund” and “BRT Week” in Hanoi | With an aim to increase the public’s awareness and support and increase the number of BRT users, the PMU should launch the “BRT week” program in Hanoi. During “BRT Week”, each sold ticket would contribute VND 200 (suggested rate) to the “BRT Fund”. This fund would be used for donating victims of orange agent, poor children, handicaps, victims of flood hit areas, etc. |
| (h) Organize seminars and/or conferences/ Conduct sociological research | There will likely be many opinions about the project at the early stage and during project progress. To frequently provide and update information, the PMU should organize seminars/ conferences (at small or medium scale). Participants in these twice yearly events would be representatives from concerned bodies/ authorities in transportation, planning and investing, public security, etc. as well as associations/ organizations of the youth, women, veteran, etc. Research on stakeholders’ perceptions should be carried out to obtain updated information and reaction from city’s citizens, traffic participants such as BRT users, students, executives, scientists/ researchers work in transportation sector. This information would help fine-tune the communications campaigns. The HUTDP’s communications strategy will seek to include close liaison with SUSTRAN and other relevant groups, so as to leverage existing successful discussion groups with both regional and global reaches. The HUTDP website will also promote available studies relevant to the region, (e.g., BRT case studies by PADECO). |
| (i) Other related activities | “BRT Go With Vietnamese Students” program offering a discount of 50% for students. Coordination would be with the management boards of universities located in BRT routes like Hanoi University of Technology, National Economic University, University of Construction, Hanoi National University, University of Architecture, Hanoi Foreign Language University, etc., to offer free 1-year-using-BRT tickets to 5-10 best students. Create “BRT Culture” and strengthen public transport using awareness through coordination with local primary schools to highlight public transport system and BRT. A discount of 50% would be offered to students. Organize painting contests of “Me and BRT” and “Green Environment”. Given the benefits brought by BRT to public transport sector in particular and community in general such as controlling traffic jam, increasing urban civilization and reducing environmental pollution, the PMU could hold painting contests for children in order to educate them on public transportation system and environment, giving the basis to have a new generation of better awareness of the environment and the advantages of public transport system, including BRT. |

- Media Relations Strategy

| Sub-components of Media Strategy | Sub-Component Description |
| --- | --- |
| Press Conferences | Hold press conference on a quarterly or half year basis to provide and update information to both local and national media. Participants will include local and national media, including: Daily media; Transportation sector media; General/ business/ trade media; TV stations; and, Radio stations. Information will be provided on: updating project implementing progress and launching of community activities. The PMU should work closely with media to publicize and increase the effectiveness of BRT system when launching all activities. |
| Disseminate Press Release | Together with press conferences, the PMU should disseminate news release on 2 months basis. Information will be provided on: updating project implementing progress; launching PMU’s community activities; and announcing traffic development programs supported by the PMU. |
| TV Reporting | Coverage in a TV reportage (3-5 minutes/ each) with VTV, or Hanoi TV will help to build BRT’s brand in Vietnam, the project progress, positive reaction from community, authority’s opinions, PMU’s comments, etc. |
| Advertise the BRT | Advertise BRT’s functions, characteristics, advantages in coordination with publications/ TVs/ radios. At the early stage of the project as well as during the project operation, advertisement should be clear images and remarks, not abstract ones. This would help the public to have an overall concept and friendly impression of the BRT. |
| Monitor media coverage | It is necessary to closely monitor media coverage in order to timely response to negative news which may cause bad impact on the project implementation and operation. The TUPMU should establish a specific office to monitor and follow up all media coverage pertaining to the project, periodically highlighting key or unusual happenings to TUPMU Director to take appropriate actions. |

Component 2: Strategic Road Infrastructure and Sustainable Urban Planning

(total US$236.8 million; US$90 million from IDA; US$ 145 million from Government; US$1.8 from GEF)

This component will construct two new road segments: (i) a section of approximately 7 km in length for the proposed second Ring Road between the proposed new bridge across the Red River (at Nhat Tan and Cau Giay); and (ii) the Hoang Quoc Viet Western extension (approximately 3.4 km), from the Third Ring Road to South Thang Long Industrial Zone.

The two road sections go through a combination of farmland and settled land and will entail resettlement. The component will also finance the construction of new housing tenements for project affected persons displaced by the BRT project.

This component will construct two new road segments: (i) a section of approximately 7 km in length for the proposed second Ring Road between the proposed new bridge across the Red River (at Nhat Tan and Cau Giay); and (ii) the Hoang Quoc Viet Western extension (approximately 3.4 km), from the Third Ring Road to South Thang Long Industrial Zone.

Component 2.A. Strategic Road Infrastructure

(total US$236.8 million; US$145.0 million from IDA; US$90.0 million from the Government; US$0 million requested from GEF)

Second Ring Road (RR2). The 2RR project will introduce a dual, 3-lane roadway facility with grade separation at key junctions and segregated frontage roads for local traffic and access between the Cau Giay area of western central Hanoi and a future crossing of the Red River at Nhat Tan.  The scope of the proposed works for the 2RR includes four elements: (a) a Northern Segment (approximately 4.6km) from Nhat Tan Bridge to the Buoi Interchange, which would constitute a new alignment across mostly open land but with some development; (b) the Buoi Interchange (580 m), proposed as a two level junction with looped ramps; (c) a Southern Segment (approximately 2.0 km), which will be from the Buoi Interchange to Cau Giay and is aligned adjacent to a drainage canal and existing local road; and (d) Cau Giay Intersection between 2RR and Route 32m which will require the improvement of existing junction.

### Hoang Quoc Viet (HQV) Western Extension Road. This section of road will construct a dual 3-lane road with a broad central reserve (to allow the subsequent construction of an elevated LRT), within an overall right-of-way of 50m. The junction with the Third Ring Road will be an at-grade signalized junction, with provision for the subsequent construction of an elevated north-south road along the line of 3RR. Two bridges are proposed for the HQV Extension, namely those at Song Nhu and Dam Bridge.

Housing for Displaced Persons. At present, two potential resettlement sites, CT1 and CT6 have been identified to accommodate persons displaced by the Project.  These sites can accommodate about 1000 to 1,200 households.

Component 2.B.  Integrated Sustainable Urban Land Development and Transport Planning

(total US$1.75 million; co-financing US$0.05 million from IDA; US$1.75 million requested from GEF)

This subcomponent will include studies that will support the Hanoi Department of Planning and Architecture to:

- review of it existing planning regulations, institutional structures, standards and procedures and consider modifications that would result in facilitating urban growth that is more compatible with competitive public transport;

- review existing plans for the newly urbanizing areas, particularly west of West Lake and north of the Red River from the same perspective;

- conduct capacity building and training for officials dealing with urban development and transport planning; and

- case studies (feasibility studies, tax incentives, zoning exceptions) at particular locations that would make the recommendations of these reviews actionable.

The purchase of GIS software will be made with the support of IDA co-financing.

Component 3:  Program to Support Air Quality, Traffic Safety, the Public Transport Authority, Transport Policy and Replication

[total US$11.15 million, IDA US$7.55, US$3.6 million requested from the GEF]

The Program has five subcomponents - an Air Quality Management (AQM) Program; a Traffic Safety program; supporting the strengthening of a newly established Public Transport Authority; transport policy development; and replication and information dissemination activities that have been designed to address GEF’s priority on replication.

Component 3.A Air Quality Management Program (total IDA US$3.45 million; US$0 from GEF))

The primary objective of AQM is to develop an air quality management system to reduce human exposure to vehicular air pollution in Hanoi. The system will target the primary sources of air pollution: motorcycles and diesel vehicles through various pollution abatement measures. To achieve this objective, the draft AQM Implementation Plan proposed the following sub-components:

- Air Quality Inventory and Monitoring

- Comprehensive Motor Vehicle Emission Control Strategies (MVECS)

- Inspection and Maintenance (I/M) Program and Motorcycle Clinic

- Economic Instrument Approaches to Air Quality Management

The table below summarizes the key components of this sub-component.  No GEF co-financing is proposed for this sub-component.

| AQM sub-components | Main elements under considerations | Proposed Schedule | Main agencies and partners |
| --- | --- | --- | --- |
| MV Emissions Inventory and Monitoring | Emissions inventory (EI); Air monitoring (AM); Air quality management plan; Data systems management; Capacity building and skills development; Health impact analysis; institutional arrangements; and Public access to AQ information | Government has ordered agencies to work together; Funding received for technical assistance; Initial work on EI and AM started; Consultations are being carried out as part of EIA; Majority of the detailed work to begin during the first two years of the HUTP implementation | DONRE, MONRE, TUPWS,:VR; Police; Swisscontact, Norwegian Agency; World Bank, CAI-Asia local network, and others |
| MV Emission Control Strategies | Vehicle standards; Fleet inventory; Old vehicle scrap program; Environment friendly retrofits; Road side testing; Fuel quality monitoring; Alternative fuel and additives; and Public awareness and education | Government is designing this program with assistance from Swisscontact and others. Further details to be finalized during appraisal and during the first year of implementation. | DONRE, MONRE, TUPWS,:VR; Police; Swisscontact, Norwegian Agency; World Bank, CAI-Asia local network, and others |
| Inspections and Maintenance Program and Motorcycles Clinic | Inspection and maintenance (I & M) system for motorcycles using “clinics” for developing the design and to raise awareness; Promotion of Motorcycle registration and improved safety (e.g. increasing helmet usage) | Received assistance for Motorcycle clinics planned for summer 2006; I & M system from other countries to be studied and shared during late 2006; Motorcycle registration requirements and safety issues will be discussed during appraisal and negotiations; | DONRE, TUPWS,:VR; Police; Swisscontact, Norwegian Agency; World Bank, and others |
| Economic Instruments for AQ Management | Use of economic instruments, such as emission reduction subsidies, emission fees and taxes included in fuel prices, user charges, tolls; transferable emission limits and dual fee programs instead of only “command and control” methods. | Once basic implementation has began, we plan to bring TA and experience from the region and around the world to discuss what may be promoted in Vietnam depending on the capacity of various agencies. | DONRE, TUPWS,:VR; Swisscontact, World Bank, and others |

Component 3.B:  Traffic Safety (total IDA US$2.9 million; US$0 from GEF)))

To achieve the long-term sustainability of all investments on traffic safety, a number of areas where road safety could be improved have been identified, including through engineering, education, and enforcement. In the project context, the traffic safety subcomponent of HUTDP will focus on the enforcement and engineering solutions that support the BRT Component.  These proposed solutions include the providing the traffic safety equipment and necessary technical assistance for Hanoi City traffic control and management institution.  These proposed solutions will complement other solutions recommended by other projects like Road Safety Project funded by the World Bank.

No GEF funding is requested for this Component.

Component 3.C: Public Transport Authority Strengthening (total US$2.4 million, IDA US$1.2 million, GEF US$1.2 million)

The PTA will be responsible for regulation and planning of all city bus operations and coordinating all new mass transit initiatives and the integration of existing services with new developments, and will play a critical role in: choosing BRT operators and monitoring BRT operations; managing the restructuring of existing bus-routes to feed and complement the BRT network; and, ensuring successful integration between the BRT, the existing bus system and future mass transit systems.

As the PTA will be a key component in ensuring the sustainability of the Urban Transport Development Project in Hanoi, GEF funding is sought to strengthen the PTA’s capacity for BRT planning, concessioning, and implementation as outlined in this section.  It should be noted that GEF funding for technical assistance for the PTA is considered essential to establish the long-term sustainability and operational efficiency of the PTA, and for the successful implementation of the BRT system in Hanoi.

To support the design and establishment of the PTA, technical assistance and services will be provided to ensure that the agency gains the necessary capacity to perform:

- long term public transport planning;

- co-ordination of all existing and new schemes in conformity with the plan;

- procurement of service providers on a contractual basis;

- control of common infrastructure (e.g. terminals); and

- control of finance, including ticketing and revenue collection.

The following tasks are anticipated:

- Review previous studies and proposals, particularly these related to the creation of the PTA, both in the PPIAF study and the HUTDP draft feasibility and preliminary designs.

- Review the normative regarding urban transport and public transport, particularly in relation to the legal tools available for the creation of the PTA and implementation of the BRT system as the first major mass transit system to be implemented and managed by the PTA).

- Recommend an institutional action plan for the creation of the PTA and implementation of the BRT system and seek HPC’s views and approval of the recommendations and action plan.

- Support HPC on the creation of the PTA and implementation of the BRT, in the preparation of pro-forma Decisions, Decrees, and any other legal tool required for the creation and implementation of the BRT system, as well as assist HPC in advancing and obtaining approval of the proposed legal tools.

- Preparation of operational rules manual: establishment of routes, selection of the type of vehicles, information system for the entrepreneurial operation of public transportation, control and supervision of the quality of service.

- Prepare a detailed procurement plan. The procurement plan shall include infrastructure, equipment, software and technical training program.

- On-the job training of assigned counterpart personnel on all the aspects related to the technical Assistance.

GEF is requested to co-finance training, including consultants to provide on-the-job support for PTA, and to support for BRT commercialization and (iii) support for planning and operating aspects of the BRT. GEF co-financing is sought to support this authority with training and related activities that would (i) ensure sustainability of the HUTDP investments and help allay GEF’s stated concerns related to sustainability; and (ii) ensure that low cost coordination and planning measures that would maximize the effectiveness of the BRT and other complementary investments in public transport are properly implemented.

Component 3.D: Transport Policy Development (total GEF US$1.5 million)

Transport policy development is an important part of HPC’s mandate.  Consequently, Hanoi invests significant resources and managerial effort on the issue.  A JICA financed plan that includes transport is near completion.  Issues related to restrictions on motorcycle and auto ownership, and parking are important and constantly on the HPC’s agenda.  However, Hanoi’s attempts to enforce restrictions on the use of auto and motorcycle ownership to manage congestion have been largely ineffective. Additionally, the Bank’s assessment is that Hanoi has not fully understood the potential of economic instruments based on price as alternatives to command-and-control methods, to effectively manage the urban transport system. Properly implemented, such instruments have the potential to significantly reduce the amount of private motorized travel (and consequently GHG emissions), by inducing shifts to public transport and encouraging trip combination.

Activities will include the following:

- raise awareness, understanding and comfort of decision-makers with economic instruments to manage/restrict  private vehicle use as a means to address congestion and related transport problems in Hanoi’s context;

- support the development of an actionable long-term plan in this respect;

- examine the role parking policy and can play to assist the HPC to manage the transport system, focusing on the development of a parking and enforcement policy that can serve to manage demand rather than just accommodate it;

- support the development of a fuel use and CO2 inventory and promote the use of indicators related to total motorized travel/energy use in Hanoi’s transport policy development; and,

- support an impact evaluation of the BRT.

Component 3E National and Regional Replication and Information Dissemination (total, GEF US$1.2 million)

The BRT project in Hanoi has a strong potential for replication, especially in similar sized cities both in Vietnam and in the region. The proposed project seeks to actively promote replication, in other Vietnamese and Asian cities, by leveraging the demonstration nature of the project and disseminating information gathered during implementation.

As the implementation of Hanoi’s BRT line sets an example for other Vietnamese cities and in the larger region, the project replication activities, therefore, will actively target replication both within Vietnam and within the region through the following:

- BRT promotion for Vietnamese cities:  Replication within the country will be promoted by briefing the managers of other major Vietnamese cities on the project and by keeping them appraised of its progress and impacts:

- Information will be made available on a regular basis through the production of public information announcements and other materials;

- A launch meeting will be held that will seek to inform other cities about the benefits of BRT, the urban planning process, and related information; and,

- At either the project’s midpoint or towards the end of the project, a dissemination workshop will be hosted to present and assess the progress of the implementation, and will include a focus on lessons learned.

- Feasibility studies for priority demonstration corridors will be financed in interested cities.

- Replication outside the country will be promoted through:

- publications (e.g. lessons learned document) on the Hanoi BRT;

- exhibits and presentations will be made by Hanoi at major transport fora in the region.  These exhibits and presentations will focus both on the experience of Hanoi is planning and implementing BRT, but also on the lessons learned; and,

- by hosting and promoting study tours to Hanoi for senior urban development and transport planners from other Asian cities. It should be noted that, based on experience from other successful systems such as Curitiba and Bogotá, replication is often not a problem.  Once the BRT systems are being implemented, great interest tends to follow quickly.  Recognizing this trend, the Hanoi project will facilitate the process both by organizing tours for interested parties and also by presenting information and lessons learned on BRT in a synthesized manner.

- For all interested cities within the region, the Hanoi BRT website will be a central repository for information on the progress, achievements, lessons learned and contact information.

The Hanoi project is already having an impact through the demonstration effect of the planning process for BRT:  Ho Chi Min City is following in Hanoi's steps and considering/planning a demonstration BRT line.

Several of the project components have elements of information dissemination (including Component 1C (BRT Consultation, Communications and Media Strategy; Component 3E on National and Regional Replication and Information Dissemination, and Component 2B on Integrated Sustainable Land Development and Transport Planning). These components were designed to be orthogonal to each other, and will be conducted to ensure that there is no overlap and that opportunities for cost savings are emphasized during project implementation.

Annex 5: Project Costs

Vietnam:  VN-Hanoi Urban Transport Project

(Note: This is a Pre-appraisal document. To be finalized at Appraisal)

| Project Cost By Component | GoV | IDA | GEF | Total |
| --- | --- | --- | --- | --- |
|  | US $million | US $million | US $million | US $million |
| 1. Development of the BRT System |  |  |  |  |
| A. BRT System (except for stations, terminals and interchanges), and NMT and Pedestrian Access | 6.270 | 60.420 | 1.300 | 67.990 |
| B. BRT Stations, Interchanges, and Terminals | 1.730 | 14.870 | 1.400 | 18.000 |
| C. BRT Consultation, Communications and Media Strategy | 0.000 | 0.000 | 1.300 | 1.300 |
| 2. Strategic Road Infrastructure and Sustainable Urban Planning |  |  |  |  |
| A. Strategic Road Implementation | 145.000 | 90.000 | 0.000 | 235.000 |
| B. Integrated Sustainable Urban Land Development and Transport Planning | 0.000 | 0.050 | 1.7500 | 1.800 |
| 3. Program to Support Air Quality, Traffic Safety, the Public Transport Authority, Transport Policy and Replication |  |  |  |  |
| A. Air Quality Management | 0.000 | 3.450 | 0.000 | 3.450 |
| B. Traffic Safety | 0.000 | 2.900 | 0.000 | 2.900 |
| C. Public Transport Authority Agency Strengthening | 0.000 | 1.200 | 1.200 | 2.400 |
| D. Transport Policy Development | 0.000 | 0.000 | 1.500 | 1.500 |
| E. National and Regional Replication and information dissemination | 0.000 | 0.000 | .0.900 | 0.900 |
| Project Management | 0.000 | 3.000 | 0.450 | 3.450 |
| Total Cost (excluding price contingencies) | 153.000 | 175.890 | 9.800 | 338.690 |

Annex 6: Implementation Arrangements

Vietnam:  VN-Hanoi Urban Transport Project

To be finalized at appraisal.

Hanoi People’s Committee will be solely responsible for executing the project. HPC will establish a Project Leading Group headed by the Vice Chairman of the HPC responsible for infrastructure (or higher) to facilitate project implementation.  To manage, coordinate and supervise the project, the HPC has established a Project Management Unit (PMU), under the Hanoi Transport and Urban Public Works Service (TUPWS), which has experience implementing the previous IDA-supported Urban Transport Improvement Project. (This will be finalized at appraisal – HPC is considering establishing this PMU directly under the HPC.) The PMU will be maintained at all times during the implementation period with adequate budget and qualified fulltime staff.

PMU will sign all contracts on behalf of the HPC.  The PMU will be the executing agency managing the implementation of all civil works.  The Public Transport Authority (PTA) will manage the procurement of the buses and all equipment related to the BRT system.  The PMU and PTA together will manage the BRT concession processes.  The BRT concessions will likely be signed with the PTA on behalf of HPC.  The traffic police and traffic inspection board under TUPWS will be involved in the procurement of all equipment related to traffic management. The Department of Natural Resources and the Environment (DONRE) will manage the implementation of the air quality component.  The Department of Architecture and Planning Management (DAPM) will manage the implementation of the urban planning TA. The PMU will coordinate with all relevant agencies including the HPC, TUPWS, the traffic inspection board of TUPWS, the traffic police, Department of Planning and Investment (DPI), the PTA and bus operators on the comprehensive planning TA.  The PMU will organize and manage all Hanoi based replication activities including workshops and hosted study tours.  Individual cities wishing to explore BRT demonstrations will execute study tours and feasibility studies for such activities, facilitated by the Ministry of Transport (this arrangement will be finalized at appraisal).

The roads and BRT road will be turned over to TUPWS after construction and will be maintained by TUPWS.  BRT buses, terminals, depots and other equipment will be owned by the City (with the PTA potentially representing the City) and leased out to operators as appropriate.

The operators will be selected based on competitive tendering.

DAPM will be responsible for revising planning standards and managing HPC processing. DONRE will be responsible for processing air quality monitoring data.  An emission control policy will be finalized with DONRE coordinating with other related agencies including traffic police, Vietnam Register and TUPWS.

Project oversight. At the national level, the Ministry of Planning and Investment (MPI) provides overall sectoral guidance on investment policy and approves and monitors the progress of all large foreign-assisted projects. For sector-specific issues, MPI consults with the sector ministry, in this case the Ministry of Transport and Communications (MOT), the national agency responsible for developing and managing the transport sector. MOT plays an advisory and coordinating role for developing the urban transport sector in Hanoi. At the city level, HPC, in consultation with TUPWS, will guide, approve and monitor project-specific policy and investment decisions. The Stakeholder Participation Plan is provided in Annex 19.

Accounting, financial reporting and auditing arrangements. To ensure financial accountability, various steps will be taken: (a) The PMU will maintain a separate project account, including the special account; (b) the special account and project account, including documentation for SOEs, will be audited annually by independent external auditors acceptable to IDA and the Government, with the audit including a separate opinion on the Sstatement of Expenditures used as a basis for disbursements; and (c) detailed audit reports will be submitted by the PMU to IDA annually, within six months after the end of the city government's fiscal year.

Annex 7: Financial Management and Disbursement Arrangements

Vietnam:  VN-Hanoi Urban Transport Project

To be finalized by appraisal.

Annex 8: Procurement Arrangements

Vietnam:  VN-Hanoi Urban Transport Project

To be finalized by appraisal.

Annex 9: Economic and Financial Analysis

Vietnam:  VN-Hanoi Urban Transport Project

## This is a pre-appraisal level analysis.  Will be finalized at appraisal

## Economic Evaluation

General Approach

#### Evaluation Procedure

This Section of the Report describes the economic evaluation process applied to the BRT component of this project, with a general description of the evaluation methodology and data inputs.

The economic evaluation process has followed standard evaluation methodology for transport investment projects. Specifically, the situation forecasted to occur with the BRT system in place, referred to as the “with project case”, has been compared with the situation expected if the present type of public transport system is maintained, the “base case”.  The process takes into account factors that can be quantified, such as the construction and maintenance costs, forecast of traffic volumes and passenger numbers, and road user costs, including vehicle operating costs and passenger time costs. It provides measures of the overall returns obtainable from the project, which can be compared with returns from expenditure on alternative transport projects and investment, so as to ensure that capital resources be distributed as efficiently as possible.

The introduction of the BRT system, while increasing road capacity as a whole, will result in the reduction of road space for other vehicles along the BRT route.  This has implications for vehicle movements over a wide area of the Hanoi road network, as traffic may choose alternative routes.  Therefore, the economic analysis has taken into account the impact of the project on the traffic flows over the whole Hanoi road network.

Annual cost and benefit streams have been considered over a 22-year period from 2006, the commencement of investment. The project uses 2006 values as the base value, applying 12% discount rate to adjust values of other years.  Civil works have been assumed to be completed by the end of 2007, giving benefits for a period of 20 years. It has been assumed that the whole system comes into operation at the beginning of 2008.  No costs to road users caused by disruptions to traffic during the construction period have been included.

The benefits have been calculated from the results of the traffic assignment model described in Chapter 3.  Trip matrices were assigned to the network for a base case, without the BRT in place, and for a project case with the two BRT routes operating.  The model incorporates a detailed simulation of the BRT system, taking into account the specific station locations and interchanges.  Conventional bus routes are also defined in the model.  Proposed changes to these services to coincide with the introduction of the BRT are included in the with project case.

From the predicted traffic volumes and vehicle speeds on each link of the Hanoi road network, the overall network vehicle operating costs (VOC) and travel times were determined.   This was done for 2005, 2010 and 2020.  Annual data was obtained by interpolating between these years, and then projecting beyond 2020.

The BRT system will not change travel costs significantly and no generated trips have been assumed in the analysis.

Evaluation Results

The results of the evaluation of the BRT system are summarized in Table A9.1.  The BRT shows an IRR of 12.9% and an NPV with a 12% discount rate of $3.58 million.  The FYRR in the proposed opening year of 2009 is 6.6%, and reaches 12% in 2011.

The two largest sources of benefits are travel time savings to bus passengers and VOC savings of other vehicle users.  The bus passenger time savings are net savings, including disbenefits to some passengers as a result of the proposed changes of the existing bus routes when the BRT system is introduced. The VOC savings to other vehicles result mainly from a reduction in the number of kilometers operated (by vehicles), resulting from journeys being diverted to the BRT system.  These savings take into account the increase in per km operating costs for all vehicle types, as a result of the slowing down of vehicle speeds caused by the reduction in road capacity.  There is a slight saving in overall bus and BRT vehicle operating costs compared with the base case, despite the increase in passenger numbers, because of the lower cost per passenger km on the BRT buses.  There are significant time losses to passengers in vehicles other than buses, as a result of the lower speeds.

Table A9.1:	BRT Summary Economic Evaluation (US$ million)

| Year | BRT System Costs | Benefits | Net Cash Flow | FYRR (%) |
| --- | --- | --- | --- | --- |
|  |  | Road Maintenance. | Vehicle Operating Cost | Passenger Time |  |  |
|  | Capital | Maintenance | Operating |  | Bus(1) | Other | Bus | Other |  |  |
| 2007 | 1.711 |  |  |  |  |  |  |  | -1.711 |  |
| 2008 | 56.878 |  |  | 0.616 |  |  |  |  | -56.282 |  |
| 2009 |  | 0.021 | 0.530 | 0.616 | -0.241 | 2.071 | 1.830 | 0.133 | 3.838 | 6.52 |
| 2010 |  | 0.021 | 0.530 | 0.616 | 0.263 | 2.597 | 2.185 | 0.262 | 5.351 | 9.10 |
| 2011 |  | 0.022 | 0.530 | 0.616 | 0.827 | 3.213 | 2.610 | 0.448 | 7.141 | 12.15 |
| 2012 |  | 0.022 | 0.530 | 0.616 | 0.851 | 3.023 | 3.016 | 0.246 | 7.181 | 12.21 |
| 2013 |  | 0.022 | 0.530 | 0.616 | 0.876 | 2.847 | 3.486 | 0.013 | 7.265 | 12.36 |
| 2014 |  | 0.023 | 0.530 | 0.616 | 0.901 | 2.687 | 4.028 | -0.263 | 7.396 | 12.58 |
| 2015 |  | 0.023 | 0.530 | 0.616 | 0.926 | 2.546 | 4.655 | -0.590 | 7.580 | 13.89 |
| 2016 |  | 0.023 | 0.530 | 0.616 | 0.951 | 2.426 | 5.380 | -0.975 | 7.824 | 13.31 |
| 2017 |  | 0.024 | 0.530 | 0.616 | 0.976 | 2.331 | 6.218 | -1.420 | 8.146 | 13.86 |
| 2018 |  | 0.058 | 0.530 | 0.616 | 1.001 | 2.266 | 7.186 | -1.909 | 8.552 | 14.55 |
| 2019 |  | 0.025 | 0.530 | 0.616 | 1.027 | 2.235 | 8.304 | -2.391 | 9.216 | 15.68 |
| 2020 |  | 0.026 | 0.530 | 0.616 | 1.052 | 2.246 | 9.597 | -2.745 | 10.190 | 17.33 |
| 2021 |  | 0.028 | 0.530 | 0.616 | 1.078 | 2.305 | 11.091 | -2.717 | 11.796 | 20.06 |
| 2022 |  | 0.029 | 0.530 | 0.616 | 1.143 | 2.444 | 11.757 | -2.875 | 12.505 | 21.27 |
| 2023 |  | 0.064 | 0.530 | 0.616 | 1.211 | 2.591 | 12.462 | -3.043 | 13.224 | 22.49 |
| 2024 |  | 0.032 | 0.530 | 0.616 | 1.284 | 2.747 | 13.210 | -3.221 | 14.053 | 23.90 |
| 2025 |  | 0.035 | 0.530 | 0.616 | 1.361 | 2.912 | 14.003 | -3.409 | 14.897 | 25.34 |
| 2026 |  | 0.038 | 0.530 | 0.616 | 1.443 | 3.087 | 14.843 | -3.609 | 15.791 | 26.86 |
| 2027 |  | 0.041 | 0.530 | 0.616 | 1.529 | 3.272 | 15.733 | -3.820 | 16.739 | 28.47 |
| 2028 | -14.219 | 0.078 | 0.530 | 0.616 | 1.621 | 3.469 | 16.677 | -4.044 | 31.930 | 54.31 |
|  |  |  |  |  |  |  |  | NPV | 3.58 |  |
|  |  |  |  |  |  |  |  | IRR | 12.9% |  |

(1) Includes capital costs of BRT buses

Source: Own estimates

## Financial Analysis

Financial Sustainability – A financial analysis of the BRT investments (see Table A9.2) determined that the BRT is financially sustainable.  It is anticipated to produce a net surplus of approximately US$2 million per year initially, rising to over US$5 million in 2015. From then onwards, credit repayments of approximately US$2.5 million per year have to be made, but the net surplus is still over US$2.8 million per year, rising to US$10 million in 2027.  Preliminary estimates suggest that the economic benefits of the BRT are even greater than the financial benefits.

Table A9.2:	BRT Project Financial Evaluation - Annual Cash Flow with Full World Bank Loan Financing (US$ million)

| Year | BRT System Costs | Savings | Revenue Increase | Net Cash Flow |
| --- | --- | --- | --- | --- |
|  | Loan Repayments | Fleet Operating Costs(1) | System Maintenance | System Operating | Reduction in Conventional Bus Operating Costs | Reduction in Road Maintenance Costs | Net Increase in Fare Revenue | Fare Subsidy |  |
| 2007 |  |  |  |  |  |  |  |  | 0.00 |
| 2008 |  |  |  |  |  | 0.70 |  |  | 0.70 |
| 2009 |  | 5.222 | 0.023 | 0.579 | 4.941 | 0.72 | 1.964 | 0.000 | 1.80 |
| 2010 |  | 5.379 | 0.024 | 0.597 | 5.696 | 0.75 | 2.343 | 0.000 | 2.78 |
| 2011 |  | 5.540 | 0.025 | 0.615 | 6.566 | 0.77 | 2.795 | 0.000 | 3.95 |
| 2012 |  | 5.707 | 0.026 | 0.633 | 6.794 | 0.79 | 3.000 | 0.000 | 4.22 |
| 2013 |  | 5.878 | 0.027 | 0.652 | 7.031 | 0.81 | 3.220 | 0.000 | 4.51 |
| 2014 |  | 6.054 | 0.029 | 0.672 | 7.275 | 0.84 | 3.456 | 0.000 | 4.82 |
| 2015 |  | 6.236 | 0.030 | 0.692 | 7.528 | 0.86 | 3.710 | 0.000 | 5.14 |
| 2016 |  | 6.423 | 0.032 | 0.713 | 7.790 | 0.89 | 3.982 | 0.000 | 5.49 |
| 2017 | 2.82 | 6.615 | 0.033 | 0.734 | 8.061 | 0.92 | 4.274 | 0.000 | 3.05 |
| 2018 | 2.82 | 6.814 | 0.082 | 0.756 | 8.342 | 0.94 | 4.587 | 0.000 | 3.40 |
| 2019 | 2.82 | 7.018 | 0.037 | 0.779 | 8.632 | 0.97 | 4.924 | 0.000 | 3.88 |
| 2020 | 2.82 | 7.229 | 0.040 | 0.802 | 8.932 | 1.00 | 5.285 | 0.000 | 4.33 |
| 2021 | 2.82 | 7.446 | 0.043 | 0.826 | 9.243 | 1.03 | 5.672 | 0.000 | 4.82 |
| 2022 | 2.82 | 8.129 | 0.046 | 0.851 | 10.092 | 1.06 | 6.193 | 0.000 | 5.50 |
| 2023 | 2.82 | 8.876 | 0.105 | 0.877 | 11.018 | 1.09 | 6.761 | 0.000 | 6.20 |
| 2024 | 2.82 | 9.690 | 0.055 | 0.903 | 12.029 | 1.13 | 7.382 | 0.000 | 7.07 |
| 2025 | 2.82 | 10.580 | 0.061 | 0.930 | 13.134 | 1.16 | 8.060 | 0.000 | 7.97 |
| 2026 | 2.82 | 11.551 | 0.068 | 0.958 | 14.339 | 1.20 | 8.800 | 0.000 | 8.94 |
| 2027 | 2.82 | 12.612 | 0.076 | 0.987 | 15.656 | 1.23 | 9.608 | 0.000 | 10.00 |
| 2028 | 2.82 | 13.769 | 0.150 | 1.016 | 17.093 | 1.27 | 10.490 | 0.000 | 11.10 |
|  |  |  |  |  |  |  |  | NPV | 109.7 |

(1) Includes capital costs of BRT buses

Source: Own estimates

Annex 10: Safeguard Policy Issues

Vietnam:  VN-Hanoi Urban Transport Project

To be finalized by appraisal.

Annex 11: Project Preparation and Supervision

Vietnam:  VN-Hanoi Urban Transport Project

To be finalized by appraisal.

Annex 12: Documents in the Project File

Vietnam:  VN-Hanoi Urban Transport Project

To be finalized by appraisal.

Annex 13: Statement of Loans and Credits

Vietnam:  VN-Hanoi Urban Transport Project

|  |  |  | Original Amount in US$ Millions |  |  | Difference between expected and actual disbursements |
| --- | --- | --- | --- | --- | --- | --- |
| Project ID | FY | Purpose | IBRD | IDA | SF | GEF | Cancel. | Undisb. | Orig. | Frm. Rev’d |
| P084871 | 2006 | VN-2nd Transmission & Distribution | 0.00 | 200.00 | 0.00 | 0.00 | 0.00 | 197.82 | 0.00 | 0.00 |
| P066051 | 2005 | VN - Forest Sector Development Project | 0.00 | 39.50 | 0.00 | 0.00 | 0.00 | 51.12 | 0.65 | 0.30 |
| P073763 | 2005 | VN-WATER SUPPLY DEV. | 0.00 | 112.64 | 0.00 | 0.00 | 0.00 | 110.40 | 0.03 | 0.00 |
| P074414 | 2005 | VN - GEF Forest Sector Development Proj | 0.00 | 0.00 | 0.00 | 9.00 | 0.00 | 9.00 | 0.60 | 0.32 |
| P074688 | 2005 | VN-2nd Rural Energy | 0.00 | 220.00 | 0.00 | 0.00 | 0.00 | 221.61 | 2.43 | 0.00 |
| P082604 | 2005 | VN-HIV/AIDS Prevention Project | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 33.68 | 0.13 | 0.00 |
| P082627 | 2005 | Payment System and Bank Modernization 2 | 0.00 | 105.00 | 0.00 | 0.00 | 0.00 | 99.44 | 0.02 | 0.00 |
| P085080 | 2005 | VN-ROAD SAFETY | 0.00 | 31.73 | 0.00 | 0.00 | 0.00 | 30.64 | 0.00 | 0.00 |
| P085260 | 2005 | VN-Targeted Budget Support for EFA | 0.00 | 50.00 | 0.00 | 0.00 | 0.00 | 48.15 | 0.00 | 0.00 |
| P086360 | 2005 | Vietnam - PRSC IV | 0.00 | 100.00 | 0.00 | 0.00 | 0.00 | 96.60 | 0.00 | 0.00 |
| P088362 | 2005 | VN-Avian Influenza Emergency Recovery Pr | 0.00 | 5.00 | 0.00 | 0.00 | 0.00 | 4.19 | 0.91 | 0.00 |
| P070197 | 2004 | VN-URBAN UPGRADING | 0.00 | 222.47 | 0.00 | 0.00 | 0.00 | 206.78 | -0.97 | 0.00 |
| P065898 | 2004 | VIETNAM WATER RESOURCES ASSISTANCE | 0.00 | 157.80 | 0.00 | 0.00 | 0.00 | 149.18 | 0.05 | 0.00 |
| P059663 | 2004 | VN-ROAD NETWORK IMPROVT | 0.00 | 225.26 | 0.00 | 0.00 | 0.00 | 216.61 | 21.73 | 0.00 |
| P075399 | 2003 | Public Financial Management Reform Proj. | 0.00 | 54.33 | 0.00 | 0.00 | 0.00 | 56.76 | 13.49 | 0.00 |
| P044803 | 2003 | VN-PRIMARY EDUC FOR DISADVANTAGED CHILRE | 0.00 | 138.76 | 0.00 | 0.00 | 0.00 | 183.84 | 20.74 | 0.00 |
| P071019 | 2003 | VN-GEF Demand-Side Management & Energy | 0.00 | 0.00 | 0.00 | 5.50 | 0.00 | 4.44 | 2.20 | 0.00 |
| P073778 | 2002 | VN-GEF-System Energy Equitization-Renewa | 0.00 | 0.00 | 0.00 | 4.50 | 0.00 | 3.92 | 2.76 | 0.00 |
| P073305 | 2002 | VN-Regional Blood Transfusion Centers | 0.00 | 38.20 | 0.00 | 0.00 | 0.00 | 42.91 | 23.38 | 0.00 |
| P072601 | 2002 | VN - Rural Finance II Project | 0.00 | 200.00 | 0.00 | 0.00 | 0.00 | 85.23 | -61.17 | 0.00 |
| P066396 | 2002 | VN-SYSTEM ENERGY, EQUITIZATION & RENEWAB | 0.00 | 225.00 | 0.00 | 0.00 | 0.00 | 210.04 | 195.29 | 0.00 |
| P051838 | 2002 | VN-PRIMARY TEACHER DEVELOPMENT | 0.00 | 19.84 | 0.00 | 0.00 | 0.00 | 18.63 | 13.75 | 0.00 |
| P059936 | 2002 | VN -Northern Mountains Poverty Reduction | 0.00 | 110.00 | 0.00 | 0.00 | 0.00 | 81.09 | 37.71 | 0.00 |
| P052037 | 2001 | VN-HCMC ENVMTL SANIT. | 0.00 | 166.34 | 0.00 | 0.00 | 0.00 | 161.51 | 59.27 | 49.00 |
| P062748 | 2001 | VN - COMMUNITY BASED RURAL INFRA. | 0.00 | 102.78 | 0.00 | 0.00 | 0.00 | 86.58 | 30.34 | 0.00 |
| P042927 | 2001 | VN-MEKONG TRANSPORT/FLOOD PROT. | 0.00 | 110.00 | 0.00 | 0.00 | 0.00 | 86.84 | 71.83 | 0.00 |
| P042568 | 2000 | VN - COASTAL Wetl/Prot Dev | 0.00 | 31.80 | 0.00 | 0.00 | 0.00 | 18.50 | 15.65 | 0.95 |
| P056452 | 2000 | VN-RURAL ENERGY | 0.00 | 150.00 | 0.00 | 0.00 | 0.00 | 36.81 | 31.13 | 26.81 |
| P059864 | 2000 | VN-RURAL TRANSPORT 2 | 0.00 | 103.90 | 0.00 | 0.00 | 0.00 | 23.97 | 21.67 | 0.00 |
| P004828 | 1999 | VN-HIGHER EDUC. | 0.00 | 83.30 | 0.00 | 0.00 | 0.00 | 42.27 | 35.41 | 36.03 |
| P051553 | 1999 | VN-3 CITIES SANITATION | 0.00 | 80.50 | 0.00 | 0.00 | 0.00 | 50.78 | 45.05 | 10.74 |
| P004845 | 1999 | VN - MEKONG DELTA WATER | 0.00 | 101.80 | 0.00 | 0.00 | 0.00 | 56.30 | 52.10 | -4.47 |
| P004833 | 1999 | VN-URBAN TRANSPT IMPRVT | 0.00 | 42.70 | 0.00 | 0.00 | 8.19 | 12.13 | 18.70 | 8.70 |
| P004839 | 1998 | VN - FOREST PROT.& RUL DE | 0.00 | 21.50 | 0.00 | 0.00 | 0.00 | 10.90 | 9.32 | 5.65 |
| P004843 | 1998 | VN-INLAND WATERWAYS | 0.00 | 73.00 | 0.00 | 0.00 | 0.00 | 27.66 | 23.13 | 10.41 |
| P004844 | 1998 | VN-AGRIC. DIVERSIFICATION | 0.00 | 66.90 | 0.00 | 0.00 | 0.00 | 21.61 | 20.12 | 0.15 |
| P045628 | 1998 | VN-TRANSMISSION & DISTR | 0.00 | 199.00 | 0.00 | 0.00 | 0.00 | 93.88 | 88.02 | 26.73 |
| P004838 | 1996 | VN-NATIONAL HEALTH SUPPORT | 0.00 | 101.20 | 0.00 | 0.00 | 2.35 | 18.13 | 27.71 | 0.00 |
|  |  | Total: | 0.00 | 3,690.25 | 0.00 | 19.00 | 10.54 | 2,909.95 | 823.18 | 171.32 |

Vietnam

STATEMENT OF IFC’s

Held and Disbursed Portfolio

In Millions of US Dollars

|  |  | Committed | Disbursed |
| --- | --- | --- | --- |
|  |  | IFC |  | IFC |  |
| FY Approval | Company | Loan | Equity | Quasi | Partic. | Loan | Equity | Quasi | Partic. |
| 2003 | ACB-Vietnam | 0.00 | 5.02 | 0.00 | 0.00 | 0.00 | 5.02 | 0.00 | 0.00 |
| 2002 | AZ/AGF Vietnam | 0.00 | 0.71 | 0.00 | 0.00 | 0.00 | 0.71 | 0.00 | 0.00 |
| 2002 | CyberSoft | 0.00 | 0.06 | 0.00 | 0.00 | 0.00 | 0.06 | 0.00 | 0.00 |
| 2002 | Dragon Capital | 0.00 | 0.00 | 1.05 | 0.00 | 0.00 | 0.00 | 1.05 | 0.00 |
| 2002 | F-V Hospital | 5.00 | 0.00 | 3.00 | 0.00 | 5.00 | 0.00 | 3.00 | 0.00 |
| 2003 | Glass Egg | 0.00 | 1.19 | 0.00 | 0.00 | 0.00 | 0.06 | 0.00 | 0.00 |
| 2005 | Khai Vy | 6.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| 1998 | MFL Vinh Phat | 0.13 | 0.00 | 0.00 | 0.00 | 0.13 | 0.00 | 0.00 | 0.00 |
| 1997 | Nghi Son Cement | 12.74 | 0.00 | 0.00 | 5.63 | 12.74 | 0.00 | 0.00 | 5.63 |
| 2001 | RMIT Vietnam | 7.25 | 0.00 | 0.00 | 0.00 | 3.50 | 0.00 | 0.00 | 0.00 |
| 1996 | SMH Glass Co. | 3.89 | 0.00 | 0.00 | 0.00 | 3.89 | 0.00 | 0.00 | 0.00 |
| 2003/04/05 | Sacombank | 0.00 | 2.04 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| 2002/03 | VEIL | 0.00 | 8.00 | 0.00 | 0.00 | 0.00 | 8.00 | 0.00 | 0.00 |
|  | Total portfolio: | 35.01 | 17.02 | 4.05 | 5.63 | 25.26 | 13.85 | 4.05 | 5.63 |

|  |  | Approvals Pending Commitment |
| --- | --- | --- |
| FY Approval | Company | Loan | Equity | Quasi | Partic. |
| 2002 | F-V Hospital | 0.00 | 0.00 | 0.00 | 0.00 |
| 2000 | Interflour | 0.01 | 0.00 | 0.00 | 0.01 |
| 1999 | MFL Chau Giang | 0.00 | 0.00 | 0.00 | 0.00 |
| 1999 | MFL Minh Minh | 0.00 | 0.00 | 0.00 | 0.00 |
| 2000 | MFL Mondial | 0.00 | 0.00 | 0.00 | 0.00 |
| 2000 | MFL-AA | 0.00 | 0.00 | 0.00 | 0.00 |
| 2005 | Paul Maitland | 0.01 | 0.00 | 0.00 | 0.00 |
|  | Total pending commitment: | 0.02 | 0.00 | 0.00 | 0.01 |

Annex 14: Country at a Glance

Vietnam:  VN-Hanoi Urban Transport Project

Annex 15: Incremental Cost Analysis and Global Environmental Benefits

Overview

The proposed GEF project seeks to assist Hanoi in implementing a sustainable strategy of city development and transport improvement with a focus on promoting public transport. This project will provide support to the establishment of high capacity busways on major corridors, by integrating investments in road infrastructure with land-use plans to generate a transit friendly urban landscape, and by enhancing the capacity of the City’s institutions to create/implement a growth strategy that is conducive to public transit oriented development.

This project is consistent with the objectives of the Global Environment Facility Operational Program 11 on “Promotion of Environmentally Sustainable Transport”, and is consistent with the GEF climate change strategic priority related to Sustainable Transport is defined in the GEF Business Plan for FY04-06 (GEF/C.21/9). Specifically, this project will address modal shifts in urban transport through emphasis on BRT, non-motorized transport (bicycles and pedestrian areas), and non-technology measures (such as traffic demand management and economic incentives). The project will also build institutional and technical capacity at the local level, support policy development and public outreach initiatives.

This project has three key components: (1) BRT and public transport promotion; (2) a strategic road and urban transport planning; and (3) and an institutional capacity development, each of which has a GEF sub-component.

Baseline Scenario

(1) BRT and Public Transport Promotion

At this stage, the without-GEF project baseline is a IDA-financed investment project that includes a significant BRT component. However, this baseline has considerable deficiencies. First, there remain significant risks related to successful implementation. The leadership of Hanoi is changing and it is anticipated that the Project will be implemented without the presence of any of the key leaders responsible for initiating and initially endorsing the project. The new leadership’s exposure to the BRT concept is likely to be limited and continued efforts will be needed to build the new leadership’s commitment to, and confidence in, the BRT. There also remains considerable uncertainty and nervousness in the public mind regarding the proposed BRT. Though awareness of the proposed system is rising, in part due to the GEF preparation grant financed activities, the public remains unclear on how the BRT would work and its applicability to Hanoi. International experience suggests that this is not unusual, while the public in most cities has been very receptive to BRT’s once the systems are operational, there is skepticism until implementation is complete.

In addition, there are issues related to long-term sustainability of the public transport system in Hanoi’s current regulatory environment. Despite significant improvements in recent years as a result of Decision 34, bus services are currently dominated by a single State Owned Enterprise operator. The Bank’s assessment is that there is a need for a unified regulatory body that plans, manages and regulates all public transport in Hanoi: an agency that ensures a level playing field for all operators, ensures a seamless experience for consumers across modes and operators and ensures that all elements of the system are operated in a manner that maximizes the benefits for Hanoi and its consumers. Hanoi has decided to establish a unified public transport authority that could play such a role, but in the baseline without initial capacity building support for this organization, it is doubtful that it would be effective.

Furthermore, in the baseline scenario, the system would not be optimized to attract current motorcycle and automobile users. Barriers to pedestrian and cyclist access to the BRT stations would likely dissuade some potential trip-makers, particularly those who have a choice between using a private motor vehicle. Physical and stakeholder surveys of pedestrian and cyclist facilities in the vicinity of the proposed BRT stations suggest that significant improvements are needed in ensuring high-quality non-motorized access to the proposed system. Further, the ability to brand the BRT as a high quality service appropriate for middle-class users who have the choice of a private vehicle would be limited by a low-key functional design for the stations; experience from other successful BRTs suggests that attractive and distinctive stations can play a crucial role in creating an attractive BRT brand image, particularly for users who have the choice of using their own motor vehicles.

It should be noted that, without the involvement of GEF, there may not have been any BRT project at all. Though a BRT system had been identified initially at Hanoi’s request, Hanoi decision makers were hesitant in endorsing preparation, unsure if a BRT was appropriate for the City. Official endorsement of the project, which allowed preparation to proceed, came only after a study tour to Latin America, financed by PDF-B funds. In other words, by virtue of the PDF-B, GEF has already been able to play a catalytic role in this project.

(2) Strategic Road Component and Sustainable Urban Planning

In the absence of the GEF project, the strategic road component financed by IDA would likely be implemented as appraised. As planned this would significantly increase the access of the Dong Anh district (north of the red river) and the areas west of West Lake in the northwest of Hanoi to the rest of the city. That in turn is expected to spur significant growth in those areas as discussed already, Vietnam is urbanizing rapidly and significant growth in Hanoi’s population is forecast in the coming years. The population of the Dong Anh and west of West Lake regions is forecast to grow from 370,000 in 2005 to about a million in 2020. However, in the baseline, this growth would occur in the ‘Los Angeles’ style unplanned medium-density manner that typifies peri-urban growth in Vietnamese cities today. As a result of fragmented institutional responsibilities, rigid standards, lack of effective planning controls, it is likely that growth would occur in a manner that is not compatible with competitive public transport services. International experience suggests that for growth to occur in ways that are compatible with competitive public transport even in the long-term (even as incomes rise) effective urban planning plays a crucial role. As the experiences of Singapore and Curitiba best illustrate, unless growth occurs in high-density nodes about public transport corridors, it is difficult for public transport to compete effectively, specially as the populace becomes affluent and can afford private vehicles.

(3) Program to Support Air Quality, Traffic Safety, the Public Transport Authority, Transport Policy and Replication

In the baseline, as incomes rise, private vehicles in Hanoi would continue to increase. Even with public transport improvements, this would result in an increased level of trip making by private vehicles, ultimately increasing the risk that these increases would negate much of the benefits from the rest of the project. Auto ownership in Hanoi is currently low relative to other cities with similar income levels, in large part because of the relatively high taxes on auto ownership (and other related restrictions) being applied by City and national leadership. However the impact of such taxes will reduce as incomes rise (unless the taxes and other restrictions are increased concomitantly). Unless the city has a definite and strong vision for transport that precludes the widespread use of private vehicles and a comprehensive program to restrict ownership and use, the city will be under enormous pressure, especially from the urban elite, to relax restrictions related to private vehicle ownership and use. This is already evident: the city is under enormous pressure to relax rules related to auto ownership (linked to parking requirements), and has already rescinded (largely ineffective) restrictions on new motorcycle registrations in the central city.

GEF Alternative

(1) BRT and Public Transport Promotion

The key strategic contribution of the GEF co-financing will be to address barriers and risks related to successful project implementation and sustainability. The GEF Alternative project will finance public consultation, a media strategy and a strategy to build awareness and knowledge of Hanoi’s new leadership (with additional study tours for the new leadership). The experience from the preparation of this project thus far, as well as other international experience, suggests that such a strategy will be critical to ensure that the BRT system is implemented as appraised. The media strategy component of the GEF Alternative project will help to reduce the risks associated with BRT implementation.

Additionally, the GEF Alternative project will finance technical assistance to support the newly established public transport authority to execute its responsibilities effectively. In addition, through general support to train authority members in issues related to the planning, regulation and management of a complex ultimately multi-modal system, this GEF financed component will enable support for

- the concessioning process to identify operators for the BRT. The financial sustainability of the BRT depends on ensuring that the City is able to implement efficient operating arrangements that minimize the financial burden on government without compromising the quality of public transport service to the public.

- integration between trunk BRT lines and the rest of the bus system including BRT feeder lines. Effective integration with the rest of the bus system is essential to achieve the benefits (including the GHG benefits) of the BRT. Without GEF support there is a risk (as with other mass transit systems including recent BRT systems in Jakarta and the metro system in Delhi) that the benefits and viability of the BRT investments would be compromised by competition from uncoordinated service offerings.

Finally, the GEF Alternative project will finance improvements in stations and pedestrian and bicycle access around BRT stations. In particular, based on extensive stakeholder and physical surveys, the GEF Alternative project will (i) co-finance the development of stations that enhance the Hanoi BRT’s brand image and attractiveness; and (ii) finance improvements to pedestrian and cyclist infrastructure and co-finance the construction of secure cycle parking facilities.

(2) Strategic Road Component and Sustainable Urban Planning

The GEF Alternative project will co-finance TA for the Department of Urban Planning and Architecture in Hanoi to address the key deficiencies in the current planning regime. The TA will support specific pilots in the area north of the red river to demonstrate public transport friendly development and will also help the department and City government develop a modern planning and plan implementation system that can produce and implement a sustainable urban plan for growth.

(3) Program to Support Air Quality, Traffic Safety, the Public Transport Authority, Transport Policy and Replication

In this sub-component, the GEF Alternative will co-finance development of price based approaches, including economic instruments that would address transport related problems such as congestion by encouraging a shift from private to public transport and reduce the overall volume of private motorized travel. An integrated set of activities illustrating the value of such instruments to address congestion, parking and other related problems are proposed. Furthermore, the GEF will co-finance replicability efforts to maximize the demonstration potential of HUTDP in other Vietnamese cities and the region.

Incremental Cost Matrix for HUTDP

Global Benefits

Making accurate estimates of GHG emission savings in the case of urban transport projects remains a difficult undertaking. The estimates below are limited to the impact of the BRT component of the project. The GHG impacts of the Program to Support Air Quality, Traffic Safety, the Public Transport Authority, Transport Policy and Replication (Component 3) and the land planning technical assistance activities (Component 2) are expected to be significant but difficult to quantify, and are not included in the calculations below. Thus, these estimates of GHG impacts can be considered conservative. The BRT is forecasted to have a 20% share of trips in the project corridors by 2020 (up from a 10% share for public transport at present). BRT can be expected to account for 5 percentage points of a modal shift to public transport and a 1% increase in the share of bicycle traffic.

Formal calculations of GHG emissions will be made as part of the GEF project, and the GHG emissions over the project life will also be monitored and reported on as part of the GEF project. An initial estimate of anticipated GHG emissions reductions attributable to this project has been made using the following basic approach:

| Transport emissions per mode | = | Number of vehicles | x | Distance traveled | x | Emissions per vehicle distance traveled |
| --- | --- | --- | --- | --- | --- | --- |

Forecasts of CO2 emissions saved are based on estimates of modal shift to BRT, combined with estimates of average trip distance, vehicle occupancy and modal carbon emission estimates.

Current modal shares

Table 1 presents modal shares and daily trip estimates by mode in the central core. The table shows that motorcycle trips predominate, with autos representing a small but rapidly increasing proportion of the mode share. Bicycle trips remain significant, especially for local journeys, whilst use of public transport is now estimated at around 10% of total trip making, up significantly from just a few years ago.  The public transport modal share has increased from about 2 percent in 1998 as a result of significant improvement in service quality.

Table A15.1:	2005 Hanoi Vehicular Trips by Mode

| Mode | Daily Trips (persons) | Modal Share (percent) |
| --- | --- | --- |
| Bicycle | 516,400 | 9.6 |
| Motorcycle | 3,942,600 | 73.5 |
| Car/Taxi | 368,400 | 6.9 |
| Public Transport (Bus) | 534,300 | 10.0 |
| All | 5,361,700 | 100.0 |

Source:  HUTDP BRT Draft Feasibility Studies

Traffic Forecasts

BRT traffic demand was based on a modal choice analysis. Two sets of forecasts based on different land-use forecasts have been made to assess the impact of the BRT: the first is based on the official Hanoi masterplan which calls for limiting center city growth and rapid urbanization in the urban periphery; and an alternative forecast based on recent trends that suggests slightly higher center city populations and slightly slower growth in the periphery.  As discussed below, both methodologies yield BRT demand estimates within 5 percent of each other.

#### (ii) Year 2010 Forecasts.    Between 230,000 to 243,000 daily BRT trips are forecast in 2010. The vast majority of the rider-ship (about 85 percent) is drawn from existing bus passengers with diversions from motorcycles representing the bulk of trips diverted from private modes.

#### (iii) Year 2020 Forecasts.  Between 352,000 to 379,000 daily BRT trips are forecast in 2020 with about 20 percent of the riders being drawn from private vehicles, predominantly motorcycles.

In this context, the baseline planning estimates used by Hanoi, which form the basis of the current estimates, assume that public transport use will continue increasing and growth in auto usage will be modest.  These assumptions produce conservative estimates of the impact of the proposed BRT.  In reality, without significant improvements in public transport, such as the proposed BRT investments, the baseline public transport shares could not be achieved.  In other words, the baseline (without project) forecasts over-estimate public transport usage, and thus under-estimate project impact.  Similarly, if baseline auto ownership is under-estimated, the potential impact of the BRT on CO2 emissions is similarly under-estimated.

Emissions Estimates

The modal choice analysis also provided estimates of BRT trip length distribution, and traffic flows on the BRT corridors.  These data were used to generate with and without project CO2-equivalent emission estimates.  As Table A.A2 indicates, these calculations suggest that approximately 1.70 to 2.23 million tons CO2-equivalent emissions reductions are attributable to BRT in Hanoi over the 15 year period from 2005 to 2020.

Table A15.2. Estimated GHG Emissions Reductions Attributable to BRT

Annex 16: STAP Expert Review and Response

Vietnam:  VN-Hanoi Urban Transport Project

See HUTDP Executive Summary, Annex C.

Annex 17: GEF Secretariat and other Agencies’ Comments and IA/ExA Response

See HUTDP Executive Summary, Annex C.

Annex 18: Maps

Vietnam:  VN-Hanoi Urban Transport Project

Maps to be inserted based on Project Appraisal.

Annex 19: Stakeholder Participation Plan

Vietnam:  VN-Hanoi Urban Transport Project

A Public Participation Strategy is considered an important element of the BRT project component.   This bus way system would have significant benefits for many residents of Hanoi at present and is key to the sustainable development of the city in the future: current riders will see a higher level of service, congestion will be alleviated as riders switch from private modes to PT, the growth of the city can be facilitated along the corridors as accessibility increases and consequently land values outside the center can increase. Still, the introduction of a BRT system could face significant challenges. Some groups, such as motorcycle riders, may perceive that they were better off before road space was dedicated for use of buses, and feel that the improved BRT service is still inferior to bus services and car usage. Others may perceive glitches in the concept or implementation. In addition, it is important to ensure that Hanoi residents and decision-makers perceive the BRT in a manner consistent with what is being planned, that is a high-quality, efficient rapid, and modern mass transit system. A strategically planned and well-executed public consultation strategy is an important element of Hanoi's plan to manage these challenges.

Based on the experience of previous successful efforts to introduce comparably significant changes in the urban transport environment, the Stakeholder Participation Plan will include the following:

- Consulting the public on the BRT, and seeking their input primarily through scheduled “town hall” meetings;

- Generating public awareness, involvement and enthusiasm and transforming that into sustained political support for the BRT; and

- Instituting ways to generate interest in BRT through the media.

Language, culture and context are also important elements of any effective consultation strategy. Good connections with Hanoi media and Community Associations will be valuable, particularly given the need to raise the media profile of the proposed BRT system with limited resources.

During the PDF-B phase of the project, the Stakeholder Participation Plan was informed by two groups:

- Focus groups from a wide range of stakeholders in Hanoi that will be impacted by BRT; and,

- Selected stakeholders including special interest groups, the public sector, media and the private sector.

Results from each group are outlined in the section below.

### (1) Focus Groups

Based on the current state of public transport usage in the city, the project has selected and interviewed 170 persons and classified them into 8 categories of focus groups as shown in the Table 19.1 below.

Table 19.1	Selected Focus Groups and Number of Participants

| Focus groups | No. of people |
| --- | --- |
| Student group | 34 |
| Retired group | 10 |
| Motorcycle riders group | 51 |
| Bus riders group | 16 |
| No private means of transport group | 21 |
| Inhabitants of new urbanization group (where BRT is accessible) | 9 |
| Small business around Hoan Kiem lake | 10 |
| Inter-provincial passengers | 19 |
| Total | 170 |

Source: BRT feasibility study, 2006

Evaluation of Focus Group’s Interest

The opinions and feedback of interviewees were collected as the basic input for the formulation of the Public Consultation Strategy for BRT.  As this is a new public transport mode in Vietnam, the result of the stakeholder interviews needs to be realistic and properly reflected. After asking general questions about the existing bus system, an introduction about BRT was made by the consultant before inviting the interviewee’s opinion. The interests of the respondents about the existing bus system are summarized in the following Table.

Table 19.2:	Focus Group Responses about Existing Bus System

| Criteria | Evaluation of people (%) |
| --- | --- |
|  | Good | Acceptable | Not good | No idea |
| The availability (in term of number of routes) | 14.7 | 45.8 | 34.7 | 4.8 |
| Service provided by bus staff | 12.9 | 49.4 | 32.3 | 5.4 |
| Safety of bus | 17.6 | 35.9 | 41.8 | 4.7 |
| Quality of bus (appearance and hygienic) | 15.3 | 51.2 | 30.6 | 2.9 |
| Ticketing system | 14.7 | 49.4 | 27.1 | 8.8 |
| Ticket price | 27.6 | 53.5 | 12.3 | 6.6 |
| Transit time for load and unload pax. | 18.8 | 44.1 | 32.3 | 4.8 |
| Travel time | 12.9 | 51.8 | 34.1 | 1.2 |

Source: BRT feasibility study, 2006

Overall Findings from Focus Groups

The focus group participants are recruited by random selection, indifferent to gender, age or occupational differences. Information about interviewees is presented in Table 19.3. Detailed responses from interviewees are summarized in Table 19.4.

On the survey, the motorcycle rider group constitutes 53% of the total sample, followed by the current bus riders group (23%), walking group (approximately 11%), while the remaining 13% are those who travel by other modes such as car, bicycle, motorbike, taxi or share rides with others. Although the biker group makes up the major portion, not all of them are satisfied with their current transport situation, around 30% of them are concerned about the lack of safety due to congestion and conflicts with public transport users. The survey result also showed promising potential of public transport development: over 70% of interviewees said they would likely use bus to travel around if bus services are improved; up to 95% expressed their desire for decrease waiting time; 69% of interviewees are willing to wait for bus only up to 5 minutes, 26% are willing to wait up to 10 minutes, and only 4% are willing to wait up to 15 minutes.

Table 19.3:	Characteristics of Interviewees

| Age | Number of interviewees | Occupation | Number of interviewees |
| --- | --- | --- | --- |
| 18-25 | 71 | Office staff | 43 |
| 26-33 | 42 | Student | 58 |
| 34-41 | 22 | Worker | 7 |
| 42-49 | 7 | Governmental officer | 20 |
| Over 50 | 28 | Retired | 22 |
|  |  | Private business | 20 |
|  | 170 |  | 170 |

Source: Own estimates

Table 19.4:	Summary of Responses

| Current means of transport1 | Motorbike | Bicycle | Car | Bus | Walk | Honda om | Depend on other |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 90 | 12 | 6 | 39 | 29 | 7 | 15 |
| Likely use of public transport | Yes | No | Undecided |
|  | 102 | 20 | 48 |
| Willing time to wait for bus | ≤ 5 minutes | 10 minutes | 15 minutes |
|  | 117 | 45 | 8 |
| Finding information about public transport | Mass media | Web | Asking experience of current bus riders | From street guide board |
|  | 104 | 15 | 75 | 45 |
| Knowledge about BRT system2 | Mass media (newspaper, TV, web) | Abroad | Unknown |
|  | 52 | 34 | 86 |
| Support for private lane | Support | Oppose | No comment |
|  | 132 | 11 | 27 |
| Likely use BRT in the future | Yes | No | Undecided |
|  | 110 | 7 | 53 |
| Personal view about BRT | Supportive | Opposing | Need further study |
|  | 102 | 5 | 63 |

Source: BRT Feasibility Study, 2006

Notes:    1 Some data might larger than the actual samples because 22 interviewees use more than one means of transport

2 Some data in this part might bigger than actual samples because some use more than one tool search channels.

#### (2) Selected Stakeholders

Ten individual interviews with representatives of various organizations and business associations were conducted by the Consultants. The interviewed representatives include the following:

Hanoi Police Service’s representative

Media representative

Social community representative

Transportation representative

Representative of Vietnam Association for safe Water and Environment Sanitation

Representative of Business Community

Representative of the Government

Representative of Hanoi People’s Committee

Representative of Vietnam Road Administration

Representative of Hanoi Television.

Generally, representatives expressed their support to the development of urban public transport in general and public passenger transport in particular.  For BRT project, most of representatives showed their concern about the limited space for transportation and the feasibility of dedicated BRT lane.

General Conclusions of Individual Interviews

Although all of the interviewees support the development of public transportation, and limiting private transport to alleviate traffic congestion, most of them express their concern that BRT’s exclusive lane will further limit the space on a number of streets. Representatives from transportation management authorities express two concerns about the development of BRT in Hanoi: that there is no space for BRT’s exclusive lane, and that transportation habits of the Vietnamese differ from others.  One of the advantages of BRT system is to provide access for disable people.  However, the Secretary General of Hanoi Sport Association for the Disabled quoted that Vietnam does not have appropriate transportation infrastructure for disabled people. Some representatives do not directly express their opposition to the BRT system but they believe that BRT is more feasible and practical if it is developed from ring roads directing to the centre.

In conclusion, the personal interviews indicate the fact that representatives of professional and social organizations have limited knowledge of BRT systems in general and of the BRT project proposed for Hanoi city in particular.  The public outreach campaign should be directed not only to the general public, but also targeted to professional and social organizations to respond to their particular concerns.  This targeted outreach should provide their members with a better knowledge of the BRT system characteristics, including technical (infrastructure and equipment), operational, social, economic, and financial aspects, and its positive impacts and advantages to the city.

Consultations with Vietnam Association for the Handicapped

Consultations have been held with the disabled, which had been identified as a key stakeholder group during project preparation. Representatives of HUTDP have made a presentation at a meeting of the VAH (Vietnam Association for the Handicapped) which highlighted BRT and implications for the disabled.  Regular meetings have subsequently been held with the VAH to inform them of HUTDP’s progress and to ensure that they become a constituency.

This work has led to further discussions at the Hanoi Disability Forum, which has allowed for an enhanced understanding of concerns and ensured that these concerns are addressed in the project’s design. Such outreach to the community is ongoing, with the PMU being introduced to the VAH and taking the lead on continuing to be responsive to the concerns of various stakeholder groups.

Elements of the Stakeholder Participation Plan

The Stakeholder Participation Plan will be implemented by the BRT Consultation, Communications and Media Strategy (see Component 1. B under Annex 4).  The plan focuses on two key elements, both allowing stakeholders to participate in the implementation of BRT in Hanoi. The public involvement strategy is intended to enable public participation in key decisions related to the BRT System, to keep the public updated on the progress and key decisions on implementation, and provide a framework to incorporate public feedback into all elements of system design and operation. In addition, the subcomponent is intended to support a media management strategy, which will provide media content and appropriate materials for TV, radio, print, and public billboards and facilitate the media’s ability to promote the BRT concept. See Annex 4 for complete details.

- Public Consultation and Communication Strategy

  - Series of stakeholder consultations targeting input from focus groups, and consultations with street (neighborhood) communes and shopkeepers associations and guilds in affected areas

  - Stakeholder consultations targeting input from Non-Governmental Organizations such as VNAH, Asia Injury Prevention Foundation, National Coordinating Council on Disability of Vietnam, etc.

  - Build up BRT Website Organize a “Design BRT Website” Contest

  - Organize Contests of “BRT’s Vietnamese Name”, “BRT’s Logo” and “BRT’s Slogan”

  - BRT - Accessible Transit”

  - Organize training course on “Customer Serving Technique” for bus and BRT drivers

  - Expand “Painting Traffic Lanes” model on BRT routes

  - Publicize “Bus Priority Signal System”

  - Mobilize “BRT Fund” and “BRT Week” in Hanoi

  - Organize seminars and/or conferences/ Conduct sociological research.

- Media Relations Strategy

- Press Conferences

- Disseminate Press Release

- TV Reporting

- Advertise the BRT

- Monitor media coverage.

wb156224

N:\Projects\Vietnam\P083581 - Hanoi\GEF TF053407\March 24 2006 submission to GEF council\HUTDP_Brief_April_26.doc

04/26/2006 3:07:00 PM

# Footnotes

* By supporting the proposed project, the Bank does not intend to prejudice the final determination of the parties' claims on the disputed areas

HIDEP, Hanoi Urban Environment Fact Book [Ref. 1], JICA, May 2005, p. 19

Ref. 1 p. 19, and HIDEP, Main Points of Progress Report [Ref. 2], JICA, May 2005, p. 14

Ref. 2, p. 2

Ref. 1, p. 19

All transport modal shares in this paragraph come from Ref. 1, p. 20

Basic Case for Bus Priority in Hanoi, PADECCO Report, p. 2-21

All figures in section 1.1 come from the following two reports: (i) Study of urban public transport conditions in Hanoi, draft final report, Gordon Nielson, March 2004, and (ii) Strategic options for private sector participation for urban transport in Hanoi, PPIAF - MVA final report, November 2004.

All figures in paragraph 1.1 come from the following two reports: (i) Study of urban public transport conditions in Hanoi, draft final report, Gordon Nielson, March 2004, and (ii) Strategic options for private sector participation for urban transport in Hanoi, final report, November 2004.

Basic Case for Bus Priority in Hanoi, PADECCO Report, p. 2-21

Calculation based on the following: car ownership (in car / 1000 people) has been growing at the average rate 13% per annum in the last four years [from 8 cars / 1000 people in 2001 to 13 cars / 1000 people in 2005], at the same time Hanoi’s population has been growing at the average rate of 3%. Therefore the number of registered cars has been growing at roughly 16% per annum over the last four years.

and a Comprehensive Poverty Reduction and Growth Strategy (CPRGS). Government’s guidance for the 2006-2010 SEDP is that these two planning instruments should be merged.

In part because of these disbenefits to bus passengers, an alternative bus reorganization scheme was prepared (see Section 8.2.1). The improvements in bus services is not yet reflected in the economic analysis

In part because of the negative impacts on vehicle speeds caused by the reduction of road capacity, the BRT insertion was modified to reduce the impact on road capacity, sharing the road space in the most narrow streets.  The improvement in road capacity is not yet reflected in the economic analysis.

See footnote (8) above.