UNDP Project Document

Governments of Bangladesh, Bolivia, Guatemala, Jamaica, Kazakhstan,

Morocco, Namibia, Niger, Samoa, and Vietnam

United Nations Development Programme

Community-based Adaptation

TABLE OF CONTENTS

Acronyms	4

SECTION I: Elaboration of the Narrative	5

PART I: SITUATION ANALYSIS	5

Context and global significance	5

Institutional, sectoral and policy context	5

Stakeholder analysis	6

Baseline analysis	8

PART II: STRATEGY	8

Project Rationale and Policy Conformity	8

Project Goal, Objective, and Outcomes and Outputs/Activities	10

Project Indicators, Risks and Assumptions	18

Expected global, national and local benefits	19

Country Ownership: Country Eligibility and Country Drivenness	19

Sustainability	20

Replicability	21

PART III: MANAGEMENT ARRANGEMENTS	22

PART IV: MONITORING AND EVALUATION PLAN AND BUDGET	23

Monitoring and Reporting	23

Independent Evaluation	26

Learning and Knowledge Sharing	27

PART V: Legal Context	29

Section II: Strategic Results Framework and GEF Increment	30

PART I: INCREMENTAL COST ANALYSIS	30

PART II: LOGICAL FRAMEWORK ANALYSIS	32

SECTION III: Total Budget and Workplan	36

SECTION IV: ADDITIONAL INFORMATION	39

PART I: OTHER AGREEMENTS	39

PART II: TERMS OF REFERENCES FOR KEY PROJECT STAFF AND MAIN SUB-CONTRACTS	39

(1) Tasks and outputs	44

PART III:  STAKEHOLDER INVOLVEMENT PLAN	48

Signature Page	49

Annex 1:  CCPS Background Activities Conducted During PDF-B	50

I.  BANGLADESH: DRAFT CBA COUNTRY PROGRAMME STRATEGY	50

Annex 2:  Project Design and Monitoring and Evaluation Framework for Community Based Adaptation	60

1. INTRODUCTION	60

2. GOAL OF COMMUNITY BASED ADAPTATION	60

3. PROJECT AND PROGRAMME STRUCTURE	61

4. MONITORING AND EVALUATION (M&E)	62

4.1 The SGP Impact Assessment System	63

4.2  The Vulnerability Reduction Assessment	63

4.3 National-Level M&E	66

4.4 Global-Level M&E	67

4.5 Adaptive Management of M&E	67

5. PROGRAMME DEVELOPMENT FRAMEWORK	67

5.1:  Scoping and designing: the CBA Country Programme Strategy (CCPS)	68

5.2:  Assessing Current Vulnerability	68

5.3:  Assessing Future Climate Risks	69

5.4:  Formulating an Adaptation Strategy	69

5.5:  Continuing the Adaptation Process	70

6. PROJECT DEVELOPMENT FRAMEWORK	70

6.1:  Scoping and designing community projects	70

6.2:  Assessing Current Vulnerability	70

6.3:  Assessing Future Climate Risks	71

6.4:  Formulating an Adaptation Strategy	71

6.5:  Continuing the Adaptation Process	71

Annex 3:  Community-Based Adaptation Programme Country-Level Toolkit	72

1.  INTRODUCTION	72

2.  PORTFOLIO DEVELOPMENT	72

1.  CBA Country Programme Strategy Development	72

2.  Initial National CBA Capacity Building Phase	73

3.  Project Concept Development	74

4.  Project Concept Review	74

5.  Project Planning and Baseline Measurement Phase	74

6.  Full Proposal Review	75

7.  Implementation, progress reporting, and ongoing M&E	76

8.  Final Project Review	76

9.  Programme Conclusion	77

II.  A USERS GUIDE TO THE VULNERABILITY REDUCTION ASSESSMENT	78

1.  Community-level Awareness Raising	78

2.  The Structure of the VRA	78

3.  The H-form	80

4.  Calculating the Final VRA Score, Measuring Percentage Change	82

5.  The SGP Impact Assessment System and the SPA Criteria	82

III.  ATTACHMENTS:	83

Attachment 1:  CBA Country Programme Strategy Template and Guidelines	84

Attachment 2:  CBA Project Concept Template and Planning Grant Application	88

Attachment 3:  CBA Concept Review Form	91

Attachment 4:   CBA Full Proposal Template and Guidelines	94

Attachment 5:  CBA Full Proposal Review Form	103

Attachment 6:  CBA Project Progress Report	105

Attachment 7:  CBA Final Grantee Report and Lessons Learned Template	109

Annex 4:  Examples of CBA Projects	115

Annex 5:  UNDP Responses to Comments by Germany, Switzerland, France and the United States on the Community Based Adaptation Programme (PIMS 3508)	118

Annex 6:  UNDP Responses to Comments by the UNDP Project Appraisal Committee	128

Annex 7:  UNDP Response to GEFSec Review, April 2006	131

Annex 8:  Responses to STAP Reviewer’s Report, February 2006	135

# Acronyms

| AC | Adaptive Capacity |
| --- | --- |
| AIACC | Assessments of Impacts and Adaptations to Climate Change Project |
| ALM | Adaptation Learning Mechanism |
| APF | Adaptation Policy Framework |
| APR | Annual Progress Report |
| AWP | Annual Work Plan |
| CBA | Community-based Adaptation |
| CBAS | Community Based Adaptation Strategy |
| CBD | Convention on Biological Diversity |
| CBOs | Community Based Organizations |
| CC | Climate change |
| CCPS | Country CBA Programme Strategy |
| COP | Conference of Parties |
| CP | Country Programme |
| CPMT | Central Programme Management Team |
| CPS | Country Programme Strategy |
| FSP | Full Size Project |
| GCF | Global Cooperation Framework |
| GEF | Global Environment facility |
| GHG | Greenhouse Gas |
| IA | Implementing Agency |
| IAS | Impact Assessment System |
| IPCC | Intergovernmental Panel on Climate Change |
| IW | Inception Workshop |
| LDC | Least Developed Countries |
| M&E | Monitoring and Evaluation |
| NAPA | National Adaptation Programme of Action |
| NC | National Coordinator |
| NCC | National Coordinating Committee |
| NGO | Non-Governmental Organizations |
| NRM | Natural Resource Management |
| NSC | National Steering Committees |
| OFP | Operational Focal Points |
| OP | Operational Programme |
| PIR | Project Implementation Review |
| RCF | Regional Cooperation Framework |
| SIDS | Small Islands Developing States |
| SGP | Small Grants Programme |
| SPA | Strategic Priority on Adaptation |
| STAP | Scientific and Technical Advisory Panel |
| TRA | Threat Reduction Assessment |
| UN | United Nations |
| UNDP | United Nations Development Programme |
| UNFCCC | United Nations Framework Convention on Climate Change |
| V&A | Vulnerability and Adaptation |

# SECTION I: Elaboration of the Narrative

## PART I: SITUATION ANALYSIS

1. In recognition that small communities are often the most severely affected by climate change impacts, yet the least equipped to cope and adapt, the Global Environment Facility (GEF) Secretariat proposed (in document GEF/C.23/Inf.8 of April 28, 2004) that up to 10% of the resources under the Strategic Priority on Adaptation (SPA) be devoted to piloting community adaptation initiatives using a mechanism similar to the Small Grants Programme (SGP). In outlining key elements of the Strategic Priority on Adaptation (SPA), the GEF indicated its intention to improve its own capacity and that of others to facilitate community-based adaptation (GEF/C.23/Inf.8/para 23).  To accomplish this, a pilot project addressing community-based adaptation has been designed to create small-scale ‘project/policy laboratories’ and generate knowledge about how to achieve adaptation at the local level through more effective national and intergovernmental projects and policies.

### Context and global significance

2. GEF Council paper GEF/C.23/Inf.8/Rev.1 (GEF Assistance to Address Adaptation) states that:

“Adaptation to climate change is increasingly recognized as significant to the attainment of sustainable development and as essential for the achievement of many global environmental objectives. While many scientific uncertainties exist, the scope and magnitude of the risks now known to be associated with climate change represent a challenge to environmental and economic goals that must be taken into account today ... the understanding of human response to climate change is still at an early stage, with much to be learned from historical experience. However, in general it is known that [among numerous factors]  the capacity to adapt is determined by access to resources, information and technology, the skill and knowledge to use them, and the stability and effectiveness of cultural, economic, social, and governance institutions that facilitate or constrain how human systems respond. Those with the least resources have the least capacity to adapt and are the most vulnerable.”

3. UNDP-GEF, led by the Capacity Development and Adaptation Cluster (CDAC), has designed the CBA initiative to target highly vulnerable communities in ten countries, and to assist them to increase their capacity to adapt to long-term climate change, including variability.  The CBA project will employ the SGP’s operational mechanisms to implement the project. The selected countries for the CBA include Bangladesh, Bolivia, Guatemala, Jamaica, Kazakhstan, Morocco, Namibia Niger, Samoa, and Vietnam.  CBA funding, which will be guided by the SPA guidelines, will support community level interventions that improve adaptive capacity of communities/ecosystems to climate change. Among other things, this will entail that global benefits in the focal area that GEF works which are realized through community based interventions are resilient in the context of climate change.

### Institutional, sectoral and policy context

4. The CBA initiative will work within the national institutional and legal framework within each of the participating countries.  In targeting adaptive capacity to address long-term climate change (including variability) impacts within individual communities, attention will also be paid to capacity and policy gaps at local, sub-national, and national levels.  As a first step, (as described below in annex 3, section 3, attachment 1), a Country CBA Programme Strategy (CCPS) will be developed for each country, which will describe patterns of community-level vulnerability to climate change including variability, priority sites, and adaptation measures for project implementation. The CCPS will also define the institutional and policy context in which appropriate adaptation measures must be implemented including capacity and policy gaps that need to be addressed in order to enhance adaptive capacity to climate change.

5. During the PDF-B phase such analyses were undertaken in Samoa, Bolivia, Niger and Bangladesh, which resulted in 4 draft CCPS documents (see annex 1). These documents, once finalized will form the CCPS that will guide CBA identification and selection in each country. The documents prepared by the 4 countries during the preparatory phase will serve as guidance for the remaining countries as they develop their own country specific CCPS.

### Stakeholder analysis

6. Stakeholder groups will be engaged at the global level to national and sub-national levels. For example, national climate change coordinators in each country, relevant ministries at the national level, to NGOs, CBOs and individual communities, along with SGP NCs, will form the stakeholder group at the local scale. The table below outlines examples of key stakeholder groups and their potential roles in the project

| Global Level – GEF, UNDP-GEF, SGP | Global guidance Project management Execution of funds M&E support Baseline development support Technical support including quality control over project selection Institutional support Lesson distillation and documentation |
| --- | --- |
| National Level (e.g., as part of a National Coordinating Committee (NCC) – SGP Country Programme, Government focal point, GEF OFP, national IA project staff, national climate change focal points, NGOs, other development partners | Capacity development (trainee) Capacity development (trainer) CBA proposal identification and approval Baseline development Support/outreach to local project participants Participation in project selection Participation in funding disbursal and management M&E |
| Local Level – Community members, NGOs, CBOs, local government, trade associations, others. | Capacity development (trainee) Local V&A assessment Project identification and proposal development Baseline development Implementation of CBA activities M&E |

7. Key stakeholders will participate in capacity building activities at each level – particularly the local and national – on designing GEF eligible adaptation to climate change proposals and on implementation requirements when developing the portfolio of CBA projects. In line with the SGP operational modality, grants for CBA projects will be released only to local NGOs and CBOs.  However, projects can be implemented (and co-financed) in partnerships with other relevant stakeholders, from international NGOs, to public agencies, to the private sector.

8.  Consistent with UNDP-GEF’s use of SGP’s existing operational modality and mechanisms for community-based project delivery, transaction costs for the development of CBA country programmes and community projects are expected to be minimal.  Where delivery of CBA project components in SGP countries adds additional, incremental costs to existing SGP operations, those costs considered additional to SGP’s normal operations will be borne by the CBA project.

9. Co-financing will be sought for the FSP at the Programme level on a 1:1 basis.  Co-financing will be secured at the level of the country programme, and at the global level.  In addition, NGO grantees at the local level will also be encouraged to secure co-financing on a 1:1 basis, both in the form of cash and in-kind support, as per standard GEF/SGP practices.

10. In each country, key stakeholders will be engaged in the formulation and implementation of each CBA project. The CBA National Coordinator (in effect, the SGP NC) will seek co-operation of stakeholders at the national scale through the NCC, to develop capacity among NGOs and CBOs at the local level in designing and implementing CBA projects. The NC will be supported by UNDP-GEF and the GEF-SGP with the necessary technical support for the identification and development of potential CBA projects in each country. Capacity will be developed for the selection and implementation of CBA projects, a task that must be undertaken through a partnership of local (NGOs and CBOs) and national level (NCC) actors, with support from UNDP-GEF and GEF-SGP as deemed necessary. In addition to key capacity building activities, national stakeholders will play a critical role in the following:

- Building the capacity of community members to understand and respond to adaptation issues

- Developing baselines for monitoring and evaluation

- Setting adaptation priorities with community members

- Designing and implementing community adaptation-related activities

- Sustaining the process of adaptation at the community level

- Monitoring and evaluating the outcome of the implementation process

11. CBA proposals by NGOs and CBOs must be aligned with the overall national adaptation priorities. National climate change focal points, through participation in the NCC, will provide input to ensure complimentarity between a country’s proposed CBA activities and its pressing vulnerabilities and adaptation needs, as identified through existing processes (i.e., the National Adaptation Programme of Action (NAPA), the National Communications process, as well as participatory community vulnerability assessment undertaken through the current project).

12. Participatory community vulnerability assessment will be a pre-condition for proposal development under the CBA Programme because it will contribute to the development of a baseline measure of adaptive capacity. To achieve this, the NC, under the guidance of UNDP-GEF and SGP, will be involved in building the capacity of local stakeholders in applying the Vulnerability Reduction Assessment at the community level, other approaches based on the APF guidelines, as well as appropriate UNFCCC V&A stakeholder methodologies.  Key tools to be used are described in more detail in annex 2.  It is expected that this effort will lead to effective understanding of the relationship between underlying livelihood problems and climate change risks. The participatory process will also provide an opportunity to initiate vital interactions between national stakeholders, community members, NGOs and CBOs during the period of project implementation.

13. Each country’s CCPS will identify stakeholders at the national and local level who will be engaged in the CBA process (See the example of the indicative Bangladesh CCPS developed during the PDF-B phase in annex 1).

### Baseline analysis

14. The Intergovernmental Panel on Climate Change (IPCC) defines vulnerability as the degree to which individuals and systems are susceptible to or unable to cope with the adverse effects of climate change, including climate variability and extremes. This is a function of:

• 	Sensitivity, which includes the extent to which natural or social systems are sensitive to changes in weather and climate (the exposure-response relationship) and the characteristics of the population, such as the level of development and its demographic structure

• 	Exposure to the weather or climate-related risk, including the character, magnitude, and rate of climate variation and long term change

• 	Adaptation measures in place to reduce the burden of a specific adverse outcome (the adaptation baseline), the effectiveness of which determines in part the exposure–response relationship.

15. The CBA program will employ a similar definition of an adaptation baseline to determine, in part, what may be eligible for SPA funding.  As outlined in the SPA guidelines: “Consistent with GEF operation criteria, project proponents are expected to outline first a baseline scenario. This baseline scenario may represent a “business-as-usual” wherein the country undertakes only those activities considered to be in its baseline development planning. Beyond the baseline scenario, an alternative GEF scenario should be constructed to include activities that, in the absence of global warming, would be expected to produce the desired global environmental benefits. However, to this scenario should be added activities to be funded under the SPA that will ensure the robustness of those global environmental benefits by improving the resilience of the systems concerned. The difference between relative costs associated with the baseline scenario and the alternative scenario are the incremental costs. Only those costs associated with the second part of the alternative scenario—those necessary to ensure the robustness of the global environmental benefits—will be funded from the SPA. The cost associated with the first part of the alternative scenario—those necessary to deliver the global benefits in the absence of global warming—will be funded from the focal area allocations of the GEF Trust Fund.”  The SPA is therefore concerned with increasing the robustness of global environmental benefits in the focal areas within which GEF works in the face of climate change including variability. SPA funds may only be used for this robustness-building – provision of global environmental benefits is considered baseline, and must be met through co-financing or focal area allocations.

16. The baseline scenario for the CBA consists of the sum of all baselines for each individual CBA projects, which cannot be known a priori.  In general terms, it can be assumed that the adaptation baseline is limited by barriers to adaptive capacity.  These barriers may be technical in nature – a lack of knowledge of possible adaptation responses, for example, or institutional – for instance, inadequate community organization.

17. See annex 4 for examples of projects that meet these requirements.

## PART II: STRATEGY

### Project Rationale and Policy Conformity

18. The approach outlined here for implementing adaptation activities is designed to be part of the wider GEF priority to pilot a strategy to implement climate change adaptation activities. Financing for CBA is proposed under the new GEF Strategic Priority “Piloting an Operational Approach to Adaptation”, described in GEF Council document GEF/C.23/ Inf.8.  In this document, the GEF proposed that funds under the SPA (up to 10% of these resources, or US$ 5 million) should be allocated to the piloting of community adaptation initiatives.  The time frame for implementation of the CBA is five years.

19. The CBA will help communities to increase their adaptive capacity to deal with current climate variability as well as for adaptation to future climate change including variability. Although the overall goal of the SPA is mainly concerned with long-term climate change including variability, communities are generally most motivated to address short-term problems.  However, by adopting the approach of increasing adaptive capacity, both short-term and long-term issues can be addressed simultaneously, as adaptation to current patterns of variability is often the best preparation for adaptation to future challenges. It is important to ensure that adaptation to long term climate change pressures reflects a dynamic approach in implementation. This consideration has guided the choice of the AFP Adaptive Capacity approach for the CBA programme. Innovative approaches for mobilising communities on a voluntary basis will be used for raising awareness, building the adaptive capacity of local communities to climate change, and enhancing ownership and sustainability of relevant initiatives. Collaboration with UNV to identify opportunities for the mobilisation of volunteers to support CBA activities, including monitoring and evaluation, and to support the building of sustainability mechanisms for community-based initiatives will be explored.  UNV involvement in the project including modalities for collaboration and detailed terms of reference for UNV volunteers will be formulated once implementation commences.

20. The Global CBA Team, headed by UNDP-GEF, will lead the CBA Programme, of behalf of the GEF Secretariat and other Implementing Agencies, and under the direction of the GEF operational guidelines for the SPA. CBA Programme activities will be implemented according to each country’s specific conditions, ideally as expressed in their National Communications, ongoing work on NAPAs, and/or national and local consultations on adaptation. UNDP – through CDAC, in coordination with GEF-SGP – will coordinate the implementation of activities that improve adaptive capacity of communities in diverse regions using the SGP mechanism.  Moreover, a partnership is currently under negotiation with the UNV programme for facilitating community mobilisation and the exchange of know-how at the local level through using international, national, online and corporate volunteers to catalyse community dynamics and facilitate local capacity development. The inclusion of a diversity of socio-economic settings will provide a meaningful basis for lesson learning, replication and up-scaling (through linkages to UNDP’s Adaptation Learning Mechanism). Country programmes will focus on relatively discrete geographic regions – e.g., ecosystems, landscapes, watersheds – to ensure synergies among projects leading to greater and more measurable impacts, but also to identify policy lessons more confidently.

21. The criteria used to select CBA projects are guided by GEF operational guidelines for the SPA and the GEF Instrument, which establishes the principle of incremental reasoning. This means two things – firstly, that GEF funding will be used to fund a subset of all possible adaptation interventions, namely those which satisfy the criterion of GEF funding through the provision of global environmental benefits; and secondly, that GEF funding will be only for that component which is deemed incremental in facilitating “adaptation” to climate change including variability.

22.  Under the baseline scenario, communities with low adaptive capacity tend to consume resources to deal with current climate uncertainties in ways that are non-sustainable under conditions of long-term climate change including variability.  Under the alternative, communities with greater adaptive capacity tend to consume resources in ways that are sustainable under conditions of long-term climate change including variability.

23.  Consistent with the concept of incremental costs, other adaptation interventions, which do not generate global environmental benefits, are expected to be funded through sources of co-financing. These activities are considered to be part of the baseline, and the costs for these activities will be met through co-financing raised at the global programme level as well as the local level.  Community-based adaptation activities which do not address GEB can be funded elsewhere through the SCCF and LDCF (and are deemed ineligible under this particular initiative).  Lastly, projects under the SPA must provide both GEB and adaptation benefits, and must make those GEB resilient to climate change including variability.  SPA monies may only be used for this purpose, and all other project components must be met through co-financing.

#### Fit within the GEF portfolio

24. The CBA is the first full size SPA-funded programme that pilots and demonstrates how vulnerability to climate change including variability can be reduced through adaptation at the community level. The outcome of the CBA programme is to demonstrate what measures can be taken to reduce vulnerability and/or increase adaptive capacity of communities to the adverse effects of climate change in GEF focal areas.

25. The CBA programme is important to the GEF portfolio for several reasons. Firstly, it will provide lessons in designing and implementing screening criteria for projects that are relevant to all GEF-funded community-based adaptation-related activities. Secondly, the diversity of adaptation-related activities emerging from the CBA will provide valuable lessons on the factors that must be taken into consideration in project design when attempting to improve adaptive capacity and/or reduce vulnerability to climate change drivers. At the end of this pilot, lessons learnt will permit a more a systematic approach to integrating climate change risks into all GEF focal areas at the community level.

### Project Goal, Objective, and Outcomes and Outputs/Activities

#### A Results-based Approach

26. The CBA programme is an overarching framework, designed to address the needs and priorities of the GEF SPA, as described in GEF Council Paper C.23.Inf.8.Rev.1.  Consequently, consistent with the principles of Results-Based Management, the CBA programme has a hierarchical set of results which it will achieve.  These include a Goal, Objective, and a set of Outcomes.

27. The CBA programme will achieve these results through the implementation of a portfolio of community-based projects in 10 pilot countries, in an approach analogous to the mechanisms employed by GEF’s Small-Grants Programme.  The selection and implementation of specific micro-projects in each country will be guided by a CBA Country Programme Strategy (CCPS or CBA CPS), each of which will have its own set of outcome targets that will be consistent with and contribute to the overall results of the CBA programme.  Each individual project will have a project-specific objective, which will contribute to the results to be achieved under the CCPS in each country.  Thus, there is a hierarchical structure to the CBA programme, as depicted in Figure 2.

Figure 1:  Hierarchical structure of the CBA programme

28. Each CCPS will be country-specific and country-driven, and processes in place (see annex 3, section 3, attachment 1:  CBA CPS Template and Guidelines) will ensure that CCPS’s are consistent with the overall Objective of the CBA programme.  Similarly, at the level of individual community-based projects, the specific project objective will be established by the communities themselves, subject to country-specific processes to ensure conformity with the CCPS and the programme-wide objective.

29. The following section describes the results to be achieved by the CBA programme as a whole.

30. The Goal of the Community-Based Adaptation (CBA) Programme is set by the GEF Council paper GEF/C.27/Inf.10 (Operational Guidelines for the Strategic Priority “Piloting An Operational Approach To Adaptation”), as “to reduce vulnerability and to increase adaptive capacity to the adverse effects of climate change in the focal areas in which the GEF work”.  As the contribution to the goal, the Objective of the CBA programme is "to enhance the capacity of communities in the pilot countries to adapt to climate change including variability."  Essentially, this objective addresses the community-based component of the GEF’s SPA.

31. It will thus provide the basis upon which the GEF and other stakeholders can effectively support small-scale adaptation activities.

32. To achieve the Objective of the programme, three Outcomes must be secured.  These are:

- Enhanced adaptive capacity allows communities to reduce their vulnerability to adverse impacts of future climate hazards

- National policies and programmes designed that include community adaptation priorities to promote replication, up-scaling and mainstreaming  of best practices derived from CBA projects

- Cooperation among member countries promoted for innovation in the design and implementation of adaptation to climate change including variability projects and policies.

33. Each of these three Outcomes corresponds with a different level in the hierarchical structure of the CBA, described above.  Outcome 1 will result from the individual community-based projects, which essentially constitute small-scale ‘project/policy laboratories’.   Benefits derived from individual projects will, however, have little value unless results are disseminated and the national policy environment is modified so as to promote replication within countries.  This is a primary function of the CCPSs, guided by the National Coordination Committee (see below), which will thereby achieve the second Outcome.  Finally, the value-added of a global programme only derives from cross-border exchange of lessons, which promotes innovation and expands the “universe” of adaptation options.  A major function of the Central Programme Management Team (see below) will therefore be to establish conditions under which the third Outcome can be secured.

#### Outcome 1: Enhanced adaptive capacity allows communities to reduce their vulnerability to adverse impacts of climate risks from both incremental and discrete events

34. The CBA programme will support the implementation of between 8 and 20 community-based adaptation projects, designed to enhance the adaptive capacity to climate change of participating communities, in each of ten countries (Bangladesh, Bolivia, Guatemala, Jamaica, Kazakhstan, Morocco, Namibia, Niger, Samoa, and Vietnam).  In order to ensure cost-effectiveness, projects will be implemented in areas that are particularly vulnerable to climate change including variability, and where there is high potential to secure global environmental benefits in the context of climate change. Projects are expected to emerge from each of the focal areas depending on local context specific vulnerability and adaptation analysis in each of the selected countries.

35. During implementation of the PDF-B, the establishment of a process for selecting projects was piloted in three countries.  In each country, this process involved:

#### 1. Modification of the existing SGP-NSC to form a CBA National Coordinating Committee

36. In countries where the GEF-SGP is already active, the CBA programme will be implemented under the existing established implementation infrastructure. This includes making use of existing organizational structures such as the SGP National Coordinator (NC) and SGP National Steering Committee (NSC). The NSC structure, however, will be reviewed with respect to the existence of expertise on climate change issues (including relevant sectoral expertise in climate change impacts and adaptation options), and if necessary, expanded to include relevant skills. The NSC structure will thereby form the foundation of what will be become a CBA National Coordination Committee (NCC).  The reliance on the current SGP NC and NSC will ensure a sustained and focused process for capacity development at the local level. The national SGP Programmes will be responsible for building the capacity of NGOs and CBOs.

37. Bangladesh, as the only GEF non-SGP country, participating in the PDF-B Phase-1 of the CBA programme, a special institutional arrangement has been identified for the implementation of the CBA projects.  The CBA will be incorporated into the Community Empowerment Component (3c) of the Comprehensive Disaster Management Programme (CDMP) – the Local Disaster Risk Reduction Fund (LDRRF).  The selection of projects and distribution of funds under the CBA programme will be managed through the same procedures as those set out for the LDRRF.  Thus, the CBA implementation will have guidance and overall supervision from the LDRRF Approval Committee, which is comprised of representatives of the Ministry of Food and Disaster Management (MoFDM), Ministry of Environment and Forests (MoEF), DFID, UNDP, and Chief Technical Advisor of the CDMP, and one Community Disaster Risk Management Expert from the civil society..

38. In order to ensure representation of the Climate Change Cell of the Department of Environment, the already existing Technical Review Committee of the LDRRF (for initial review and screening of proposals) will co-opt the Climate Change Technical Adviser as a member of the Committee.  Such a management and execution arrangement of the CBA will save transaction costs, thereby allowing bulk of the resources for actual implementation of the adaptation measures on the ground in the pilot areas. The TRC will screen project proposals based on the criteria approved by the LDRRF Approval Committee and UNDP-GEF.

39. The overriding guiding principle of implementation of the CBA programme will be to allow small NGOs, CBOs of the pilot region easy and expedited access to funds to ensure their timely and targeted utilization.  Proposals having exit strategy leading to future sustainability should get priority.  Day to day supervision will be done by the already full-time working Programme Component Implementation Specialist.  He will ensure that all monitoring, evaluation and reporting protocols associated with CBA are abided by.  The PCIS will report to the CTA of the CDMP.  The TRC will also establish a monitoring system to assess the resource utilization, outputs and outcomes/impacts at intervals set by the LDRRF Approval Committee

#### 2. Site selection

40. The selection of a geographic region within each country where CBA projects will be implemented will follow a multi-step process guided by the principles of the Adaptation Policy Framework (APF):

- In each of the pilot countries, vulnerability assessments available at the national scale will be reviewed to identify those regions of highest vulnerability to climate change including variability.

- Regions having high potential to deliver global environmental benefits, based on considerations of the GEF focal areas and assessments such as the potential rates of soil loss or reduction in productive capacity and information such as levels of globally significant biodiversity will be identified.

- An overlay of regions identified by these two criteria indicates priority ecosystems or landscapes for CBA projects (see Site Selection Figure, below, for a graphical representation of this process).  However, additional criteria may also be considered in different countries.  Additional criteria, such as the existence of social unrest, or pre-existing adaptation interventions, may be necessary to ensure effectiveness of CBA interventions and the avoidance of duplication of efforts.

- The criteria described in step (3) will then be used to select within the ecosystems and landscapes identified by steps (1) and (2) one or more locations that will serve as the focus of pilot CBA activities.  The 8 to 20 NGO/CBO projects in each country will be implemented in the identified locations. The aggregate impact of the 8 to 20 CBA projects will be to improve the adaptive capacity of individual community members to climate risks.

Figure 2: Site selection.  A hypothetical country with overlays of high vulnerability and high potential for global environmental benefits identifies the northwest as eligible for CBA.

#### 3. Development and application of criteria for project screening

41. Proposals for CBA projects will be assessed by country specific National Coordinating Committees on the basis of nationally-developed criteria relating to:

- Climatic vulnerability.  The proposal must relate to a sector identified at the national level (e.g. through NAPA or National Communication) that is particularly vulnerable to climate change including variability.  The proposed project must be located in the focal landscape or ecosystem selected on the basis of the procedure described in (2), above.  The CCPS may pre-select one or a small number of sectors from which proposals will be considered.  Selection of sectors will be based on the relative magnitude of vulnerability to climate change, as reflected in the NC and/or NAPA documents.

- Addressing the adaptive capacity or resilience of a community to climate change.  The CBA is expected to support projects which either increase the adaptive capacity of a community, or increase their resilience (including, for example, by increasing the resilience of the natural systems on which they depend) to climate change, including climate variability.

- Assessment of community vulnerabilities.  The proposed project must be based on the application of methodologies developed in (3), above, and must describe the characteristics of community vulnerability and options considered to address these vulnerabilities

- Cross-scale policy potential.  The proposed project must describe potential for replication, up-scaling, or integrating of the innovations to be supported, and must describe a process to support such processes (e.g. holding workshops to promote replication).

- Monitoring.  The proposed project must include a description of the monitoring baseline and activities to monitor indicators of vulnerability, based on the programmatic monitoring system below.

- Global environmental benefits.  The proposed project must demonstrate potential to respond to specific Operational Programme criteria under one of the GEF Focal Areas (e.g., climate change, biodiversity, land degradation, international waters). The proposal must produce global environmental benefits in a relevant GEF Focal Area, SP and OP, and these benefits must be made resilient to climate change including variability, as per the SPA guidelines.

- Others – country programs may wish to add additional priorities

42. In parallel with these country-specific actions, other PDF-B activities established an APF-guided methodology for the development of a Community-based Adaptation Strategy (CBAS) within each country (see annex 3, section 3, attachment 1).  A programme-wide M&E framework was also developed (see annex 2).

43. With the experience gained through the preparatory phase, the CBA programme will need to generate the following Outputs in each country in order to secure Outcome 1.

44. Output 1.1 A Country Programme Strategy.  In each country a Country Programme Strategy for improving adaptive capacity of ecosystems/communities will guide the design, implementation, and analysis of a portfolio of CBA projects.  The production of a Country Programme Strategy involves a number of activities.  Although the activities to be followed may vary from country to country, indicative activities leading to this Output include:

- Formation of a CBA National Coordinating Committee.  In the case of SGP countries, this consists of the SGP National Steering Committee, modified where necessary by the introduction of additional expertise in the field of adaptation to climate change including variability.

- Selection of a geographic region for implementation of CBA projects.  Based on the criteria described above, the CBA National Coordinating Committee will, through a consultative process, identify country-relevant criteria for the selection of a particular geographic region as the project site.  By application of the criteria to existing data, the geographic region will be selected.

- Formulation of a Country Programme Strategy document.  The CBA National Coordinating Committee will lead a process in which APF methodology for the development of a Community-based Adaptation Strategy (CBAS), and programme-wide M&E process are integrated with the formulation of national project screening criteria. This will form the basis of the national CBA strategy.

- Review of the Country Programme Strategy by UNDP.  In order to ensure that the CCPS conforms to the Objective of the CBA programme, the draft CCPS for each country will be reviewed by UNDP.

45. In countries which participated in the preparatory phase, some of these activities have already been completed. However, during implementation of the CBA, even these countries will need to revisit their CCPS and ensure conformity with guidelines provided with this project document.

46. Output 1.2 NGOs/CBOs capacity to design and support implementation of CBA projects is developed.  Specific NGOs and/or CBOs will be identified in each country that have a comparative advantage in terms of designing and supporting implementation of community-based adaptation-related activities.  Since it is unlikely that any of these organizations already have fully developed capacity to support the CBA (as dictated by the guidelines of the GEF SPA), a capacity building process will be undertaken to build adequate capacity.  Indicative activities leading to this Output include:

- Prepare and train NGOs/CBOs in the use of toolkits for designing and implementing SPA eligible adaptation to climate change, including variability, projects (preferably in local languages).

- Conduct thematic workshops on country relevant climate change impacts and adaptation issues.

- Proposal writing workshops for CBOs and NGOs at national level.

- Undertake visits for NGOs/CBOs to existing community-based projects, in countries where these exist, to learn form practical experiences of community-based project formulation and implementation.

47. Output 1.3: A portfolio of CBA projects.  Under the guidance provided by the Country Programme Strategy (Output 1.1), and supported by the NGOs/CBOs whose capacity has been built under Output 1.2, a portfolio of CBA projects will be implemented in each country.  Under this initial phase of the CBA, the total number of projects in each country will be limited (8-20).  Therefore, it is possible that a portfolio will be established in its entirety through a single call for proposals. Alternatively, it is advisable to undertake an initial call for proposals to establish a few projects, followed by a wider call once experience has been gained through the initial experiences.  A process for scoping and guidelines for the design of CBA projects is presented in annexes 2 and 3.

48. Indicative activities leading to this Output include:

- Advertise through popular media, NGO/ CBO magazines and NGO/CBO inventories for proposals.

- Preparation of CBA project concepts.

- Preliminary screening of concepts, consultation with proponents, as well as technical assistance with the guidelines developed in the context of the CBA programme (see annex 2).

- Review of concepts by the CBA National Coordinating Committee then award of planning grants to accepted concepts

- Approval of proposals and disbursement of funds.

- Monitoring of implementation of CBA projects (see below).

#### Outcome 2: National policies and programmes include community adaptation priorities to promote replication, up-scaling and integration of best practices derived from CBA projects

49. One of the criteria to be applied in selection of the geographic region wherein the CBA projects will be based is opportunities for integrating climate risks into national level policies on  rural development and/or ecosystem management and the sustainable use of natural resources. The purpose of this is to strengthen the potential for policy lessons derived from community-based adaptation to be replicated, scaled up, and/or integrated into country economic and social development programmes.

50. The importance of this process is widely recognized.  For example, guidance for the GEF from the UNFCCC CoP (Decision 6/CP.7) called for the GEF to:

“Establish pilot or demonstration projects to show how adaptation planning and assessment can be practically translated into projects that will provide real benefits, and may be integrated into national policy and sustainable development planning …”

51. This is also reflected in the GEF’s initial strategy to address adaptation (GEF/C.23/Inf.8/Rev.1), which notes that:

“… policy makers will need to take into account the potential adverse impacts of climate change in planning their development strategies within and across sectors. An important feature of national policy making will be the need to strengthen existing policies (and actions) which enhance a country’s ability to respond to its vulnerabilities to climate change, while seeking to cease policies and actions that may lead to ‘maladaptation’ to climate change.”

52. Consequently, this Outcome will promote replication, scaling up, and integrating of lessons learned through implementation of the initial portfolio of community-based adaptation projects within each country.  This will be a major function of the CBA National Coordinator, supported by the CBA National Coordinating Committee.

53. To achieve this Outcome, the following Outputs will be secured:

54. Output 2.1 Policy makers engaged in the CBA process.  Past experience from GEF projects and other similar interventions has demonstrated that policy makers tend not to respond to lessons presented after the fact, no matter how compelling.  Conversely, they are frequently highly responsive to lessons learned from processes in which they have been closely involved.  For this reason, the CCPS in each country will identify a process to engage key decision makers from relevant sectors, such as agriculture and rural development, actively in the CBA process. The UNFCCC focal point in particular will be consulted to determine relevant policy makers that must be included from early on in the design process.

55. The process to engage policy makers will necessarily be country-specific, but indicative activities under this Output may include:

- Preparation of country-specific briefing materials;

- Organization of workshops on adaptation to climate change including variability designed for policy makers and other senior decision-makers;

- Establishment of policy advisory councils, with membership from among policy makers and other senior decision-makers;

- Preparation of country-specific newsletters and other dissemination materials;

- Field visits to CBA project sites for policy makers and other senior decision-makers;

56. Output 2.2 Lessons from community-based adaptation-related activities compiled and disseminated. As lessons (positive and negative) concerning increasing the capacity of communities to adapt to climate change including variability emerge from the portfolio of CBA projects (Output 1.3), the CBA Country Coordinator will be responsible for compiling and disseminating them.  The target audiences will include both communities engaged in CBA projects and policy makers, and the mechanism for dissemination may differ for these two audiences.  This process will also feed into the international exchange of lessons that constitutes a component of Outcome 3, both of which will also link with the ALM.  Indicative activities under this Output may include:

- Documentation of progress in each CBA project;

- Preparation of one-page or longer briefing materials on lessons and best practices from specific projects;

- Preparation and delivery of presentations at national forums, especially those relevant to policy development in relevant sectors;

- Organization of regular meetings of the policy advisory councils; and

- Organization of workshops on lessons learnt.

#### Outcome 3: Cooperation among member countries promotes innovation in the design and implementation of adaptation to climate change including variability projects/policies.

57. The rationale for a CBA programme, rather than a series of independent country-specific CBA projects, is that cooperation and coordination across ecosystems and countries can provide added value in deriving policy solutions to global problems through action at the local level.

58. The CBA will therefore use the SGP mechanism to promote coordination and cooperation among the CBA programme countries.  The Central Programme Management Team will be primarily responsible for supporting activities and outputs leading to this Outcome.  The following Outputs will be required:

59. Output 3.1 CBA website.  An existing web-site such as UNDP-GEF’s Programming Adaptation will be developed and expanded to incorporate a site dedicated to dissemination of information on the CBA.  Indicative activities leading to this Output include:

- Web-site design

- Web-site preparation

- Web-site maintenance

60. Output 3.2 Global database of CBA projects.  Using the existing SGP global projects database as a platform and adding necessary new features, the CBA database will incorporate information from the project- and global-level M&E system, allowing progress towards portfolio-wide impacts to be tracked. This Output will link closely to the GEF’s Adaptation Learning Mechanism, which is designed to contribute to the integration of adaptation to climate change including variability within development planning of non-Annex I countries, and within the GEF’s portfolio as a whole.  Indicative activities leading to this Output include:

- Design of database structure, most likely based on a derivation of the existing SGP database, but with necessary modifications to reflect technical aspects of adaptation to climate change including variability and the information generated through the CBA M&E system;

- Data input, based on information from CBA member-countries;

- Database maintenance.

61. Output 3.3 Best practices and lessons learned exchanged among countries.  Using a variety of approaches, including regional, and possibly global, meetings and exchange visits, newsletters, the CBA web-site, and presentations at appropriate international forums, examples of best practices and lessons learned from CBA projects will be disseminated both to CBA participants and to a wider audience.  Indicative activities leading to this Output include:

- Documentation of examples of best practices and lessons learned, both electronically and in hard copy;

- Organization of regional meetings (and possibly a global meeting, if necessary cost benchmarks can be met);

- Exchange visits among countries for CBA Country Coordinators, policy makers and CBA participants;

- Preparation and delivery of presentations at international forums.

62. Output 3.4 Guidance documents for GEF and others on CBA programming and project support.  Analyses of experience with the pilot programme will be used as input to GEF and others regarding the effectiveness of the CBA modality in achieving sustained adaptive capacities to climate change at the community level.  Thus, the CBA will inform the development of further GEF policy on adaptation to climate change, provide lessons for medium-size and full-size projects, and also indicate the potential for future phases of the CBA itself.  Indicative activities leading to this Output include:

- Preparation of documentation for informing IAs, the GEF Secretariat and GEF Council on progress and results from the CBA

- Preparation of proposals for future directions for GEF support to adaptation relevant to all funding windows.

### Project Indicators, Risks and Assumptions

63. At the level of programme Objective, two indicators measure progress in terms of the dual foci of the SPA.  To measure progress in terms of adaptation to long-term climate change including variability, the indicator is:

“At any time after the completion of initial CBA projects, the average VRA value over all completed projects is at least 35%, and for no project is this value less than 10%.”

64. This indicator makes us of the Vulnerability Reduction Assessment (VRA), see annex 2, under which each individual CBA project assesses progress in terms of vulnerability reduction.  Individual project scores can be averaged to provide a country-level impact index, and well as a measure of overall impact at the programme level.

65. Global environmental benefits generated through the CBA will be measured using the same approach as used in the SGP, namely the Impact Assessment System (IAS).  The indicator is therefore:

“At least 75% of CBA projects shall have met all of their IAS targets by the conclusion of the programme.”

66. Indicators for each of the CBA’s three Outcomes are:

Outcome 1: By the end of the programme, at least two new strategies in each category of vulnerability have been introduced at the community level in each participating country.

Outcome 2: By the end of the programme, at least 8 national policies or programmes have been adopted, or existing policies and programmes adapted to take account of experiences generated through the CBA.

Outcome 3: By the end of the programme, there is at least one example in each country of a strategy or practice that was introduced on the basis of experiences gained in other countries.

67. More information on impact and performance indicators, risks and assumptions, including indicators at the programme Output level is provided in the Logical Framework Matrix, in Section II, below.

### Expected global, national and local benefits

68.  Under the baseline scenario (see Incremental Cost Analysis, Section 2 part 1), economic and social development objectives are achieved through baseline policies and programmes, but these are non-sustainable due to threats posed by future, long-term climate change including variability.  Under the alternative scenario, economic and social development objectives are achieved through projects that account for the need to adapt to future, long-term climate change including variability.  This will confer sustainability on progress made toward social and economic development.

69.  The CBA, under the SPA, is concerned with building resilience to climate change in the focal areas within which the GEF works, and is generally focused on ecosystem and natural resource management activities.  These ecosystems and natural resources are often relied upon by local communities for vital goods and services, and enhancements in their resilience to climate change will directly benefit these communities at the local level.  At the national level and the international level, the CBA programme will generate lessons on how to operationalize adaptation at the community level, ensuring benefits far beyond the “one-off” nature of individual community projects.

70.  Under the baseline scenario, globally important ecosystems and natural resources are lost to climate change including variability.  Under the alternative scenario, globally important ecosystems and natural resources will be made resilient to the effects of climate change including variability through community initiatives, first in the 80-200 community projects, and eventually through replication, upscaling and mainstreaming globally.

### Country Ownership: Country Eligibility and Country Drivenness

#### Country Eligibility

71. The CBA Programme is a global initiative. It will apply the SGP programming and delivery mechanism in a variety of countries. For the purposes of rapid learning and effective design of the FSP, the PDF-B phase of the project will pilot projects in four countries. The preliminary choice of countries for this phase includes Bangladesh (representing adaptation concerns of low-lying coastal communities), Bolivia (mountain communities), Niger (dryland communities) and Samoa (small island communities).

72. A key challenge of the CBA Programme is to design and foster frameworks for cross-scale decision-making and funding disbursal that will work in both with and without SGP infrastructures – i.e. which can use the SGP model, but do not require direct SGP support. Thus it is essential that the CBA be potentially open to all non-Annex I countries.

73. In both the PDF-B and full-sized project phases, adaptation activities will be carried out in selected countries, representing a range of ecological and socioeconomic conditions. During the PDF-B, the goal is to test the most effective programming and project models available for community based adaptation; for this reason, this phase will rely on the participation of countries where strong SGP Programmes exist, and will test carefully designed variations on the SGP mechanism.

74. Ultimately, the community-based projects that the CBA Programme will support will be selected based on a simple set of criteria (e.g. provision of global environmental benefits and responsiveness to local vulnerabilities), driven by existing GEF funding requirements, the priorities outlined in the GEF SPA, and country-driven priorities. Since there are a great number of local initiatives in every non-Annex I country that could potentially meet these criteria, this would suggest that any non-Annex I country will have at least the potential to participate in the CBA Programme in the FSP phase. On this basis, During the FSP design process, the Programme Team, with GEF Secretariat and non-Annex I country input, made a strategic selection of an additional 6 countries (Guatemala, Jamaica, Kazakhstan, Morocco, Namibia, and Vietnam, based on where the greatest opportunities lie for rapid lesson-learning as well as ensuring diversity in the expected CBA portfolio).

#### Country Drivenness

75. Country drivenness is a key principle behind the CBA initiative. The adaptation to climate change priorities of one country will differ from that of its neighbour. The CBA Programme aims to design, test and establish a conceptual and operational framework through which individual countries – and indeed, communities within countries – can drive the process of CBA Programme implementation at the local and national level in such a way that it responds directly to their needs.

76. Individual CBA Country Programme Strategies (CCPS) will guide CBA national programmes, and will be prepared through a participatory process, involving all relevant stakeholders in discussions.  In this cross-scale forum, ideas are exchanged and deliberated and therefore include relevant national and community development perspectives and priorities, including environmental priorities.  Country Programmes are encouraged to focus geographically and/or thematically to create synergies among projects, generate greater overall impacts and make impact assessment both practically and methodologically more straightforward.

77.  CCPS’s will focus the scope of the interventions on nationally important regions and sectors that are vulnerable to climate change as identified in the CP/GCF/RCF, as well as National Communications to the UNFCCC, and NAPAs.  Where applicable, CCPS’s will also link to appropriate UNDAF outcomes.  See the CCPS template and guidelines (annex 3, section 3, attachment 1) for more detail.

78.  As the focus of the CBA programme is on the development of adaptive capacity in the face of climate change including variability, and on the generation of lessons about how adaptation can be mainstreamed into development policy, CBA is uniquely suited to UNDP’s niche and mandate.

### Sustainability

79. For this project, sustainability must be considered in two main ways: on the one hand, sustainability of the institutions, processes and mechanisms established by the project must be assessed. On the other hand, the sustainability of the individual CBA projects supported by the project must be evaluated. On the side of individual CBA projects, sustainability will be built through formation of strong partnerships and co-financing arrangements with communities, NGOs, local authorities, governments, the private sector and other bilateral and multilateral development partners. Of crucial importance is partial funding from the beneficiaries themselves whether in-kind or in cash to consolidate community ownership of CBA projects. The 1:1 GEF requirement will be applied as part of project design and approval assessments. Development of design and implementation capacities of the beneficiary communities will be crucial for sustainability.

80. From the ‘project/policy laboratories’ started up by the CBA programme, important lessons on adaptation will be generated. The following programme elements encourage sustainability:

- Pursuit of the project objective will raise awareness on adaptation among community-based adaptation stakeholders at all scales, from the national to the local level.

- The project will be designed to encourage mainstreaming of community adaptation priorities in national adaptation strategies and, ultimately, development plans.

- Successful experiences will attract long-term policy and financial support for CBA activities from government, as well as donors, NGOs and other sources.

81. In terms of the institutions and mechanisms for the CBA Programme, sustainability will be assessed at the Programme, national and local community levels. These mechanisms will be designed with longer-term sustainability as a key target.

Global/intergovernmental:

- Frameworks and mechanisms put in place by the project are assured sustainability for the duration that they are needed, in part through growing country-level demand, voiced within the UNFCCC and other intergovernmental processes, for lessons on how to “do” effective community-based adaptation.

- Global advocacy and dissemination of good practices via various channels including UNV country-level activities.

National:

- Sustainability is enhanced by virtue of the CBA Programme’s reliance on the experienced management, project support and operations of existing SGP infrastructure and UNV programme.

- This approach will facilitate inter-linkage of the pilot community adaptation measures with other GEF and non-GEF national adaptation activities.

Local:

- New local capacity to engage with cross-scale decision-making processes and funding mechanisms will help to ensure long-term sustainability.

- Sense of ownership through voluntary involvement of local communities to insure sustainability after the completion of the project.

82. In terms of the individual, ground-level CBA projects, sustainability will be assured in a number of ways, including:

- opportunities for new CBA projects to integrate with ongoing community-based sustainable development activities,

- the bottom-up approach taken to CBA project development, which helps to ensure local project acceptance, support and long-term sustainability, and

- the local community investment made in the project in the form of time, labour, local resources, cash, etc.

- Participatory planning and inclusion of all stakeholders including vulnerable groups (women, youth, minorities and IDPs), as well as formal and informal social groups (resource use groups, self-help groups, CBOs and cooperatives).

### Replicability

83. Replicability will be achieved at the global level (e.g. through the provision of key lessons for CBA mainstreaming), the national (e.g. through the development of national capacity to support CBA) and the local level (e.g. where new know-how among local NGOs and CBOs can encourage a scaling out of CBA activities).

84.  Lesson learning and knowledge management has been incorporated into the programme design at the global, national and local levels.  At the local level, community project proponents will be required to submit information on progress toward adaptive capacity objectives, and on the processes behind that progress, both as a consequence of monitoring and evaluation activities (Annex 2) and in the form of final project reports (Annex 3, section 3, attachment 7).  At the national level, reports, seminars and policy briefs will be generated, and lessons generated at the country programme level will be spread globally through outcome 3 of the CBA programme.

85. To lay the foundation for the use of the SGP mechanism for the CBA programme, a programme-wide capacity development effort will be initiated at the global level, the country Programme level and the local level.

86. UNDP will develop a model for community-based adaptation that is widely applicable and readily taken up by participants at the global, national or local scales. The SGP mechanism will allow fast-tracking of community projects, making it easy for adaptive management and replication.

87. Finally, though it is beyond the scope of the CBA Programme, replication of CBA activities will ideally occur over the long term through the implementation of new and emerging adaptation funds.

## PART III: MANAGEMENT ARRANGEMENTS

88. As the CBA uses GEF SGP mechanisms for the implementation of project activities, the contracting, funding disbursal, and management of accounts for this project will also be undertaken through mechanisms already established for the GEF SGP.  In countries where GEF SGP mechanisms are absent (Bangladesh), these activities will be undertaken through the UNDP country office.

89. During the PDF-B phase of project preparation, frameworks were established in four countries (Bolivia, Niger, Samoa and Bangladesh) to pilot and demonstrate management arrangements for the CBA.  In practice, the frameworks developed in each country were very similar to one another, composed of a constituted National CBA Coordination Committee under the auspices of the national adaptation focal point. Where there is no existing SGP mechanism (Bangladesh), the national adaptation focal point will serve as the NC and coordinate overall project activities while the proposal development and approval process will be supported by the national CBA coordinating committee. The committee will be responsible for supporting the portfolio of community-based adaptation-related activities. As needed, UNDP country offices will provide support for the set up of these institutions in countries where the SGP mechanism is absent.

90. The National Coordinator will conduct outreach to selected CBOs, volunteer-involving organisations (VIOs) and NGOs to engage them in capacity building activities. Following a set of training workshops, these local groups will then work with communities to develop local vulnerability assessments and CBA proposals. To the extent possible, these training activities will be coordinated with ongoing meetings and capacity building efforts. Linkages will be made with national adaptation activities carried out by GEF Implementing Agencies in the selected countries.

91. The funding for CBA projects will be based on the principle of equitable access and will depend significantly on the strength of Country Programme strategies and project ideas. Criteria such as innovativeness, whether or not a project idea is catalytic of additional funding, strategic importance, fit with national priorities, comparative advantage of the CBA project proponent and CBA portfolio balance will be applied. Funds will be channelled existing SGP mechanisms, and through the UNDP country office where that mechanism is absent.

92. Funds will also be allocated for Programme-wide outcomes such as lesson learning, monitoring and evaluation, and documentation of experiences at the end of the FSP.

93. In order to accord proper acknowledgement to GEF for providing funding, a GEF logo should appear on all relevant GEF project publications, including among others, project hardware and vehicles purchased with GEF funds. Any citation on publications regarding projects funded by GEF should also accord proper acknowledgment to GEF. The UNDP logo should be more prominent -- and separated from the GEF logo if possible, as UN visibility is important for security purposes.

## PART IV: MONITORING AND EVALUATION PLAN AND BUDGET

94. The monitoring programme for the CBA is based on approaches recommended by UNDP-GEF’s Adaptation Policy Framework (APF).  To monitor progress in building capacity for adaptation, the monitoring programme will adopt the “Vulnerability Reduction Assessment”, a modification of the Threat Reduction Assessment (TRA) approach, first developed for the USAID-funded “Biodiversity Support Programme,” and drawing heavily on several stakeholder methodologies from the UNFCCC Compendium of Decision Tools to Evaluate Strategies for Adaptation to Climate Change. Like the TRA, the VRA (described in annex 2) emphasizes monitoring based on qualitative assessment using simple techniques that are easily interpreted. M&E is strongly related to specific project interventions, using such combinations of qualitative information and quantitative indicators. Indicators to assess project impacts in terms of global environmental benefits are based on those from the SGP.

95. Programme monitoring and evaluation will be conducted in accordance with established UNDP and GEF procedures, which will involve (a) the NGOs/CBOs involved in implementing projects (to be overseen by the NC in each country); (b) the UNDP Country Office (UNDP-CO) for country-level monitoring, and (c) UNDP, through CDAC, in collaboration with SGP at the programme level.  The Logical Framework Matrix provides performance and impact indicators for programme implementation along with their corresponding means of verification. These will form the basis on which the programme's Monitoring and Evaluation system will be built.

96. The following sections outline the principle components of the Monitoring and Evaluation Plan and indicative cost estimates related to M&E activities. The programme's Monitoring and Evaluation Plan will be presented and finalized at the Programme's Inception Report following a collective fine-tuning of indicators, means of verification, and the full definition of programme staff M&E responsibilities.

### Monitoring and Reporting

#### Programme Inception Phase

97. A Programme Inception Workshop will be conducted with NCs from each participating country, relevant government counterparts, co-financing partners, the UNDP-COs and UNDP, through CDAC, in collaboration with SGP.

98. A fundamental objective of this Inception Workshop will be to assist the entire programme team (including UNDP, SGP, and the National Coordinators) to understand and take ownership of the programme’s goal, objective and outcomes, as well as finalize preparation of the programme's first annual work plan on the basis of the logframe matrix. This will include reviewing the logframe (indicators, means of verification, assumptions), imparting additional detail as needed, and on the basis of this exercise finalize the Annual Work Plan (AWP) with precise and measurable performance indicators, and in a manner consistent with the expected outcomes for the programme.

99. Additionally, another purpose of the Inception Workshop will be to provide a detailed overview of UNDP-GEF reporting and monitoring and evaluation (M&E) requirements, with particular emphasis on the Annual Project Implementation Reviews (PIRs) and related documentation, the Annual Project Report (APR), Tripartite Review Meetings, as well as mid-term and final evaluations. Equally, the IW will provide an opportunity to inform the programme team on UNDP programme related budgetary planning, budget reviews, and mandatory budget rephrasing.

100. The Inception Workshop will also provide an opportunity for all parties to understand their roles, functions, and responsibilities within the programme's decision-making structures, including reporting and communication lines, and conflict resolution mechanisms. The Terms of Reference for programme staff and decision-making structures will be discussed again as needed, in order to clarify for all, each party’s responsibilities during the programme's implementation phase.

#### Monitoring responsibilities and events

101. A detailed schedule of programme review meetings will be developed by the programme management, in consultation with programme implementation partners and stakeholder representatives and incorporated in the Programme Inception Report. Such a schedule will include: (i) tentative time frames for Tripartite Reviews, Steering Committee Meetings, (or relevant advisory and/or coordination mechanisms) and (ii) programme related Monitoring and Evaluation activities.

102. Day to day monitoring of implementation progress will be the responsibility of the National Coordinators based on the programme's Annual Work Plan and its indicators. The National Coordinators will inform the UNDP-CO and UNDP of any delays or difficulties faced during implementation so that the appropriate support or corrective measures can be adopted in a timely and remedial fashion.

103. The National Coordinators and UNDP will fine-tune the progress and performance/impact indicators of the programme in consultation with the full programme team at the Inception Workshop. Specific targets for the first year implementation progress indicators together with their means of verification will be developed at this Workshop. These will be used to assess whether implementation is proceeding at the intended pace and in the right direction and will form part of the Annual Work Plan. The local implementing partners will also take part in the Inception Workshop in which a common vision of overall programme goal will be established. Targets and indicators for subsequent years will be defined annually as part of the internal evaluation and planning processes undertaken by UNDP.

104. Measurement of impact indicators related to global benefits will occur according to the schedules defined in the Inception Workshop. The measurement of these will be undertaken through subcontracts or retainers with relevant institutions where necessary to be determined during the inception workshop or through specific studies that are to form part of the programmes activities or periodic sampling.

105. Periodic monitoring of implementation progress within each country will be undertaken by the UNDP-CO through quarterly meetings with the National Coordinators, or more frequently as deemed necessary. This will allow parties to take stock and to troubleshoot any problems pertaining to the programme in a timely fashion to ensure smooth implementation of programme activities.

106. UNDP Country Offices and UNDP (through CDAC, in collaboration with SGP), as appropriate, will conduct yearly visits to field sites, or more often based on an agreed upon schedule to be detailed in the programme's Inception Report / Annual Work Plan to assess first hand programme progress. Any other member of the National Coordinating Committee can also accompany, as decided by the NCC. A Field Visit Report will be prepared by the CO and circulated no less than one month after the visit and circulated to UNDP, and all NCC members.

107. Annual Monitoring will occur through the Tripartite Review (TPR). This is the highest policy-level meeting of the parties directly involved in the implementation of the programme. The programme will be subject to Tripartite Review (TPR) at least once every year. The first such meeting will be held within the first twelve months of the start of full implementation. The National Coordinators will prepare reports that will be compiled into Annual Project Report (APR) by UNDP at least two weeks prior to the TPR for review and comments.

108. The APR will be used as one of the basic documents for discussions in the TPR meeting. The UNDP will present the APR to the TPR, highlighting policy issues and recommendations for the decision of the TPR participants.  UNDP also informs the participants of any agreement reached by stakeholders during the APR preparation on how to resolve operational issues. Separate reviews of each programme component may also be conducted if necessary.

#### Terminal Tripartite Review (TTR)

109. The terminal tripartite review is held in the last month of programme operations. UNDP (through CDAC, in collaboration with SGP) is responsible for preparing the Terminal Report and submitting it to UNDP and the GEF Secretariat. It shall be prepared in draft at least two months in advance of the TTR in order to allow review, and will serve as the basis for discussions in the TTR. The terminal tripartite review considers the implementation of the programme as a whole, paying particular attention to whether the programme has achieved its stated objective and contributed to the broader environmental objective. It decides whether any actions are still necessary, particularly in relation to sustainability of programme results, and acts as a vehicle through which lessons learnt can be captured to feed into other projects under implementation of formulation.

110. The TPR has the authority to suspend disbursement if programme performance benchmarks are not met. Benchmarks will be developed at the Inception Workshop, based on delivery rates, and qualitative assessments of achievements of outputs.

#### Programme Monitoring Reporting

111. The National Coordinators in conjunction with UNDP will be responsible for the preparation and submission of the following reports that form part of the monitoring process.

#### (a)	Inception Report (IR)

112. A Programme Inception Report will be prepared immediately following the Inception Workshop. It will include a detailed First Year/ Annual Work Plan divided in quarterly time-frames detailing the activities and progress indicators that will guide implementation during the first year of the programme. This Work Plan would include the dates of specific field visits, support missions from the UNDP-CO, UNDP or consultants, as well as time-frames for meetings of the programme's decision making structures.  The Report will also include the detailed programme budget for the first full year of implementation, prepared on the basis of the Annual Work Plan, and including any monitoring and evaluation requirements to effectively measure programme performance during the targeted 12 months time-frame.

113. The Inception Report will include a more detailed narrative on the institutional roles, responsibilities, coordinating actions and feedback mechanisms of programme related partners.  In addition, a section will be included on progress to date on programme establishment and start-up activities and an update of any changed external conditions that may effect programme implementation.

114. When finalized, the report will be circulated to programme counterparts who will be given a period of one calendar month in which to respond with comments or queries.

#### (b) 	Annual Project Report (APR)

115. The APR is a UNDP requirement. It is a self -assessment report by programme management to UNDP and provides input to the Tripartite Project Review.  An APR will be prepared on an annual basis prior to the Tripartite Project Review, to reflect progress achieved in meeting the programme's Annual Work Plan and assess performance of the programme in contributing to intended outcomes through outputs and partnership work.

116. The format of the APR is flexible but should include the following:

- An analysis of programme performance over the reporting period, including outputs produced and, where possible, information on the status of the outcome

- The constraints experienced in the progress towards results and the reasons for these

- The three (at most) major constraints to achievement of results

- AWP, CAE and other expenditure reports (ERP generated)

- Lessons learned

- Clear recommendations for future orientation in addressing key problems in lack of progress

#### (c) 	Project Implementation Review (PIR)

117. The PIR is an annual monitoring process mandated by the GEF. It has become an essential management and monitoring tool for programme managers and offers the main vehicle for extracting lessons from ongoing projects. Once the programme has been under implementation for a year, a Project Implementation Report must be completed by UNDP, in cooperation with National Coordinators. The PIR can be prepared any time during the year (July-June) and ideally prior to the TPR.  The PIR should then be discussed in the TPR so that the result would be a PIR that has been agreed upon by all partners.

#### (d)	Quarterly Progress Reports

118. Short reports outlining main updates in programme progress will be provided quarterly to the local UNDP Country Office and UNDP (through CDAC, in collaboration with SGP) by National Coordinators.

#### (e)	Periodic Thematic Reports

119. As and when called for by UNDP or the GEF Secretariat, country programme teams will prepare Specific Thematic Reports, focusing on specific issues or areas of activity.  The request for a Thematic Report will be provided to the country programme team in written form by UNDP and will clearly state the issue or activities that need to be reported on.  These reports can be used as a form of lessons learnt exercise, specific oversight in key areas, or as troubleshooting exercises to evaluate and overcome obstacles and difficulties encountered.  UNDP is requested to minimize its requests for Thematic Reports, and when such are necessary will allow reasonable timeframes for their preparation by the country programme team.

#### (f)	Project Terminal Report

120. During the last three months of the programme UNDP (through CDAC, in collaboration with SGP) will prepare the Project Terminal Report.  This comprehensive report will summarize all activities, achievements and outputs of the Programme, lessons learnt, objectives met or not achieved, structures and systems implemented, etc. and will be the definitive statement of the programme’s activities during its lifetime.  It will also lay out recommendations for any further steps that may need to be taken to ensure sustainability and replicability of the programme’s activities.

### Independent Evaluation

121. The programme will be subjected to at least two independent external evaluations as follows:

#### (i) 	Mid-term Evaluation

122. An independent Mid-Term Evaluation will be undertaken at the end of the second year of implementation. The Mid-Term Evaluation will determine progress being made towards the achievement of outcomes and will identify course correction if needed. It will focus on the effectiveness, efficiency and timeliness of programme implementation; will highlight issues requiring decisions and actions; and will present initial lessons learned about programme design, implementation and management. Findings of this review will be incorporated as recommendations for enhanced implementation during the final half of the programme’s term.  The organization, terms of reference and timing of the mid-term evaluation will be decided after consultation between the parties to the project document. The Terms of Reference for this Mid-term evaluation will be prepared by UNDP based on guidance from UNDP’s Office of Evaluation.

#### (ii)	Final Evaluation

123. An independent Final Evaluation will take place three months prior to the terminal tripartite review meeting, and will focus on the same issues as the mid-term evaluation.  The final evaluation will also look at impact and sustainability of results, including the contribution to capacity development and the achievement of global environmental goals.  The Final Evaluation should also provide recommendations for follow-up activities. The Terms of Reference for this evaluation will be prepared by the UNDP based on guidance from UNDP’s Office of Evaluation.

### Learning and Knowledge Sharing

124. Results from the programme will be disseminated within and beyond the programme intervention zone through a number of existing information sharing networks, in particular, the ALM.

125. Learning is an important goal of this GEF pilot phase on adaptation. Each adaptation project should incorporate a significant learning component in its project design, using monitoring and evaluation good practices. Rigorous evaluation will enable the GEF and other agencies to measure progress and the GEF to learn how to strengthen and widen its portfolio. The UNDP-GEF's ALM has been launched to facilitate this learning process.

126. The Adaptation Learning Mechanism (ALM) will help maximize global learning from GEF-managed funds for adaptation, including the Strategic Priority on Adaptation (SPA). It will contribute to incorporating adaptation into planning and provide good practices for adaptation. Developed as a new “knowledge base”, the ALM will provide tools and establish a learning platform for integrating adaptation into development and build partnerships and capacity. It will be designed as a collaborative, open-source knowledge network with regional partner institutions in the lead.

127.  In the context of the CBA, community project proponents will generate several sets of completed H-forms, as well as interim and final reporting.  All projects will be documented on the CBA database, final project reports (see annex 3, section 3, attachment 7) will be fed into the ALM knowledge base of project information, and case studies for particularly successful projects, written as part of outcome 3, will be facilitated by the availability of these documents.  Saving the H-forms will be the responsibility of the CBA country programme.

128. The programme will systematically identify, analyze, and share lessons learned that will be beneficial in the design and implementation of similar future projects. Identifying and analyzing lessons learned is an on-going process, and the need to communicate such lessons as one of the programme's central contributions is a requirement to be delivered not less frequently than once every 12 months. UNDP shall provide a template for assessing and reporting lessons learned and assist the country programme team in categorizing, documenting and reporting on lessons learned through experience. To this end a percentage of programme resources will need to be allocated for these activities.

Indicative Monitoring and Evaluation Work plan and corresponding Budget

(Please see annex 2 for a more detailed description of the CBA M&E framework)

| Type of M&E activity | Responsible Parties | Budget US$ | Time frame |
| --- | --- | --- | --- |
| Inception Workshop | UNDP-GEF CDAC National Coordinators from CBA countries GEF-SGP | 80,000 | Within first two months of project start up |
| Inception Report | UNDP-GEF CDAC, in collaboration with SGP and the CBA National coordinators | None | Immediately following IW |
| Measurement of Community Project Indicators (Outcome 1) | Grantees of CBA community projects (see annex 2 for more detail), in collaboration with CBA National Coordinators | To be finalized in Inception Phase and Workshop. Indicative cost 50,000 | Throughout project, as determined by the M&E cycles of individual community projects. See annex 3 for more detail. |
| Measurement of country-level and global level indicators (related to outcomes 2 and 3) | Oversight by UNDP-GEF (through CDAC, in collaboration with SGP) at the global level CBA National Coordinators at the country level | To be determined as part of the Annual Work Plan's preparation. Indicative cost 30,000 | Annually prior to APR/PIR and to the definition of annual work plans |
| APR and PIR | UNDP-GEF CDAC, in collaboration with GEF-SGP | None | Annually |
| TPR and TPR report | Government Counterparts UNDP CO’s UNDP-GEF (through CDAC, in collaboration with SGP) | None | Every year, upon receipt of APR |
| Steering Committee Meetings | UNDP-GEF (through CDAC, in collaboration with SGP) UNDP CO | None | Following Project IW and subsequently at least once a year |
| Periodic status reports | UNDP-GEF (through CDAC, in collaboration with SGP) | 5,000 | To be determined by UNDP-GEF (CDAC) in collaboration with GEF-SGP and the CBA National Coordinators |
| Technical reports | UNDP-GEF (through CDAC, in collaboration with SGP) | 15,000 | To be determined by UNDP-GEF (through CDAC, in collaboration with SGP) |
| Mid-term External Evaluation | UNDP-GEF (through CDAC, in collaboration with SGP) External Consultants (i.e. evaluation team) | 10,000 | At the mid-point of project implementation. |
| Final External Evaluation | UNDP-GEF (through CDAC, in collaboration with SGP) External Consultants (i.e. evaluation team) | 24,000 | At the end of project implementation |
| Terminal Report | UNDP-GEF (through CDAC, in collaboration with SGP) | None | At least one month before the end of the project |
| Lessons learned | UNDP-GEF (through CDAC, in collaboration with SGP) at the global level National coordinators, (with assistance from national coordinating committees) at the country level | 15,000 (average 3,000 per year) | Yearly |
| Audit | UNDP-GEF (through CDAC, in collaboration with SGP) CBA country programmes | 4,000 (average $1000 per year) | Yearly |
| Visits to field sites (UNDP staff travel costs to be charged to IA fees) | UNDP Country Office UNDP-GEF Regional Coordinating Unit (as appropriate) Government representatives | 15,000 (average one visit per year) | Yearly |
| TOTAL indicative COST | US$ 218,000 |  |

## PART V: Legal Context

129. The UNDP in New York is authorized to effect in writing the following types of revisions to this Project Document, provided that he/she has verified the agreement thereto by the UNDP and is assured that the other signatories to the Project Document have no objection to the proposed changes:

- Revision of, or addition to, any of the annexes to the Project Document;

- Revisions which do not involve significant changes in the immediate objectives, outputs or activities of the project, but are caused by the rearrangement of the inputs already agreed to or by cost increases due to inflation;

- Mandatory annual revisions which re-phase the delivery of agreed project inputs or increased expert or other costs due to inflation or take into account agency expenditure flexibility; and

- Inclusion of additional annexes and attachments only as set out here in this Project Document

# Section II: Strategic Results Framework and GEF Increment

## PART I: INCREMENTAL COST ANALYSIS

| Cost/Benefit | Baseline (B) | Alternative (A) | Increment (A-B) |
| --- | --- | --- | --- |
| Domestic Benefits | Economic and social development objectives are achieved through baseline policies and programmes, but these are non-sustainable due to the threats posed by future, long-term climate change including variability | Economic and social development objectives are achieved through modified policies and programmes that account for the need to adapt to future, long-term climate change including variability, and which are therefore sustainable |  |
| Global Benefits | Communities with low adaptive capacity tend to consume resources to deal with current climate uncertainties in ways that are non-sustainable under conditions of long-term climate change including variability, thus resulting in loss of globally significant biodiversity, loss of soil and productive capacity, emission of greenhouse gases, mismanagement of transboundary water systems, and mismanagement of POPs and products which generate POPs | Communities with high adaptive capacity tend to consume resources in ways that are sustainable under conditions of long-term climate change including variability, thus resulting in conservation of globally significant biodiversity, soil and productive capacity, reduced emissions of greenhouse gases, and improved management of transboundary water systems, POPs, and products which generate POPs |  |
| Costs Outcome 1: Enhanced adaptive capacity allows communities to reduce their vulnerability to adverse impacts of future climate hazards | $15,000,000 (approximately $1,500,000 invested per country, on average, in the selected priority areas and sectors in non-sustainable economic development that does not account for the impacts of long-term climate change including variability) | $20,158,660 | $5,158,660, of which: GEF: $2,579,330 Co-financing (cash and in-kind): $2,579,330 |
| Outcome 2: National policies and programmes promote replication of best practices derived from CBA projects | $1,000,000 (approximately $100,000 per country, on average) | $2,810,056 | $1,810,056, of which: GEF: $905,028 Co-financing (cash and in-kind): $905,028 |
| Outcome 3: Cooperation among member countries promotes innovation in adaptation to climate change including variability | $0 | $2,081,564 (includes programme management and M&E costs) | $2,081,564, of which: GEF: $1,040,782 Co-financing (cash and in-kind): $1,040,782 |
| Cost Totals | $16,000,000 | $35,050,280 | $9,050,280, of which: GEF: $4,525,140 Co-financing (cash and in-kind): $4,525,140 |

## PART II: LOGICAL FRAMEWORK ANALYSIS

| Project Strategy | Objectively verifiable indicators |
| --- | --- |
| Goal | To reduce vulnerability and to increase adaptive capacity to the adverse effects of climate change in the focal areas in which the GEF works |
|  | Indicator | Baseline | Target | Sources of verification | Risks and Assumptions |
| Objective of the project: To enhance the capacity of communities in the pilot countries to adapt to climate change including variability | Reduction to vulnerability to climate change including variability Magnitude of global environmental benefits secured (using the SGP’s IAS) | Each individual CBA project will undertake a quantitative assessment of its vulnerability (based on the VRA approach). The programme baseline is the average of individual project values Projects will apply the SGP IAS methodology in defining focal area-specific indicators of GEBs and measuring baseline values | At any time after the completion of initial CBA projects, the average VRA value over all completed projects is at least 35%, and for no project is this value less than 10% At any time after the completion of initial CBA projects, 75% of projects will have met or surpassed their IAS targets. | Individual project reports of participatory VRA assessments, compiled at country and global levels Individual project reports of IAS assessments, compiled at country and global levels | Communities are able to identify factors that contribute to their vulnerability to climate change including variability and can rank these objectively. Priority adaptation interventions can be identified that also contribute to securing global environmental benefits |
| Outcome 1: Enhanced adaptive capacity allows communities to reduce their vulnerability to adverse impacts of future climate hazards | Number of strategies adopted to address drought and other categories of vulnerability | No strategies adopted other than pre-existing strategies | By the end of the programme, at least two new strategies in each category of vulnerability have been introduced at the community level in each participating country | Project reports, NC reports | In developing and implementing CBA project proposals, innovative solutions to increase adaptive capacity are generated |
| Output 1.1: A Country Programme Strategy. | Approval of CPS documents | No CPS documents | Within 4 months of the start of implementation, all 10 countries have an approved CPS | NC reports, and submissions of CPS documents to UNDP | Expressed government commitment translates into early and prompt action to develop CBA CPS documents |
| Output 1.2 NGOs/CBOs with capacity to design and support implementation of CBA projects. | Number of CBA concepts submitted | No CBA concepts | Within 8 months of the start of implementation, at least 30 CBA concepts have been received by the NC in each country | NC reports, and copies of concepts forwarded to UNDP | NGO/CBO capacity building is effective in allowing communities to develop concepts for CBA funding |
| Output 1.3 A portfolio of CBA projects. | Number of approved CBA projects | No approved CBA projects | Within 11 months of the start of implementation, at least 3 projects have been approved in each country | NC reports, and copies of approved proposals forwarded to UNDP | The NSC remains committed and active |
| Outcome 2: National policies and programmes promote replication of best practices derived from CBA projects | Number of policies and programmes adopted or adapted on the basis of CBA experiences | National policies and programmes rarely account for community based adaptation strategies | By the end of the programme, at least 8 national policies or programmes have been adopted, or existing policies and programmes adapted to take account of experiences generated through the CBA | NC reports, supported by surveys of policy makers in each country | Policy makers are effectively engaged in the CBA process and CBA projects generate policy-relevant experiences |
| Output 2.1 Policy makers engaged in the CBA process. | Number of policy makers engaged in the CBA | No CBA process initiated | Within 12 months of the start of CBA implementation in each country, at least one senior policy maker (at the level of Director General or above) in each of the identified sectors for CBA implementation is engaged in the CBA process through participation in the NCC or equivalent body. | NCC reports | Selection of policy maker to be engaged maximizes potential for lessons to be integrated into national policies and programmes |
| Output 2.2 Lessons from community-based adaptation-related activities compiled and disseminated | Number of lessons compiled and disseminated | No lessons generated | Within 12 months of the start of CBA implementation in each country, at least one lesson generated by CBA projects has been described and disseminated to national level stakeholders. By the end of the programme, this number is at least five in each country | NC reports | Engagement of senior policy makers increases the likelihood of lessons being adopted in non-CBA locations within each country |
| Outcome 3: Cooperation among member countries promotes innovation in adaptation to climate change including variability | Adoption or adaptation of practices piloted through the CBA | No cross-border learning | By the end of the programme, there is at least one example in each country of a strategy or practice that was introduced on the basis of experiences gained in other countries | Survey of NCs and CBA project teams | Projects are under implementation long enough for lessons to be transferred to other countries before the end of the programme |
| Output 3.1 CBA web-site | Existence of CBA web-site Value of web-site | No web-site No web site | Within 1 month of the start of implementation, a public programme web-site has been created At the end of the programme, a survey of stakeholders in each country reveals that at last 60% used the CBA web-site regularly to learn about progress in the CBA | Project reports Survey of stakeholders as part of the final evaluation |  |
| Output 3.2 Global database of CBA projects. | Existence of CBA global database Value of CBA global database | No database No database | Within 11 months of the start of implementation, a public global database of CBA projects has been created At the end of the programme, a survey of stakeholders in each country reveals that at last 60% referred to the global CBA database regularly | Project reports Survey of stakeholders as part of the final evaluation |  |
| Output 3.3 Best practices and lessons learned exchanged among countries. | Number of cases included in the ALM | No cases of best practice recorded | At the time of programme completion, at least 3 examples of best practice generated through the CBA are accessible through the ALM (12 months after programme completion, this figure is at least 10) | Programme reports, ALM reports | ALM becomes operational and effective in time to document best practices from the CBA |
| Output 3.4 Guidance documents for GEF and others on CBA programming and project support. | Documented CBA experiences guide future GEF interventions on adaptation to climate change including variability | Initial GEF guidance developed without benefits of community experience in adaptation to climate change including variability | At the time of programme completion, discussions have been initiated with the GEF Secretariat to ensure that experiences from the CBA guide future GEF interventions on adaptation to climate change including variability | Programme reports, interviews with GEF Secretariat personnel | GEF continues to target adaptation to climate change including variability |

# SECTION III: Total Budget and Workplan

| Award ID: 00046129 |
| --- |
| Award Title: PIMS 3508: CC/SPA/FSP: Community-Based Adaptation Programme (CBA) |
| Business Unit: UNDP1 |
| Project ID: 00054763 |
| Project Title: PIMS 3508: CC/SPA/FSP: Community-Based Adaptation Programme (CBA) |
| Implementing Partner: UNOPS |
| GEF Outcome/Atlas Activity | Responsible Party (Implementing Agent) | Fund ID | Donor Name | Atlas Budgetary Account Code | ATLAS Budget Description | Amount (USD) Year 1 (2007) | Amount (USD) Year 2 (2008) | Amount (USD) Year 3 (2009) | Amount (USD) Year 4 (2010) | Amount (USD) Year 5 (2011) | Total (USD) | See Budget Note: |
| OUTCOME 1: Enhanced adaptive capacity allows communities to reduce their vulnerability to adverse impacts of future climate hazards |  |  |  | 72600 | Grants | $750,000 | $750,000 | $750,000 | $750,000 | $750,000 | $3,750,000 | 1 |
|  |  |  |  |  | Total Outcome 1 | $750,000 | $750,000 | $750,000 | $750,000 | $750,000 | $3,750,000 |  |
| OUTCOME 2: National policies and programmes promote replication of best practices derived from CBA projects | UNDP | 62000 | GEF | 72100 | International Consultants | $20,625 | $20,625 | $20,625 | $20,625 | $20,625 | $103,125 | 2 |
|  |  |  |  | 63400 | Learning Costs | $47,285 | $0 | $0 | $0 | $0 | $47,285 | 3 |
|  |  |  |  | 71300 | Local Consultants | $47,125 | $0 | $0 | $0 | $0 | $47,125 | 4 |
|  |  |  |  | 74500 | Miscellaneous Expenses | $27,465 | $0 | $0 | $0 | $0 | $27,465 | 5 |
|  |  |  |  |  | Total Outcome 2 | $142,500 | $20,625 | $20,625 | $20,625 | $20,625 | $225,000 |  |
| OUTCOME 3: Cooperation among member countries promotes innovation in adaptation to climate change including variability | UNDP | 62000 | GEF | 72100 | International Consultants | $13,750 | $13,750 | $13,750 | $13,750 | $13,750 | $68,750 | 6 |
|  |  |  |  | 63400 | Learning Costs | $47,285 | $0 | $0 | $0 | $15,105 | $62,390 | 7 |
|  |  |  |  |  | Total Outcome 3 | $61,035 | $13,750 | $13,750 | $13,750 | $28,855 | $131,140 |  |
| OUTCOME 4: Monitoring, learning, adaptive feedback and evaluation | UNDP | 62000 | GEF | 72100 | Contractual Services -- Companies | $1,000 | $250 | $250 | $250 | $250 | $2,000 | 8 |
|  |  |  |  | 71200 | International Consultants | $9,625 | $29,625 | $9,625 | $9,625 | $39,625 | $98,125 | 9 |
|  |  |  |  | 63400 | Learning Costs | $46,840 | $45,000 | $45,000 | $45,000 | $50,035 | $231,875 | 10 |
|  |  |  |  | 71600 | Travel | $6,400 | $6,400 | $6,400 | $6,400 | $6,400 | $32,000 | 11 |
|  |  |  |  |  | Total Outcome 4 | $63,865 | $81,275 | $61,275 | $61,275 | $96,310 | $364,000 |  |
| Project Management Unit | UNDP | 6200 | GEF | 71200 | International Consultants | $11,000 | $11,000 | $11,000 | $11,000 | $11,000 | $55,000 | 12 |
|  |  |  |  |  | Total Management | $11,000 | $11,000 | $11,000 | $11,000 | $11,000 | $55,000 |  |
| PROJECT TOTAL | $918,250 | $815,625 | $795,625 | $795,625 | $845,765 | $4,525,140 |  |

Budget Notes:

1.  Grants refer to funds that will be disbursed to CBOs/NGOs for designing and implementing CBA projects.  As per approved responses to council comments, 86% of the total funds will be used for the implementation of CBA projects in the ten countries.  The amount on this budget line corresponds to approximately 83% of the total project funds, before execution costs (78% after execution costs).  The remaining implementation costs are found in the budget lines that correspond to budget notes 2, 3, 4, 5, 6, and 9.

2.  This covers the cost of 2 international consultant with expertise on designing climate change adaptation projects (at the rate of $300/day for 150-170 days over 4 years) who will provide technical support to between 8-20 NGOs in each of the 10 countries in designing CBA projects that meet SPA criteria.  The amount covers the cost of effectively 7.5-8.5 days of support per country (by each consultant) involved in the CBA for providing guidance on proposal development.  TORs for the International consultants are attached (Section IV, part II, TOR E, task 2).  This item corresponds to approx 2% of total costs.

3.  This covers part of the cost of the inception workshop, a necessary first activity once the project is endorsed. The cost will include coverage of travel and DSA for the SGP National Coordinators who will be trained on the operational requirements of the CBA programme. As the SGP NCs will be largely responsible for oversight, it is essential that this activity is funded.  This item corresponds to approx 1% of total costs.

4.  This covers the cost of developing CBA country programme strategies in each of the ten pilot countries.  This will cover the cost of setting in place the mechanisms for capturing lessons from CBA projects.  Costs associated with the collection and processing of baseline information and adaptation benefits will be covered.  It is envisaged that a local consultant with expertise on climate change adaptation in each of the 10 countries (at the rate of $200 per day for approximately 15 days) will be necessary to for this task.  TORs for the local consultants are attached (Section IV, part II, TOR G).  This item corresponds to approx 1% of total costs.

5.  This covers the cost of capacity building activities for potential NGO/CBO grantees in each of the ten pilot countries.  Capacity-building tasks will vary according to the circumstances in each CBA country, as outlined by their CCPS documents.  IN general, they will consist of national-level workshops for potential grantees.  This item corresponds to approx 0.6% of total costs

6.  This covers costs of providing CBA technical support for the global lessons learning component, an important element of the CBA programme and SPA. Approximately 30 days per country at a rate of $220 consultancy support will be required to deliver this output over the lifetime of the project.  It is envisaged that this task will be carried out by project development/knowledge management consultant (see IV, part II, TOR E, task 1).  This item corresponds to approx 1.5% of total costs

7.  This cost covers cost of establishing the learning component at the project inception workshop and lessons learned publications at the end of the project.  This item corresponds to approx 1.4% of total costs

8.  This covers the cost of establishing a website for the project and database development and maintenance over the duration of the project.  This item corresponds to less than 0.5% of total costs.

9.  This item covers the costs of standard UNDP Monitoring and Evaluation requirements including mid-term and final evaluations.  It will also cover the costs involved in M&E on adaptation to climate change, an important requirement for adaptation projects.  This item corresponds to approx 2.2% of total costs

10.  The covers part of the final lessons learned publication and support for collection of programme-level M&E indicators in the ten CBA countries. The costs will support M&E as well as knowledge management in the CBA pilot countries.  This item corresponds to approx 5.1% of total costs.

11.  This item will support travel costs of consultants for the purposes standard UNDP M&E requirements.  This item corresponds to approx 0.7% of total costs.

12.  This covers the cost of a consultant to provide approximately 250 days of support spread over 4 years (at a rate of $220) for ensuring the smooth operation of project level activities.   TOR for the Programme Management consultant is attached (refer to Section IV, part II, TOR F).  This item corresponds to approx 1.2% of total costs.

# SECTION IV: ADDITIONAL INFORMATION

## PART I: OTHER AGREEMENTS

130. Letters of financial commitment and other agreements are attached.

## PART II: TERMS OF REFERENCES FOR KEY PROJECT STAFF AND MAIN SUB-CONTRACTS

131.  This section outlines the Terms of Reference for the following

- CBA National Coordinator

- CBA National Coordinating Committee

- CBA Programme Assistant Tasks/Outputs

- Global Level Project Management Unit

- TOR for CBA Technical Support/M&E/Learning Consultant

(a) TOR for the CBA National Coordinator

Location:			Post is located at each CBA country programme

Responsible unit:		EEG/GEF, Bureau for Development Policy

Supervisor(s):	Global Project Management Unit

132.  The NC will manage each national CBA programme from day to day, serving as the vertical linkage between NGOs and UNDP.  The NC may be assisted by the CBA Programme Assistant, whose role is to provide support to the NC, especially in the role of providing technical support to grantees.

Key Tasks:

- Country Programme Strategy Development

  - Recruitment of additional personnel to serve on the CBA national coordinating committee

  - Development of a country programme strategy document, in consultation with the NCC and national-level stakeholders

- Portfolio Development

  - Recruitment and capacity building of prospective grantees to participate in the CBA programme

  - Technical assistance as prospective grantees develop project concepts and proposals

  - Receiving project concepts and proposals, and forwarding them to the NCC for review

  - Coordinating meetings of the NCC for proposal review

- Monitoring and Evaluation

  - Technical assistance to grantees in fulfilling the requirements of the VRA and IAS indicator systems

  - Entry of monitoring data  into the CBA database prior to disbursement of funds

  - Overseeing the preparation and evaluation of midterm and final progress reports, approval of requests for disbursements of funds

- Knowledge management

  - Aggregation and reporting of indicator data from the country level to UNDP

  - Maintenance of a filing system for all project progress, H-forms and associated project data, to serve in the development of case studies near the conclusion of the project

  - Identification of successful projects for the development of case studies and lessons learned

  - Liaising with headquarters knowledge management staff during the production of lessons-learned papers and briefs

- Preparation of Budgets and Workplans

  - Preparation of workplans and timelines for country-level CBA programme implementation

  - Preparing cost estimates and funding requests for country programmes

Recommended Qualifications

- Experience working with communities and NGOs/CBOs in sustainable development contexts in the CBA country

- Advanced university degree in environmental fields, Environmental Economics, Business Administration or similar field.

- At least 5-8 years of relevant experience in development work, which should include programme management, preferably with an extended specialized experience in any of the GEF focal areas at the national level.

- Excellent analytical and writing skills, excellent teamwork and people management skills, excellent communication and interpersonal skills, good negotiation and problem-solving skills.

- Fluency in the official national language (must be one of the 6 UN languages) and English or a second UN language.

- Proficiency in standard computer software (word-processing, excel, presentations, databases and internet)

The budgetary support for the CBA National Coordinator will not be covered by the CBA project funds. These costs are already borne by the SGP, as per established GEF-SGP procedures.

(b) TOR for CBA National Coordinating Committee

Location:			In the respective CBA Country

Responsible unit:		N/A

Supervisor(s):	N/A

133.  In SGP countries, the CBA National Coordinating Committee is comprised of the SGP National Steering Committee, modified with additional personnel as necessary to ensure expertise in the field of adaptation to climate change including variability.  In the case of non-SGP countries, the NCC will be a voluntary body similar to that in SGP countries, responsible for applying CBA criteria and approving funding decisions.  The NCC is also expected to have a significant role in ongoing programme development and monitoring and evaluation activities as an advisory body.

Key Tasks

- Country Programme Strategy Development

  - In collaboration with other members of the NCC, decide on the geographic and thematic focus of the CCPS, based on national priorities and CBA guidelines, as described in the CBA Toolkit (annex 3).

- Portfolio Development

  - Working with other members of the NCC and the NC, determine a schedule for meetings to screen project concepts and proposals

  - Meet several times over the course of the CBA programme to screen CBA projects.  This may be done in parallel with meetings to screen SGP projects

Recommended Qualifications (for NCC’s recruited specifically for the CBA programme, whether as additions to a NSC or as a new body developed in a non-CBA country):

- Expertise in climate change science and impact assessments

- Expertise in economic development issues at the community level

- Senior-level experience in government, civil society or the private sector of the CBA country

The budgetary support for the CBA National Committee will not be covered by the CBA project funds. This is a voluntary function, as per established GEF-SGP procedures.

(c) TOR for CBA Programme Assistant Tasks/Outputs

Location:			Post is located in the office of each CBA country programme

Responsible unit:		EEG/GEF, Bureau for Development Policy

Supervisor(s):	CBA National Coordinator

- Portfolio Development

  - Assist prospective grantees as they conduct baseline studies and indicator measurements

  - Assist the NC with other tasks as needed

- Monitoring and Evaluation

  - Travel to field sites to assist in the measurement of VRA and IAS indicators for progress and final reporting

  - Ensure complete and efficient data collection, assist NC with inputting data into CBA database

  - Assist NC with other M&E tasks as necessary

- Knowledge Management

  - Assist NC with knowledge management tasks as required

Recommended Qualifications

- Masters level qualifications on climate change sciences and impacts assessments

- Experienced in economic development issues at the community level

Part of the budgetary support for the CBA Programme Assistants will be covered by the CBA project funds. The total costs to be borne by the project will be less than 2% of the total CBA budget.

(d) TOR for Global Level Project Management Unit

Location:			New York

Responsible unit:		EEG/GEF, Bureau for Development Policy

Supervisor(s):	UNDP-GEF CDAC Principal Technical Advisor

134.  The CBA programme will be implemented through the SGP’s existing country mechanisms where applicable, under the direction of a UNDP-GEF, through Capacity Development and Adaptation Cluster (CDAC), in collaboration with the GEF-SGP CPMT.  The project team will have the following responsibilities:

- Country Programme Strategy Development

  - Provide technical support to country programmes during the CCPS development phase

  - Review draft CCPS’s to ensure consistency with SPA guidelines prior to their adoption

- Portfolio Development

  - Oversee the strategic development of CBA projects in the relevant countries

  - Monitor the concepts and projects being approved by the NCC for fit to global CBA criteria, including SPA criteria

  - Provide technical assistance to UNDP-CO (and NCs) as necessary for the development of CBA projects

- Monitoring and Evaluation

  - Monitor progress of country programmes in meeting M&E requirements, providing technical assistance where necessary

  - Carry out programme level monitoring and reporting activities (see Section I, Part IV above)

- Knowledge Management

  - Assist the facilitation of lessons learned into the UNDP-GEF Adaptation Learning Mechanism

  - Facilitate cross-country knowledge transfer

  - Develop papers and briefs highlighting successful case studies and lessons learned from the CBA programme

- Operational Tasks

- Liaise with implementing partner for the disbursement of funds for CBA activities and maintaining budgetary oversight.

- Identify and liaise with potential and actual co-financing agencies and institutions.

- Monitor the overall implementation and outputs of the CBA programme.

- Delegating Tasks

- Hire and supervise international consultants to provide support with above tasks where necessary, as per the TORs for international consultants, specified below

Budgetary support for the global level project management unit will not be covered by the project funds. Instead, staff costs will be borne by IA fees as per standard rules and procedures.

(e) TOR for International Project Development/Knowledge Management Consultants

Location:			New York

Responsible unit:		EEG/GEF, Bureau for Development Policy

Supervisor(s):	UNDP-GEF CDAC Principal Technical Advisor

Background:

135.  The CBA Programme will is to develop community-level adaptive capacity, supporting the generation of lessons to facilitate mainstreaming community-based adaptation into policy, and to provide guidance to inform the development of future global-level community-based adaptation initiatives.  Support will be required to ensure the development of a high-quality portfolio of projects to achieve these ends, and to ensure the extraction of high quality lessons from these projects.

Overall Objective:

136.  The Consultant will undertake a number of activities designed to facilitate the development of the global portfolio of CBA projects, and the development of high-quality knowledge products.

# (1) Tasks and outputs

- Monitoring and Evaluation/Knowledge Management

  - Coordinate monitoring requirements of CBA projects, including data entry into the CBA database and submission of project progress reports carried out by the project teams;

  - Review of H-forms and associated project data, to serve in the development of case studies and other knowledge products

  - Consolidate quantitative and qualitative monitoring data, develop brief reports, and coordinate with knowledge sharing networks such as the Adaptation Learning mechanism;

  - Continually develop content for the CBA website, including up-to-date information on CBA projects including an updated FAQ section

  - Assist with the preparation and evaluation of midterm and final progress reports

  - Development of periodic thematic reports, and assistance on the development of the final lessons-learned publication

Deliverables:

  - Organized and completed CBA database content

  - Project-level data consolidated and organized

  - Reports on lessons learned during the project development and implementation phases

  - CBA website content developed

  - Input provided to midterm and final progress reports

  - Periodic thematic reports, final project lessons learned documents developed

- Project Development

  - Provision of technical support to NGO/CBO grantees of CBA projects, including assistance with proposal development

  - Assistance to grantees and prospective grantees to align proposals with the requirements of the SPA

  - Liaising with CBA NC’s on portfolio development, country programme strategy development, M&E and other requirements

Deliverables:

- CBA proposals of high quality, meeting SPA criteria

- CBA reporting requirements met by country programmes

- Country level strategies, proposals and projects that are successful and meet CBA requirements

Implementation and Coordination Arrangements

  - To be determined pending CBA programme implementation.

Qualifications and Experience

  - Technical knowledge of adaptation to climate change

  - Expertise in the design of adaptation projects

  - Familiarity with UNDP/GEF and CBA Procedures

  - Fluency in English (knowledge of French/Spanish is an advantage)

(f) TOR for International Programme Management Consultants

Location:			New York

Responsible unit:		EEG/GEF, Bureau for Development Policy

Supervisor(s):	UNDP-GEF CDAC Principal Technical Advisor

Background:

137.  The CBA Programme has a unique and distributed implementation structure, comprised of ten country programmes, the UNDP-GEF project management unit, and the SGP CPMT.  Coordination and support will be needed to ensure a steady flow of solutions and technical support, as well as information – both internally and to the public.

Overall Objective:

138.  The Consultant will undertake a number of activities designed to ensure the smooth operation of the global CBA programme.

- Support to the Global Project Team

- Coordination and logistical support of international CBA meetings

- Contribute to preparing key documents for CBA meetings including presentations on the CBA programme, analysis of the CBA Country Programme Strategies and Portfolio development progress

- Support the Global Team in developing partnerships with donors for the CBA programme

- Day-to-day maintenance of the CBA website

Deliverables:

  - Inception workshop for the CBA organized and executed

  - Documents for CBA meetings prepared

  - Relationships with global stakeholders secured

  - CBA website current, troubleshooting provided

2.  Assistance to CBA national coordinators

- Liaising with CBA NC’s for administrative and management purposes

- Providing guidance, under the supervision of the Task Manager, on financial, reporting, or procedural issues

Deliverables:

- CBA national coordinators provided with technical support and administrative backstopping

- CBA project procedures adopted by country programmes

Implementation and Coordination Arrangements

  - To be determined pending CBA programme implementation

Qualifications and Experience

  - Technical knowledge of adaptation to climate change

  - Website design and maintenance skills

  - Familiarity with UNDP/GEF and CBA Procedures

  - Familiarity with the CBA, and with UNDP/GEF CBA progress and priorities

  - Fluency in English (knowledge of French/Spanish is an advantage)

(g) TOR for Local Country Programme Strategy Consultants

Location:			In the respective CBA country

Responsible unit:		EEG/GEF, Bureau for Development Policy

Supervisor(s):	UNDP-GEF CDAC Project Management Unit, CBA National Coordinator

Background:

139.  Each CBA country programme will be guided by a CBA Country Programme Strategy.  This document will provide the necessary guidance, based on National Communications to the UNFCCC, NAPA’s, and other scientific vulnerability and adaptation assessments, to develop and support a portfolio of CBA projects to achieve the outcomes of the CBA programme on the country level.  The CCPS will require input from experts with extensive country-level expertise in climate change vulnerability and adaptation, as well as knowledge of local policy, capacity, and priorities.

Overall Objective:

140.  The consultant will, under the supervision of the CBA NC and the UNDP-GEF project management unit, develop and/or strengthen the CBA country programme strategy in one particular country.   One consultant for each CBA country will be supported.

- Develop the CBA country programme strategy

- Review National Communications, NAPAs, and other relevant documents

- Assess national policy as it relates to vulnerability and adaptation

- Conduct wide-ranging stakeholder consultations

- Write the CCPS, and work with CBA project development/knowledge management consultants in strengthening and securing approval of the document

Deliverables:

  - Completed and approved CBA country programme strategy

Implementation and Coordination Arrangements

  - To be determined pending CBA programme implementation.

Qualifications and Experience

  - Technical knowledge of adaptation to climate change

  - Knowledge of national policy relevant to adaptation

  - Experience with project and programme design

  - Capacity to engage with multiple levels of stakeholders, including communities, civil society, government, and the private sector

  - Fluency in English (knowledge of French/Spanish is an advantage)

## PART III:  STAKEHOLDER INVOLVEMENT PLAN

141.. As the CBA programme targets interventions at the community level in each of ten countries, a wide range of stakeholders will be involved.  Each participating country will develop its own stakeholder involvement plan, as part of its CPPS.  See annex 1 for examples of CCPS documents developed during the PDF-B phase.

142. At the programme level, inter-country exchange of experiences and lessons learned will be promoted in order to provide opportunities for wider learning and dissemination.  Key stakeholders in this process will include:

143. At the global level, a core CBA team will be formed. The core team will consist of (a) United Nations Development Programme – Global Environment Facility (UNDP-GEF), in collaboration with (b) GEF-SGP. The core team will be guided by the full set of Programme Team members, including GEF (e.g., both Secretariat and STAP), other Implementing Agencies and country representation. Since the activities and lessons of the CBA are part of a global GEF SPA commitment to the UNFCCC COP, guidance of the GEF STAP will be actively sought.

144. At the regional level, the UNDP Regional Coordination teams will be involved to support in monitoring progress and giving technical backstopping support to the national Coordination Committee.

145. At the national level, a National Coordinator (NC) and National CBA Coordinating Committee (NCC) will provide the necessary vertical linkage between community-based activities and national-scale climate change adaptation activities (by working in close consultation with national climate change focal points) as well as linking to UNDP. In SGP countries, these roles will be filled by the existing SGP National Coordinator and members of the National Steering Committee (NSC) respectively, with selected additional members to fill any important stakeholder gaps; for the CBA this body will be referred to as a National Coordination Committee, so as to ensure sufficient distinction between the two funding streams. In non-SGP countries, this SGP institutional model will be used to create similar bodies, with the support of UNDP country offices.

# Signature Page

Country: __Global______

UNDAF Outcome(s)/Indicator(s):				_____________________________________

(Link to UNDAF outcome. If no UNDAF, leave blank)

Expected Outcome(s)/Indicator (s):				_____________________________________

(CP outcomes linked to the SRF/MYFF goal and service line) 	_____________________________________

Expected Output(s)/Indicator(s):					_____________________________________

(CP outcomes linked to the SRF/MYFF goal and service line)

_____________________________________

Other Partners:							_________________________

Agreed by (Government): _______________________________________________________

Agreed by (UNDP):______________________________________________________________

# Annex 1:  CCPS Background Activities Conducted During PDF-B

1.  During the PDF-B phase, preparatory activities for the development of CBA Country Programme Strategies were conducted in the four PDF-B pilot countries (Bangladesh, Bolivia, Niger and Samoa).  These activities have led to the development of the CCPS Template and Guidelines (annex 3, section 3, attachment 1), which will guide CCPS development during the FSP phase.

2.  The Bangladesh CBA Country Programme Strategy below is a draft version, to be revised and finalized after the implementation of the FSP, during which time the six follow-on countries (Guatemala, Jamaica, Kazakhstan, Morocco, Namibia, Viet Nam) will also develop CCPS documents.  The draft Bangladesh CCPS below, along with CCPS documents from other CBA countries, will be available on the CBA website.

## I.  BANGLADESH: DRAFT CBA COUNTRY PROGRAMME STRATEGY

Please note:  this CCPS will be finalized during the implementation phase of the CBA project

- Overall CBA Country Programme Strategy (CCPS)

Summary:

3.  Climate change in Bangladesh is expected to bring temperature increase, sea-level rise, increasingly erratic and intense monsoon rainfall, and increased prevalence and intensity of flood and drought.  This will lead to substantial impacts on ecosystems, and threaten the sustainability of land management practices.  Pilot activities for the CBA will be concentrated on the southern coastal belt, a region that is expected to be highly impacted by climate change, but also provides opportunities for the generation and resilience-building of global environmental benefits in the face of climate change.  Recent assessments of likely impacts suggest that by 2030, the following climate change impacts are likely to materialize:

- significantly increased flooding due to 88cm or more of sea-level rise by the end of the century, and increasingly erratic and intense rainfall

- transformation of thousands of hectares of land from non-flood-prone to moderately or extremely flood-prone status

- loss of biodiversity in mangrove forests, due to storm damage, and changing balances between rainfall and salinity

- beginnings of the progressive inundation of mangrove forests, farm land, and other land in the area, stemming from the 30cm (or more) of sea level rise

- sedimentation of riverbeds, leading to changing ecosystem dynamics, and increasing risk of flood

4.  The CBA programme in Bangladesh will seek to build adaptive capacity in policy and institutional arenas to manage natural resources sustainably in the face of the above anticipated climate change impacts.  It will do so through the development of a portfolio of projects in the southern coastal belt of the country, focusing on community interventions to sustainably manage the ecosystems on which the water and agriculture sectors are based.  In line with country driven requirements, the portfolio will prioritize interventions focusing on women, the poor, fishers, landless and land-poor farmers.  The portfolio of CBA projects in Bangladesh will generate global environmental benefits in the biodiversity and land degradation focal areas. The portfolio will contribute towards building ecological, social and institutional resilience of these benefits in the face of pressures stemming from climate change including variability, by translating best practices identified by community-based projects into national policy and beyond.

  - Objectives and Impact Indicators:  Brief statement of objectives, and impacts indicators to be adopted by the country-level CBA programme.

5.  The objective of the Bangladesh national CBA country programme strategy will be the following:

Institutional capacity to manage natural resources sustainably in the face of climate change enhanced.

6.  The achievement of this objective will be measured by the following impact indicators:

- Rate of loss of natural resource base for livelihoods determined to be negatively impacted by climate change.

- Livelihoods options better suited to climate change available to target community.

7.  These indicators will be measured at the level of the national CBA programme with each project making a contribution towards an impact at the national level.

  - Sectoral Focus:  Description of the sector(s) to be targeted by the CBA programme.

8.  Based on priorities identified in the National Communications to the UNFCCC and recently completed NAPA process, the CBA Programme in Bangladesh will focus its activities in water and agriculture. These sectors have been identified to be especially vulnerable to climate change impacts, and activities within these sectors feature prominently in the NAPA’s list of priority activities.  CBA projects in Bangladesh will therefore focus on ensuring that ecosystems upon which these key sectors are based are made resilient to climate change.  Within this sector, global environmental benefits will be achieved in the LD and BD focal area, and made resilient to climate change including variability.

9.  In addition to the NAPA and the National Communication, the choice of water and agriculture as the focus of the CBA programme is supported by:

- Bangladesh’s PRSP.  The PRSP sets out a number of specific actions to be taken within these sectors, and includes the integration of climate change with other policies and programmes, policies and projects as among these objectives

- Bangladesh’s emphasis on sustainable development as part of its UNDAF outcomes, including natural resource management as part of UNDAF outcome 2

- The emphasis on land and water management under initiatives to address climate change in the UNDP Country Programme for Bangladesh

10.  The focus on the agriculture and water sector for CBA adaptation projects is consistent with country priorities as articulated in the CP/GCF/RCF. According to these documents, the following are priority areas of intervention that are compatible with the CBA objective in Bangladesh:

  - Vulnerability Assessment:  Description of the vulnerability of the targeted sector(s) to climate change including variability.

11.  Climate change assessments of Bangladesh suggest steadily increasing temperatures, particularly for the winter season, but also during the monsoon season.  There is some uncertainty in projections on a clear direction of change in the case of long-term precipitation averages, though rainfall events are expected to become more intense, with increasing variability during the monsoon season. In addition, the IPCC Fourth Assessment Report (SPM) suggests sea-level rise of several tens of centimeters by the end of the century, barring rapid glacial disintegration which could increase sea level much faster than anticipated with gradual change.  This will change coastal morphology – leading to progressive inundation of low-lying lands – but will change river flow patterns and reduce river speeds, increasing sedimentation, raising river beds and worsening the threat of floods.

12.  Anticipated climate change will translate into a diverse array of impacts on the ecosystems.  Sea-level rise, as well as increasing climate variability (taking the form of increasing frequency of droughts and floods) will worsen erosion pressures on agricultural lands, as well as erosion risks at the edges of waterways.  Freshwater ecosystems are increasingly stressed by increasing salinity, as well as sedimentation stemming from ongoing non-climate related erosion, as well as from the SLR-related processes described above.  Along coastal belts, drought and sea-level rise together constitute a substantial salinization risk, threatening both water, agriculture, and the biodiversity of the coastal mangrove ecosystems that protect water and agriculture from climate extremes.

13.  Locally-specific manifestations of vulnerability in Bangladesh’s dynamic and complex coastal zone will be gauged by participatory tools.  The Government of Bangladesh has introduced Community Risk Assessment Process to identify hazards (including climate change dimensions) and vulnerabilities to determine specific risks associated with different sectors (water, agriculture, etc.) and elements (crop, drinking water, employment, etc.).  This process is broadly used in Bangladesh, and will compliment the methodologies to be employed by the CBA programme to develop local-level vulnerability assessments in support of individual CBA projects.

  - Baseline-additionality reasoning:  Describe the current pressures to the target sector from non-climate threats, and the anticipated climate change risks.

13.  The ecosystems associated with water and agriculture in Bangladesh are under threat both from climate change, as well as a number of other social and environmental pressures.  CBA projects will address community-level ecosystem management or NRM priorities where they address challenges that arise directly from climate change including variability, and not where they arise from non-climatic drivers.  Non-climatic drivers of degradation in the water/agriculture include unsustainable agricultural practices, loss of protective forest cover through unsustainable extraction of fuelwood, conversion of coastal forests and agricultural land to shrimp farms.  These impacts are considered to be “baseline.”

15.  These baseline ecosystem management problems are being driven by a number of factors, but rural poverty is among the most central. According to studies completed for the NAPA, the entire southern coastal belt (the pilot region for the CBA programme) is classified as either moderately or highly food-poor, with its component regions having between 10 and 30% of its population subsisting on less than 1805 kcal per capita per day.  In the context of such poverty, long term approaches to sustainable ecosystem management are difficult, as the priorities of local stakeholders may not permit a focus beyond immediate livelihood needs.  Many of the ongoing environmental stressors, including unsustainable fuelwood extraction and conversion of ecosystems to aquaculture, are among the ways for communities to meet their immediate livelihood needs.

16.  Addressing the baseline poverty problem will facilitate addressing baseline natural resource management problems, and is the foundation upon which CBA activities may be based.  Strategies being undertaken to do so are spelled out in Bangladesh’s Poverty Reduction Strategy Paper.  In addition, the government is beginning to take climate change into account, and is leading the Comprehensive Disaster Management Programme, which is undertaking initiatives including:

- Conducting adaptation research aiming to generate livelihood options in the face of changing climate, which could be offered in the context of CBA implementation.

- Similarly, CDMP is also taking steps to review and analyze good practices for adaptation to climate change and disaster risk. This could be replicated in the CBA pilot region.

17.  Climatic drivers include sea-level rise, increasing temperatures (and subsequent increases in evapotranspiration and water stress), increasingly erratic rainfall, the component of riverbed sedimentation that is caused by climate, and increasingly intense and frequent cyclones.  These will lead to coastal inundation, coastal erosion, salinization of land, salinization of water resources, and riparian erosion.  These will directly impact agriculture and water through salinization, erosion, destruction of natural defenses against erosion and storm surges, as well as heat stress and increasing water needs in agricultural land.  These impacts are considered to be “additional.”

18.  Many of the climate change impacts that Bangladesh faces represent intensifications of historically familiar climate variability impacts (such as the intensification of cyclones, floods, and droughts).  Others are entirely novel, such as sea-level rise.  Projects that manage risk to ecosystems from novel climate changes (such as SLR) will be eligible for support from the CBA programme.  While CBA projects will not support risk management based on historically familiar climate variability, the CBA will support projects that address the increment of a given ecosystem problem attributable to intensifying climate variability, in situations where the baseline climate variability impacts are addressed by project partners, and supported through co-financing.  These criteria will be applied on a project-by-project basis, and proponents will be required to show that CBA support will be applied in situations where future climate risks to ecosystems are being taken into account.

19.  The GEF CBA intervention will add value to ongoing efforts to address baseline natural resource management problems, by piloting projects that explicitly address climate change risks through community projects.  Co-financing organizations and programmes, through the Government of Bangladesh’s Comprehensive Disaster Management Programme, as well as other organizations and initiatives, will work with CBA to ensure that these baseline constraints are removed, allowing CBA to focus on the natural resources management in the face of climate change.

  - Focal Area(s):  Description of the GEF focal areas in which these strategies will deliver global environmental benefits, and a discussion of how these benefits will be made resilient to climate change.

20.  CBA interventions in Bangladesh will build resilience to climate change in the Land Degradation and Biodiversity focal areas.  Climate change presents significant risks to global environmental benefits in these focal areas, including saltwater intrusion, greater erosion pressures, changing rainfall regimes – all of which will affect the natural resource management practices of people, leading to potentially greater ecosystem impacts.  Important biodiversity includes the eastern reaches of the Sundarbans mangrove ecosystem, and priority areas to combat and prevent land degradation cover the intensively cultivated landscape of the area, upon which many rely for sustenance, but which is threatened by erosion and salinization.  As per SPA guidelines, projects will deliver global environmental benefits, and ensure that these benefits are made resilient in the face of climate change.  Specific modalities for doing so will be determined on a project-by-project basis.

  - Local Priorities:  In addition to addressing the above requirements, description of additional local priorities that will guide project selection.

21.  Interventions under the Bangladesh CBA programme will be encouraged to focus on the needs of women, the poor, fisherman, and landless and land-poor farmers.  Many of the NGOs working in the target area (see item G below) are engaged in providing microfinance services to these populations.  The CBA programme will build on this experience and capacity while carrying out its climate change adaptation programming mission, providing lessons for replication elsewhere on how micro-finance can be used as an approach to community-based climate change adaptation.

  - Geographic Focus:  Description of the geographic region(s) of the country in which CBA activities will be focused, and how the selected region(s) aligns with sector specific vulnerability to climate change and other CBA requirements.

22.  CBA activities in Bangladesh will focus on the southern coastal belt region, including the districts of Barisal, Barguna, Bhola, Jhalakathi, Patuakhali, and Pirojpur (see map 1).  This selection was made based on detailed vulnerability assessments of several regions of the country, on the high vulnerability of communities/ecosystems to climate change including variability, as well as the excellent potential to generate global environmental benefits in the land degradation and biodiversity focal areas.

23.  This coastal area is interlaced with innumerable rivers and canals, where historically there was no dearth of fresh water or fisheries.  This region was once known as the granary of Bengal.  Climate conditions have changed over time, and drought, salinization, lack of fresh water, and severe decline of fisheries – both marine and fresh water – are now common phenomena.  Biodiversity and ecosystems have also declined.  The landscape between Patuakhali town and southern Kalapara Upazilla presents a bleak picture of drought-prone paddy fields lying idle, with not much water in sight.  Even the homestead ponds appeared dry.  Dug-up shallow ditches for collecting fresh water also were dry.  This is a new phenomenon in the region, as reported by the communities. Irrigation has never been a culture of this region.  Now, it is becoming a hard reality.  Road communications are not yet developed.  As a result, engine and country boats are the main means of internal communication within the region and between islands.

  - Community Project Typologies:  Description of the specific activities to be undertaken in the targeted sector(s) and explanation of how they contribute to the objective(s) of the CCPS.

23.  NGO/CBA grantees will have considerable latitude to develop CBA proposals and projects, provided that they comply with the requirements of the SPA, as well as the other requirements elaborated in this country programme strategy.  While proposals will not be limited to the sorts of examples provided below, projects such as the examples below would be fundable under the CBA:

- Adaptive community-based management of mangrove forests to sustain ecosystem services and conserve biodiversity in the face of climate change.  As sea-level rise progresses, ecosystem services such as storm surge protection, erosion prevention, fuelwood provision, and fish nursery provision will be threatened by inundation of mangrove forests, as well as changing balances between fresh and salty water in mangrove forests.  Under the baseline scenario, land pressures and other baseline pressures may continue to support the degradation of mangrove ecosystems, as their services become more valuable than ever in light of climate change.  Under the project, alternative livelihood systems and adaptive community-based ecosystem management practices will ensure the robustness of mangrove ecosystems and their associated services into the future, reducing vulnerability of communities and building adaptive capacity.  This will help to defend against the salinization of agricultural land and water resources.

- Adaptive community-based management of riparian corridor ecosystems.  In the face of climate change, floods and droughts stemming from increasingly intense and erratic rainfall will worsen the erosion of rivers and streams in the pilot region, threatening sustainable land management practices as well as riparian biodiversity.  While riparian erosion is a problem owing both to climate change drivers as well as baseline drivers, baseline drivers of erosion will be supported through cofinancing by project partners, while CBA will support the component of the problem that is driven by climate change, including changing patterns of variability.  Community-based riparian corridor activities could include reforestation and revegetation, creation of setbacks, and development of community-based mechanisms ensuring equitable access to riparian goods and services.

  - Policy Strategy:  Description of the strategy to be employed to involve and disseminate lessons learned to local authorities and national government.

25.  The CBA will develop pilot projects to identify successful approaches to upscaling and replication, as well as to provide insight into potential policy targets for mainstreaming lessons derived from community-based adaptation into national policy.

26.  There are quite a few other laws and regulations governing the agriculture and water sectors in Bangladesh. Many of these laws are outdated however, many others are contradictory, and many state agencies are inconsistent in enforcing them.  In addition to these baseline inadequacies, legislation relating to the agriculture and water sectors has not yet been framed to explicitly take ongoing climate change risks into account.  The CBA programme will, through community projects, provide lessons which will influence national policy on how it might best take climate change into account, including baseline legislative inadequacies where relevant to adaptation.

27.  The CBA project will be implemented following the existing grant-giving mechanism of Local Disaster Risk Reduction Fund in CDMP.  As such, the field level monitoring will involve the local government representatives, field level government resource management agencies, and NGOs.  This will result in a sustained partnership between these stakeholders, exposing policymakers to best practices identified by the CBA project.  This will facilitate replication, upscaling and mainstreaming, as the architecture of the Local Disaster Risk Reduction Fund places policymakers directly into contact with project activities.  This in turn will be support and be supported by the generation of knowledge products by the CBA programme, which will aim to influence policy at the national level and beyond.

28.  These activities will prompt at least one significant policy change that protects, manages, or otherwise supports the ecosystems upon which agriculture and water are based in the face of climate change including variability.

- Development of the CBA team

  - NCC Formulation:  Description of how the NCC has been or will be constituted.

29.  As Bangladesh is only now joining the GEF -SGP, there is no such National Coordination Committee for overseeing the implementation of small-grants projects.  However, the Comprehensive Disaster Management Programme (CDMP) under the Ministry of Food and Disaster Management has a national Steering Committee, comprising the senior officials including the GEF Focal Point and Department Heads of development ministries.  The Government of Bangladesh has nominated this committee, which also includes a civil society representative.

Composition of the NCC:  The composition of the Steering Committee is as below:

- Representative, Economic Relations Division, Ministry of Finance

- Representative, Ministry of Food and Disaster Management

- Representative, Disaster Management Bureau, Ministry of Food and Disaster Management

- Representative, Directorate of Relief and Rehabilitation, Ministry of Food and Disaster Management

- Representative, Directorate of Food, Ministry of Food and Disaster Management

- Representative, Planning Commission

- Representative, Ministry of Home Affairs

- Representative, Department of Environment (DoE)

- Representative, Bangladesh Disaster Preparedness Centre (BDPC)

- Representative, United Nations Development Programme (UNDP)

- Representative, Department for International Development (DFID)

- Representative, World Food Programme (WFP)

- Representative, Food and Agriculture Organization (FAO)

- Representative, Comprehensive Disaster Management Programme (CDMP)

- Representative, Bangladesh Meteorological Department (BMD)

- Identification and Capacity Building of Potential NGO/CBO grantees

  - NGO/CBO Identification: Description of the NGOs/CBOs to be engaged as partners in the CBA programme.

30.  Initial scoping activities for the development of the CBA programme have identified several NGOs working in the pilot region.  Shortly after inception of the CBA programme, NGOs will be shortlisted based on their potential capacity to implement CBA activities under this country programme strategy, to be engaged in capacity building activities to develop CBA projects.

31.  The criteria of selecting partners might be as follows.  These are the minimum requirements, and NGOs/CBOs will not necessarily be chosen simply by satisfying these criteria, but rather selected from a pool of applicants, all of whom fit these criteria

  - Institutional capacity to implement, monitor, satisfy reporting requirements, and assist in the generation of knowledge products for the CBA project

  - Previous work experience in climate change, NRM, risk reduction, and livelihood security

  - Having community based and community level work experience

32.  A broad cross section of the eligible NGO/CBO community will be included in CBA capacity-building activities, prompting a wide selection of proposals for CBA projects.  This will facilitate competition for CBA funding opportunities, in turn facilitating the submission of quality proposals from competent proponents.

  - NGO Capacity Building:  Description of CBA capacity building and networking activities for partnering NGOs/CBOs.

33.  Shortly after CCPS completion, a workshop will be held to introduce selected regional NGOs to the CBA programme, and to build capacity among the potential proponents to develop and deliver high-quality projects.  This workshop will have the following outcomes:

- NGO/CBO understanding of project requirements under the CBA built

- Capacity for successful proposal writing built

- Community leadership and organizational management skills improved

- CBA project specific M&E framework understood by prospective proponents

Development of a common understanding of likely climate change impacts in the target region established

# Annex 2:  Project Design and Monitoring and Evaluation Framework for Community Based Adaptation

## 1. INTRODUCTION

1.  This annex provides a combined framework for the development of Community Based Adaptation (CBA) projects and associated monitoring and evaluation (M&E) system. Recognizing that climate change impacts will be felt at the community level, and that adaptations will occur at the community level (even if they are in tandem with or in response to larger-scale adaptations), the programme development as well as monitoring and evaluation (M&E) framework presented here emphasizes local stakeholder priorities.

2.  Adaptation to climate change has a long history under the United Nations Framework Convention on Climate Change (UNFCCC).  Based on climate change risks identified through the process of preparing national communications to the UNFCCC, countries are recognizing the necessity to implement holistic programmes and strategies that promote adaptation to climate change.  At the community level, projects that promote adaptation to climate risks may not be new.  There are, however, few if any rigorously tested frameworks for project conceptualization, guidelines for project development, or indicators to assess project success in CBA to climate change.  Relying heavily on processes and intellectual frameworks developed for climate risk identification and capacity building under UNFCCC processes, this UNDP-GEF initiate will pilot an approach to develop, implement, monitor and evaluate actual CBA projects.  It is intended to serve as part of the beginning of an ongoing global discussion on how to “do” CBA.

3.  The framework presented here is informed by the experiences of a variety of established programmes and adaptation methodologies including UNDP-GEF’s Adaptation Policy Framework (APF). Considerations of climate risk, hazard and vulnerability, and the use of a quantitative and qualitative (question-based) indicators echo elements of the APF. The stakeholder-based approaches herein draw heavily on vulnerability and adaptation methodologies compiled in the UNFCCC Compendium of Decision Tools to Evaluate Strategies for Adaptation to Climate Change.  Specific evaluative methods are strongly driven by intended project outcomes, using such combinations of qualitative information and quantitative indicators.

4.  As required by all GEF Trust Fund projects, CBA projects will generate global environmental benefits.  Conforming to the guidelines of the GEF Strategic Priority on Adaptation (SPA), these global environmental benefits will be made resilient to climate change including variability.  CBA projects will focus on ecosystems and natural resource management practices, and it is through enhancing the resilience of these that local communities will increase their adaptive capacity and reduce their vulnerability to climate change including variability – by safeguarding the ecosystem goods and services upon which they rely.

5.  The document begins with a discussion of the aims of CBA, the methods of M&E and the rationales behind the approach chosen. A programme development framework is then outlined, followed by a project development framework describing the scoping and implementation phases of a project in terms of a number of steps, each of which is associated with specific M&E activities.

## 2. GOAL OF COMMUNITY BASED ADAPTATION

6.  The goal of CBA projects is to enhance the ability of communities to cope with climate change including variability by strengthening the resilience of ecosystem goods and services upon which they depend. Within the context of enhancing ecosystem resilience to climate change, CBA projects may seek to:

(i) help communities to better adapt to historically familiar patterns of climate variability, where these may provide lessons and basis for adaptation to climate change.

(ii) help communities adjust to new trends in climate

(iii) anticipate and plan for projected long-term changes in climate

7.  Projects may be highly targeted at specific adaptation activities.  For example, a project could improve crop yields through rainwater harvesting linked with irrigation in the face of reductions in the amount or predictability of rainfall – stemming land degradation, and creating mechanisms to ensure that the land will be able to be managed sustainably in the face of climate change including variability into the future.  Alternatively, projects may seek to increase the capacity of a community to design and implement adaptation strategies and measures in a more general sense, so long as they deliver GEB and ensure that these will be made resilient to climate change including variability. In practice CBA projects are likely to contain elements of both approaches (i.e. actual adaptation and the enhancement of adaptive capacity). Nonetheless, projects should have a clear objective and a series of outcomes which are stated at the outset.

8.  All CBA projects will have the similar overarching objective of enhancing adaptive capacity.  That is, the ability of communities to proactively assess current and future climate risks on ecosystems upon which they depend will be strengthened as well as capacity to respond to those risks in a proactive and evolving manner.

9.  The objective listed above will be pursued through a set of outcomes, which will be highly specific to local community contexts. These are discussed in more detail in the project proposal development guidelines (annex 3, section 3, attachment 4).

10.  In addition, CBA projects will need to satisfy the following GEF objectives:

- Delivering global environmental benefits

- Achieving financial and environmental sustainability for the project intervention

11.  Furthermore, CBA projects must meet SPA criteria, demonstrating increases in adaptive capacity or resilience of global environmental benefits in the focal areas in which GEF works.

## 3. PROJECT AND PROGRAMME STRUCTURE

12.  The CBA programme includes all CBA-supported interventions at a global level.  The global programme is made up of 10 national CBA programmes.  These individual programmes will be driven by a Country Programme Strategy (CCPS) that will articulate the objective of the country level interventions. The CCPS will identify priority vulnerabilities to climate change and form the strategic basis for the identification and selection of a number of individual projects for implementation at the community level. Each national programme will encompass 8-20 projects.

13.  Individual projects will contribute to the overall objective of the country programme through their own specific objective and set of outcomes. These will be developed by project proponents as part of the project proposal development process, and will be evaluated based on their fit with the objective of the CCPS, and the global objective of the CBA.

14.  The selection of community projects by the national CBA programme will be guided by a CCPS, the development of which will be the first indicator for each country programme under outcome 1 (see section 5 below: “Programme Development Framework”).  The CCPS will be approved by the UNDP/GEF (CDAC) based on congruence with SPA requirements, as well as technical rigour.  See annex 3, section 3, attachment 1 for a CCPS template and guidelines.

15.  The approved CCPS will guide the development a portfolio of community projects in each country.  Potential project proponents will be invited to submit project concepts and proposals (templates for which can be found in annex 3, section 3, attachments 2 and 4).  Receipt of a concepts and proposals by each country programme will comprise the second indicator under outcome 1.

## 4. MONITORING AND EVALUATION (M&E)

16.  At the global, country and project levels, monitoring and evaluation is necessary in order to ensure that the stipulated objective of building adaptive capacity, reducing community vulnerability and increasing the resilience of global environmental benefits to climate change including variability in the GEF focal areas is met.

17.  In addition, a well defined M&E process will:

- facilitate the identification and resolution of problems that arise throughout the course of projects

- enhance project performance and assess project impacts

- provide the basis for technical and financial accountability

- build local capacity to implement and manage projects successfully and strengthen community ownership of adaptation activities

- promote the identification and dissemination of lessons learned by participants themselves

- ensure congruence with CBA project criteria, which are in turn based in SPA criteria, SGP criteria, and criteria elaborated in the individual country CCPS documents

18.  M&E will be strongly participatory and stakeholder driven. It will also facilitate learning and knowledge transfer. The people who are best placed to assess a project’s impacts are those at whom the project is targeted, or those who interact on a regular basis with the systems that are the targets of the project activities. Thus, M&E will be “based on data that are collected through simple techniques, directly related to project interventions, and readily interpreted by project staff.” Such data will include objective indicators of project outputs, and qualitative, participatory indicators that seek to measure community perception of changing risk over time (described as part of the vulnerability reduction assessment, below).

19.  M&E will be at both the programme (global) and project (local) level. At the programme level this will involve the aggregation of information derived from M&E during the course of individual projects, as well as outcome indicators, described in the logical framework matrix. For the sake of comparison between projects and aggregation at the programme level, M&E will involve the use of indicators and the construction of indices.

20.  Prior to the implementation of each CBA project, current levels of risks, vulnerabilities, livelihood options, coping strategies as well as indicators measuring global benefits in a relevant focal area will be determined.  Project impacts will be assessed in relation to data gathered and collated at different intervals during implementation (the number of intervals will depend on the length of the project and context, but will include at least 3 intervals). Impacts will be evaluated in relation to the stated objective and outcomes of the project.

21.  The CBA Programme will rely on two sets of complementary indicators-- (i) SGP’s Impact Assessment System (IAS) and (ii) the Vulnerability Reduction Assessment.  SGP’s IAS will measure the global environmental benefits generated by the project.  The IAS consists of a set of indicators for each GEF focal area, one or more of which is adopted by each project based on the focal area it operates under.  Measurement of improvement in adaptive capacity will lean on perception-based indicators based on the Threat Reduction Assessment (TRA) approach which is used frequently in the Biodiversity Support Programme. Following the TRA approach, the Vulnerability Reduction Assessment (VRA) indicator framework emphasizes M&E based on qualitative assessments using simple techniques that are easily interpreted.

22.  Together, the VRA and IAS provide separate and complimentary set of indicators to measures global environmental benefits, and community validation of project impacts.  Both sets of indicators will generate information that will be useful in identification of lessons learned and contribute towards the development of knowledge products.

### 4.1 The SGP Impact Assessment System

23.  As per SPA criteria, all projects will generate global environmental benefits, and enhance their resilience to climate change including variability.  These global environmental benefits will be measured through the SGP IAS, which is a system of objective indicators, classified according the GEF focal areas.  The indicators are standardized, and constitute a menu from which project proponents may choose at least one.  In other words, each project will choose from the selection of indicators developed under its focal area.

24.  IAS indicators measure either to biophysical impacts or project processes that are in turn indicative of biophysical impact toward achieving global environmental benefits.  Furthermore, IAS indicators are based on a target-achievement approach, rather than a baseline target approach.  Thus, all projects will set IAS targets at project outset, as part of the project proposal.  Progress toward these targets will be measured at regular intervals to be determined in the project proposal, and will be monitored regularly by the CBA country programmes.

25.  IAS indicators will be chosen based on best fit to the ecosystem resilience-building and sustainable NRM approach of the CBA, and their values recorded in the CBA database.  As stated in the logical framework matrix, 75% of projects are expected to have met their IAS targets by the completion of the five year period of the CBA.

### 4.2  The Vulnerability Reduction Assessment

26.  At the level of community projects, the indicators for development of adaptive capacity to climate change will be based on the Vulnerability Reduction Assessment (VRA) framework.  Based on the TRA, several UNFCCC stakeholder-based adaptation methodologies, and being informed by UNDP-GEF’s Adaptation Policy Frameworks (APF) guidelines, the VRA relies on a set of seven perception-based indicators to develop an index of adaptive capacity.

27.  These seven VRA indicators each correspond to an open-ended question, all of which are posed to local stakeholders in a group meeting.  The questions gauge key elements of adaptive capacity by measuring evolving perceptions of risk and ability to autonomously adapt to climate change (see next section for details).  The discussions elicited will be recorded using the “H-form” (Figure A2-1).  The H-form (used frequently in stakeholder driven processes) provides a format for stakeholders to numerically answer the questions posed, and also provide comments justifying that score.

28.  Beyond simply recording numerical scores however, the H-form also serves as a record of the VRA meetings, inviting stakeholders to comment on their reasons for negative or positive responses (on either side of the form), as well as their ideas on how the score might be improved (recorded on the bottom).  This will facilitate effective participatory project design.  All H-form questions must be formulated so that a numerical score is possible, and the numerical scores should always be oriented so that the higher score is the more favourable while the lower is the least favourable.  For detailed guidance on implementation of the H-form and the VRA in a community setting, see annex 3, section 2:  “A Users Guide to the Vulnerability Reduction Assessment.”

Figure A2-1:  A blank H-form.  Questions are written across the top centre, each participant scores their answer to the question on the centre line, and comments about why the scores are high or low are recorded to the left and right.  Comments about how the score might be improved are recorded on the bottom centre.  H-forms are generally drawn on large flip-charts, and VRA questions are adapted for the specific project context based on the VRA framework.

29.  Use of perception-based indicators requires a common understanding about the magnitude of current and developing climate risk.  Therefore, initial VRA meetings will be preceded by awareness raising sessions, to help the community to understand the significance of coming changes that are not yet perceptible, or to the place current impacts into a broader context.  This will not only lay the foundation for monitoring and evaluation using the VRA, but will facilitate autonomous adaptation as the awareness of community members is raised as to and ongoing climate risks.  More practically, it will help to establish a common understanding of climate dynamics that will facilitate group discussion while measuring the VRA.

30.  The exact format of the questions asked will depend on the community context and on the specific project focus, though each community will answer the same sort of question for their own locally specific adaptation concerns.  The seven indicators with their corresponding questions and the logic behind them is presented in the table below.  As the table show, the indicators each map to a step of the UNDP-GEF APF process (note that the first step, “scoping and designing an adaptation project,” is completed before the VRA is done, at during project concept development.  See section 6, “Project Development Framework,” below.

| APF Step | Indicator | Sample Question | Logic |
| --- | --- | --- | --- |
| Assessing current vulnerability | 1. Vulnerability of livelihood/welfare to existing climate change and/or climate variability. | How severe is the present impact of (climate risk) on your (climate-sensitive livelihood or welfare)? Example: How severe is the present impact of drought on farming in your community? (The choice of “drought” and “farming” would have already been dictated by the development of the project concept in this example). | Addresses present climate-related development issues – often the main climate concern of the community. Applicable to climate variability and/or climate change (depending on specific risk and community context). Prepares community for following questions that are specific to anthropogenic climate change by grounding that discussion in a framework that relates it to present impacts. |
| Assessing current vulnerability | 2. Efficacy of coping mechanisms in the face of current climate change/climate variability risks. | How effective are your mechanisms for dealing with (climate risk) presently? Example: What does the community currently do to limit the damage caused by cyclones, and how effective are these measures offsetting damage and reducing mortality? | During the first VRA meeting, this question will describes baseline adaptation to climate variability. During subsequent meetings, it will assess progress against that baseline. Applicable to climate variability and/or climate change (depending on specific climate risk and community context). As above, grounds community in present practices, preparing them to think about how changing conditions might impact those practices. |
| Assessing future climate risks | 3. Vulnerability of livelihood/welfare to developing climate change risks.* *Climate risks as based on country strategies, which in turn are based on National Communications and NAPAs | How severe would the impacts of (climate change risk be on (climate-sensitive livelihood or welfare)? Example: How severe would the impact of doubled frequency of meningitis epidemic years be on the health of your community? | Once present context of variability has been discussed, this question focuses the community on their perceptions of likely impacts of climate change. This question is based on “likely” impacts on sectors identified in project target, which in turn are based on CCPS. Allows the community to begin to consider long-term viability of livelihood practices in the face of climate change, leading to the following question. |
| Assessing future climate risks | 4. Ability of the community to respond to developing climate change risks. | To what degree is the community prepared to address (climate change risk), through (project intervention and current coping mechanisms) without a diminution in livelihood or wellbeing? Example: Will the community be able to address doubled soil salinity without a decrease in livelihoods or wellbeing? | This question compliments the previous one by focusing the community on potential actions to respond to CC. During the first VRA meeting, this question will measure baseline adaptive capacity. During subsequent VRA meetings, as answers to this question improve, this question measures progress against that baseline, influenced by the project intervention. |
| Formulating an adaptation strategy | 5. Magnitude of barriers (institutional, policy, technological, financial, etc) barriers to adaptation. | What are the barriers to adaptation, and how surmountable are they? Example: What stands in the way of more widespread use of drip irrigation, and how difficult will it be to overcome these barriers? | This question will qualify the above question, and focus it onto the needs of the community in successfully achieving adaptation. This question will identify policy barriers, forming useful lessons for the country and global programmes. This question will also measure unintended consequences, unexpected setbacks, and other barriers that were not identified during the project scoping phase. |
| Continuing the adaptation process | 6. Ability and willingness of the community to sustain the project intervention | To what degree do you think that (project intervention) will continue after the project concludes? Example: Will the community be able to continue stabilizing erosive hillsides with improved grasses after the conclusion of the project? | This question measures project sustainability and ownership, essential if adaptation to long-term climate change is to be successful. |
| Continuing the adaptation process | 7. Ability and capacity of community to continue the adaptation process, and to carry it beyond the specific project focus | To what degree will the community be able to go further in decreasing their vulnerability to (climate change risk)? Example: To what degree is the community able and willing to take other measures to adapt to sea-level rise beyond the measures taken by this project? | This question measures adaptive capacity more directly than other questions, as it seeks to determine to what extent communities will continue to adapt, and to what extent they feel that they are able to do so. |

31.  The seven questions will be answered by community participants in the project at a single VRA meeting.  A number of VRA meetings will occur during project implementation,  This will allow for measurement of the ways in which scores – as well as qualitative justifications for scores – change, forming the basis of the VRA index, which is simple percentage change from the baseline VRA score.  Again, for more detail, consult annex 3, Section 2.

32.  At the level of a country programme, all of the VRA percentage change scores for each of the individual projects may be averaged to provide a measurement of that country’s progress in facilitating community adaptive capacity through the CBA programme.  At the global level, this averaging across country programmes will also be done, providing a similar indicator under outcome 1.  As described in the logical framework matrix, the CBA is expected to increase globally averaged VRA values by 35% over baseline values by the end of the project period.

33.  Percentage changes in VRA index values over the course of an individual CBA project yield a VRA score, which can be averaged over the whole of the global CBA programme.  This provides comparability across a wide array of project contexts, and readily facilitates aggregation.  Lastly, VRA is simple to measure and easy to interpret, facilitating collection by diverse project teams.

34.  The VRA is a flexible tool, and is especially suited to community projects that are focused on building adaptive capacity, measuring the changing nature of people’s perception of their long-term ability to cope to changing climate.  Based on community-level awareness raising about climate-change risks and training to better meet them, adaptive capacity-based approaches will provide stakeholders with the necessary tools and access to strategies that facilitates improved adaptation to climate change autonomously.  The VRA will provide an indication of their changing levels of confidence in this regard. However, it must be borne in mind that perception based approaches have their limits to gauging climate conditions and impacts. Thus, the use of scientifically measured indicators on climate trends and other measurable indicators of vulnerability (e.g. incomes, yields per hectare etc) will be provided to stakeholders to facilitate discussion as well as in the analysis of the perception based results.

### 4.3 National-Level M&E

35.  Outcome 2 supporting the objective of the CBA relates to the development of national policies and programmes that promote replication of best practices derived from CBA projects.  This is to be accomplished through engagement of each country programme with relevant decision makers, reports, briefs, site visits, seminars, etc.  As described in the logical framework analysis, the CBA expects to influence the adoption of 8 policies or programmes at the national level in the various countries in which it will be implemented. The adopted policies and programmes should be based on lessons learned and best practices from the CBA.  This indicator will be monitored by NC reports to the project team.

### 4.4 Global-Level M&E

36.  Outcome 3 of the CBA relates to cooperation among member countries to share knowledge and experience on best practices in climate change adaptation, with the goal of at least one example of a strategy or practice being instituted based on the experience of another country.  This will be monitored by surveys of NCs and the UNDP-COs, and will be accomplished through the collection and development of lessons from CBA projects and country programmes into knowledge products.  This will be facilitated by the information gathered in the H-forms, the CBA database, the reporting requirements for funding disbursement (annex 3, section 3, attachment 6), and the ALM-linked final project reporting requirement (annex 3, section 3, attachment 7).  Interim reports, required of country programmes, will also contribute towards this.

### 4.5 Adaptive Management of M&E

37.  The programme development and monitoring and evaluation frameworks developed herein are intended to allow for adaptive management by UNDP (through CDAC, in collaboration with SGP).  In addition to lessons on how to “do” community-based adaptation, the CBA programme will generate lessons on how adaptation can be evaluated on the community level.  Taking a learning-by-doing approach, this framework – especially the VRA – will be modified as necessary by the project team based on feedback from stakeholders, especially implementing NGO partners and CBA country teams.  This will be done in a coordinated manner, in such a way as to not render previous measurements incompatible with newer approaches.  The specific questions and project-level methodologies used to generate this information may be modified over the course of the initial 5-year period based on successes and setbacks in project implementation.  The project team will actively monitor these methodologies and suggestions, and provide updates on any methodological changes as part of the programme’s periodic reporting requirements.

## 5. PROGRAMME DEVELOPMENT FRAMEWORK

38.  The programme development framework in each of the participating countries will follow the APF 5-step process shown in figure A2-3 below.  Each individual community project will follow this framework as well.

Figure A2-2:  Outline of the Adaptation Policy Framework process

### 5.1:  Scoping and designing: the CBA Country Programme Strategy (CCPS)

39.  Scoping and designing involve developing a programme infrastructure, consulting stakeholders, clarifying the objective, forming the country programme team, and reviewing existing information on vulnerability and adaptation.  In the context of the CBA, this will involve consultations between the National Coordinator, National Coordinating Committee, and stakeholders who are involved in any relevant adaptation-related initiatives or projects.  These should include national hydrological and meteorological services, as well as experts and policymakers involved in the identified sector.  In countries where there is an existing SGP mechanism, this process involves building the capacity of the existing NC in adaptation issues within their country context, modifying their NSC into a CBA NCC, and establishing workplans, procedures, and all of the relevant programme infrastructure required to implement the CBA.  In countries where SGP is not active, a new body will be formed, incorporating relevant stakeholders from NGOs, government bureaus, the private sector, and the national hydrological and meteorological services, as it has in the case of Bangladesh (see annex 1).

40.  Following the conclusion of the global level CBA inception workshop, the CBA country programmes will begin to draft their CCPS’s, which involve choosing a sectoral focus for CBA activities, as well as a geographic region of the country for the activities to focus on.  This choice of sector and location allows for the subsequent steps: assessing current climate vulnerability and future risks.

### 5.2:  Assessing Current Vulnerability

41.  Current climate vulnerability assessment is the second step in developing the CCPS.  The assessment will be based on a synthesis of existing materials such as National Communications to the UNFCCC, NAPA’s, outside research, expert consultations, and feedback from relevant stakeholders.  Beyond a simple listing of climate risks and their impacts on the target CBA sector however, this step involves the identification of the adaptation baseline – to what degree have stakeholders adapted to existing variability in climate or to extant manifestations of climate change, what the needs are in adapting to current climate.  This baseline will be used to demonstrate additionally, informing what is eligible for CBA support under the SPA requirements.

42.  The assessment of current climate vulnerability will comprise part of the CCPS.  Rather than an exhaustive summary of all the climate vulnerability issues faced by the country, it will be highly focused on the sector chosen for that country’s CBA programme.  It will rely on scientific assessments and consultations with experts from national hydrological and meteorological services, as well as other experts and policymakers in the selected sector.

### 5.3:  Assessing Future Climate Risks

43.  Following a similar process as that described in the previous step (synthesizing existing documents, surveying literature, consulting experts and stakeholders, etc), the process of assessment of future climate risks forms the next part of CCPS development.  Also similar to the previous step, this step need not be an exhaustive list of all climate change risk, but rather be highly focused on the biophysical and associated socio-economic risks stemming from coming climate changes in the selected sector.  It should also include an assessment of baseline adaptations and adaptive capacity (to extant and worsening manifestations of climate change), to help set the baseline for interventions which might be supported by the CBA programme.  Like other steps, it should be based in scientific assessments and probabilistic projections of future climates.

### 5.4:  Formulating an Adaptation Strategy

44.  The adaptation strategy forms the heart of the CCPS.  It should be based on the specific needs of the targeted sector, and will elaborate types of interventions that will be supportable under the country CBA programme.  Beyond simply responding to ongoing and coming climate risks however, the adaptation strategy will also identify and seek to address local priorities, be they either on the level of national governments, or local-level priorities with regard to types of adaptation interventions.

45.  The formulation of the adaptation strategy will also include the selection of a specific region of the country that will be eligible for CBA support.  As CBA projects must satisfy a double requirement – generating and increasing the resilience of global environmental benefits (in a relevant focal area) to climate change, and increasing adaptive capacity of ecosystems and communities – a region of the country will be selected where both requirements are achievable (figure A2-3).  See annex 3, section 3, attachment 1 for further details.

Figure A2-3:  A hypothetical country, divided into areas with high vulnerability to climate change including variability, and areas where global environmental benefits from enhanced ecosystem resilience or improved natural resource management might be attained.  Areas where the two intersect have the potential to host CBA projects.

### 5.5:  Continuing the Adaptation Process

46.  The completed CCPS will serve to guide the CBA country programme, setting guidelines for the types of community projects that it can support, and providing a basis for technical assistance to projects.  In the context of the CBA, this final step in the APF process will generate a series of small-scale APF processes at the community level.  These projects will then generate lessons, which will generate ongoing policy change and momentum for mainstreaming of adaptation best practices – continuing the adaptation process.  See annex 3, section 3, attachment 7 for the global lessons learned template, which will record lessons from CBA projects and transmit them to the ALM.

## 6. PROJECT DEVELOPMENT FRAMEWORK

47.  Individual CBA projects will be a microcosm of the country-level APF process.  Each will move through the same five steps, and in their totality, they will contribute to the overall country-level adaptation process described in the programme development framework above.

### 6.1:  Scoping and designing community projects

48.  The scoping and design process of the community projects will be accomplished though the project concept and proposal process, templates for which can be found in annex 3, section 3, attachments 2 and 4.  They will be completed by project proponents, in consultation with both the local communities involved in the projects, as well as the CBA country programme team.

49.  Where the project concepts and proposals call for local-scale climate impacts and scientific assessments, the proponents will rely upon both publicly available scientific literatures.  These may be from locally available expertise on climate impacts, from local government, local NGOs, national hydrological and meteorological services, and others with specialist knowledge of ongoing risks from climate variability, or who are in a position to have an understanding of the implications of climate change for the region.  Feedback from these stakeholders will set an impacts baseline, setting the context under which the VRA can be measured, and more clearly reflect changes from a baseline.  This information will also be used for awareness-raising activities at the project level, preceding the VRA and ensuring that all stakeholders have a clear and common understanding of likely climate change risks.

50.  Also as part of the project proposal development, each project will develop a set of outcomes, activities and tasks to support the project objective, which should be independently verifiable, and may include objective measures such as size of area protected, percentage yield increase, number of people with access to clean water, etc.  See the project proposal template and guidelines (annex 3, section 3, attachment 4) for more details.

### 6.2:  Assessing Current Vulnerability

51.  With broad-scale vulnerability already defined at the national level by the CCPS, the current climate assessment at the community project level will focus more strongly on the manifestations of current climate variability at the local level, in the context of livelihoods, geographic location and socio-economic vulnerability.  It will be assessed in a participatory manner through the VRA process.  This process will merge scientific and local perceptions of climate risks and.  The first and second VRA indicators speak to this stage of project development.

### 6.3:  Assessing Future Climate Risks

52.  Similar to the above step, this step will define local-scale vulnerability to future risks in the context of the national-scale vulnerability described in the CCPS.  Also like the above step, it will be assessed through the VRA, with questions 3 and 4 being most relevant to this component of the APF process.

### 6.4:  Formulating an Adaptation Strategy

53.  Consistent with the adaptive capacity approach of the CBA programme, project design will assist the community with building their own capacity to implement adaptations to climate change.  While the general focus of the project was already formulated during the scoping process, the community will determine how to operationalize that focus, by removing barriers to increased uptake of the identified adaptation option.  Question 5 of the VRA relates most to this step, but all of the VRA questions, through the part of the H-form that asks “how might this score be improved,” work to help formulate the adaptation project strategy with the community.

54.  Given that the initial VRA meeting occurs between the submission of the project concept and the project proposal, this community co-formulation of the adaptation strategy will serve to substantially guide the actual design of the project, ensuring responsiveness to local needs and lessons about how best to work with communities to adapt to climate change.

### 6.5:  Continuing the Adaptation Process

55.  Successful proposals will move to implementation, and be evaluated by at least two more VRA meetings.  These will serve to adaptively manage the projects – providing mid-term course corrections where necessary and ensuring that the proponents are accountable not just to the country CBA programme but to the people who the projects purport to serve.  In addition, the VRA questions 6 and 7, which relate to perceptions of capacity to continue the project intervention and take other adaptation measures, related directly to the built capacity of the community to adapt to climate change into the future.

56.  CBA projects of course will be selected based on their fit with the CCPS, which will be elaborated in such a way as to provide lessons for continuing adaptation both within the country and internationally – fitting into national adaptation policy initiatives and into the Adaptation Learning Mechanism.

# Annex 3:  Community-Based Adaptation Programme Country-Level Toolkit

## 1.  INTRODUCTION

1.  This annex is aimed at NCs who will be responsible for overseeing the implementation of CBA activities in each country.  Taking a chronological approach, this guidebook details key steps including:

- country-level portfolio development,

- community-level project development,

- monitoring and evaluation activities,

- identification and distribution of lessons learned and best practices

2.  These sections are followed by more in-depth guidance on:

- the indicator frameworks that are to be used in CBA projects,

- discussion of the programme-level monitoring and evaluation structure which will be supported by the country-level details described herein

3.  Ultimately, the objective of the CBA Programme is to enhance the capacity of communities in the pilot countries to adapt to climate change including variability.  The framework described below has been created to allow the maximum level of project flexibility while ensuring good project design, strong compliance with M&E requirements. The guidance also will ensure a good return on project investments through the generation and distribution of best practices and lessons learned that will be applicable to multiple stakeholders at a variety of scales.

## 2.  PORTFOLIO DEVELOPMENT

4.  While structurally similar to the SGP and implemented through the same infrastructure, the CBA programme is different in a number of ways.  The topic of adaptation to climate change will be new to many prospective grantees, as will the monitoring and evaluation procedures.  Therefore, the CBA project is requiring a more structured approach to portfolio development, in line with its status as a pilot project, as well as the imperative to generate lessons to guide future adaptation interventions.  The following section is a chronological outline of a CBA country programme describing the steps needing to be taken at the country level, and providing a guide to the various forms and guidance documents associated with the programme.

### 1.  CBA Country Programme Strategy Development

5.  The first phase of country-level programme development for the CBA will be development of a CBA country programme strategy (CCPS) to focus on the specific needs of the CBA programme. The CCPS  should be a short, focused document which guides the development of a portfolio of projects, and represent the consensus of the country project team and relevant stakeholders on key issues such as priority sectors that are vulnerable to climate change, priority sites (for potential CBA activities), etc.  Development of the CCPS should be based on national-level assessments of vulnerability to climate change including variability, such as the national communications to the UNFCCC and the National Adaptation Programmes of Action. Furthermore, the CCPS will reflect national adaptation priorities as reflected in National Communication and NAPA documents.  It should also be based on surveys of scientific literature related to climate impacts in the country, as well as consulted expertise, likely from national hydrological and meteorological services.

6.  Each country, led by the NC and NCC, must prepare a CCPS. The CBA CPS Template and Guidelines is provided (see Attachment 1) for this purpose.  The template is intended to provide a common structure for the CCPS’s, to encourage sharp focus on the GEF SPA requirements of the CBA programme, and to encourage the prioritization of specific adaptations to ensure portfolio-wide coherence.  Where necessary, limited resources may be used to develop the CCPS, especially if there is limited expertise among the CBA country programme team in the field of climate change impacts and adaptation, and especially if the National Communications and NAPA’s present a framework that does not easily lend itself to serving as a basis for the development of a portfolio of projects. After receiving feedback from UNDP on a draft of the CCPS, the CCPS should be adopted by the NCC and guide the selection of CBA activities in that country.

7.  During the development of the CCPS, the NCs should also review the composition of the National Steering Committee (NSC) for appropriate expertise in climate change adaptation.  Should appropriate expertise be lacking, one or more new members should be added for this purpose to help guide the committee in screening project concepts and proposals.  Country programmes may especially consider incorporating expertise from the climate related sectors which will be focused on, as well as national hydrological and meteorological services.

- Outcome:  Completed Country Programme Strategy

- Outcome:  Modification of the NSC into the CBA NCC

### 2.  Initial National CBA Capacity Building Phase

8.  The programme development phase commences upon adoption of the CCPS, beginning with initial CBA capacity building activities.  Since the CBA is a new programme it is anticipated that many of the prospective grantees may be both unfamiliar with climate change adaptation and/or new to the indicator framework that is required of CBA projects.  Following the global level inception meeting, and completion of the CPS, CBA countries are encouraged to conduct their own national-level inception workshops and other capacity building activities, targeted specifically at prospective grantees.  These activities should be advertised in the same manner that SGP calls for proposals are normally advertised, and context-appropriate mechanisms should be put in place by the NC to limit participation to NGOs/CBOs with potential capacity to implement CBA projects.

9.  The purpose of the country level inception meeting is twofold.  The first is to build the capacity of potential grantees to develop successful CBA concepts and proposals within CPS and global frameworks, and to familiarize them with the requirements of the CBA monitoring and evaluation systems.  These include description of the Vulnerability Reduction Assessment (VRA), as well as to provide an overview of the SGP Impact Assessment System (IAS) requirements, both of which CBA projects must fulfil.  The second is to encourage grantees to network with one another, developing project concepts that support one another and work synergistically to achieve the objective elaborated in the CCPS.

10.  Project concept development materials (discussed below) should be distributed and explained at the events, and relationships between prospective grantees and the country CBA team should be developed at this stage, to ensure that prospective grantees are able to access technical assistance in proposal development from the CBA country team.  Prospective grantees should also be encouraged to network among themselves to ensure a high degree of complimentarity among projects.

11.  The inception meeting could also serve as a forum to obtain consensus on the CCPS from a wider group of stakeholders. Where prospective grantees have high degrees of experience in NRM, based on local ecological, scientific, or agro-technical knowledge, perspectives and information may be shared during initial workshops that may potentially justify minor revisions of the CCPS.  This will be permitted, provided that CCPSs do not stray from GEF or SPA criteria.

- Outcome:  Prospective grantees with the capacity to develop fundable CBA proposals

- Outcome:  Prospective grantees have a basic understanding of CBA monitoring and evaluation systems and project development requirements

- Outcome:  NGO/CBO networks will work together to develop project concepts that collaborate to achieve the CCPS objective and outcomes

### 3.  Project Concept Development

12.  Upon completion of the CBA capacity building activities, interested NGOs/CBOs will develop and submit project concepts.  Project concepts should succinctly lay out the framework for the project based upon guidance in the CBA Project Concept Template. Proposals should be based on consultations with local community stakeholders.  They should include a tentative budget for proposed projects, as well as a more detailed description of project planning and development activities, with an attached detailed budget for a small (<$2000) grant for the planning phase.  Co-financing on 1-1 ratio should also be secured at this stage.

- Outcome:  Within 8 months of inception, at least 30 project concepts have been developed and submitted to the national coordinator for NCC review.

### 4.  Project Concept Review

13.  Evaluation of submitted project concepts is one of the key tasks of the NCC.  It is envisioned that the majority of approved project concepts will proceed to full project proposals and then to implementation.  This makes rigorous scrutiny of project concepts especially important, to ensure compliance with global and local criteria, to ensure project feasibility, to ensure the appropriateness of the proposed budget, and to ensure congruence with other key factors as defined in the CCPS.

14.  The NCC should approve initial proposals based on guidance in the CBA Review form.  The NCC may choose to grant provisional approval pending changes in project design where appropriate, or accept or reject concepts straightaway.  Each CBA country should have a portfolio of 3-4 projects approved and moving towards implementation within the first year.

15.  The attached “CBA Concept Review Form” has been prepared to help guide NCC members during the approval process for the CBA programme.

- Outcome:  initial project concepts approved and moving toward implementation

### 5.  Project Planning and Baseline Measurement Phase

16.  NGOs/CBOs with approved concepts will receive small planning grants (<$2000) to be used for those activities that are necessary to implement the requisite CBA M&E system, to conduct participatory project design and baseline indicator measurement activities with the target community, and to assist with the development of the full project proposal.  Consistent with the SGP mechanism, monies for these planning grants will be deducted from the overall project budget.

17.  Baseline M&E is the first focus of the planning phase.  Measurement of the baseline VRA (section 2: “A Users Guide to the Vulnerability Reduction Assessment”) is a required component of the full project proposal as it serves as the key baseline indicator for M&E in the context of adaptation projects.  The NC will build the capacity of the grantees to measure VRA as necessary during this phase.  Adoption of specific SGP Impact Assessment (IAS) indicators, for measuring global benefits, is another key requirement at this stage.  An appropriate fraction of total project funds should be allocated for M&E.

18.  Consultation with local stakeholders is the second focus of the planning phase.  In line with the CBA’s approach of ensuring project success through participatory design, the target communities are to play a strong role in the design of the project, as well as the design and implementation of the project-scale M&E framework.  It is important to focus these meetings on the elements of the community that are most vulnerable to the climate risk in question (i.e.: women, the poor, practitioners of certain sorts of livelihoods, etc).  The planning grant will support the grantee in organizing and facilitating a meeting with the target community, during which VRA indicators will also be measured and IAS indicators adopted (see section 2: “A Users Guide to the Vulnerability Reduction Assessment”).

19.  Drafting of the full project proposal is the final element of the planning phase.  Generally this will not require any funds, but in some instances small amounts will be required for research, outside expertise, or other costs. The attached “CBA Full Proposal Template” must be used.  The proposal will be significantly influenced by the data collected on the H-forms, (described below in the “Users Guide,” section 2), which will be saved to serve as an archive of project data to be drawn upon later for inclusion into the CBA website and compilation of lessons learned.

- Outcome:  Prospective grantees with capacity to implement CBA M&E procedures

- Outcome:  Baseline VRA indicators measured at all of the prospective project sites

- Outcome:  Full project proposals drafted

### 6.  Full Proposal Review

20.  The purpose of the NCC full proposal review is quite different from the purpose of the concept review.  As all of the prospective grantees should have had adequate time and guidance to develop strong project proposals based on approved project concepts, the purpose of the second review is to give the NCC (as well as UNDP) a chance to offer comments and suggestions on various aspects of the proposals before project implementation.   The attached “Full Proposal Review Form” provides guidance to NCC members as they are evaluating the submissions.  Full proposals should describe the mechanics of the project and give details of the measures to be implemented – all of which are aspects of the project that will have been developed with local stakeholders during the planning phase of the projects.

21.  Ideally, all proposals will be approved, either immediately upon initial review, or upon modifications of the proposal based on NCC comments.  Approved proposals should include baseline VRA scores, and should also indicate which IAS indicators will be adopted.  These data, along with brief project descriptions, should be immediately entered into the CBA database.  Note that new elements have been added to the SGP database to monitor VRA outcomes, and that funding disbursements to country programmes will be linked to successful data entry and management.  Co-financing must also be secured prior to implementation.

- Outcome:  NCC meeting reviews and approves projects, or sends them back for revision.  Successful proposals sent to UNDP for review.

- Outcome:  Project proposals approved, paving the way for implementation

- Outcome:  Initial entry of indicator data completed – projects displayed on CBA website

### 7.  Implementation, progress reporting, and ongoing M&E

Upon successful review of full proposals, funds will then be transferred to successful grantees, and implementation of the measures described in the proposals will begin.  Funds will be allocated in four separate disbursements:

- 30% at project inception

- 30% at a one-third interval

- 30% at a two-thirds interval

- 10% at project completion

22.  At each disbursement interval, grantees will be required to prepare a short progress report, including new measurements of VRA and IAS indicators (using the attached “CBA Progress Report” template).  These reports should highlight project accomplishments, setbacks and other notable events, and give brief descriptions of the background and methods behind the indicator results.  Note that VRA data must only be collected once between project inception and conclusion – if VRA measurements are not included in the first interval, they must be included in the second.  These reports should be quite brief, in order to avoid overburdening the grantees with M&E activities, and shifting the project focus away from project activities.

23.  As with the global level, disbursement of funds will be contingent on adequate progress reporting at the project level as well.  The CBA staff person described above may be made available to assist with these reporting requirements, which include community meetings for the collection of VRA data.  Again, immediately on collecting indicator data, the CBA database should be updated with this information.

- Outcome:  Approved projects under implementation, and meeting programmatic M&E requirements

- Outcome:  CBA project entries in the CBA database are continually updated

### 8.  Final Project Review

24.  As the project nears completion, a separate process is required for the disbursement of the final 10% of project funds.  The 10% is intended to finish the implementation of the project and implement relevant mechanisms to ensure project sustainability and generation of lessons learned.  The reporting requirements for the final disbursement include the budget reporting required during the previous reports, but also an analysis of lessons learned.  The “CBA Final Grantee Report and Lessons Learned Template” will provide structure for these reports.

- Outcome:  Projects concluded, and lessons learned from project experiences elaborated and submitted to NCs for wider dissemination

- Outcome:  Completed lessons learned templates submitted to UNDP for inclusion into the Adaptation Learning Mechanism (ALM)

- Outcome:  As with other phases of project reporting, indicator measurement results will be incorporated into the CBA database

### 9.  Programme Conclusion

25.  As CBA projects begin to reach conclusion for this initial 5-year pilot phase of CBA, NCs should begin to compile lessons learned, begin to aggregate indicator data, and begin to prepare and disseminate lessons learned to relevant stakeholders.  Especially successful projects should be highlighted to UNDP for inclusion in a publication of CBA lessons learned, to be developed around this time.

26.  NCs should also begin to plan strategies – in consultation with partners in government and other stakeholders – for integrating lessons learned from CBA projects into national or regional policy.  Especially successful cases with potentially useful lessons potentially applicable in cross-border context should also be identified for discussion at the CBA project conclusion meeting.

- Outcome:  IAS and VRA indicators aggregated at the country level

- Outcome:  Case study candidates identified and transmitted to UNDP for potential publication

- Outcome:  Lessons learned at the national level identified and transmitted to national and international stakeholders, with resultant policy change in relevant sectors

## II.  A USERS GUIDE TO THE VULNERABILITY REDUCTION ASSESSMENT

27.  The Vulnerability Reduction Assessment (VRA) forms a cornerstone of the CBA programme’s monitoring and evaluation activities.  It is designed to measure the changing vulnerabilities of communities to climate change including variability, and to be comparable across vastly different projects, regions, and contexts, making it possible to determine if the programme is successful or unsuccessful.  The VRA is complimented by the SGP IAS, which measures global environmental benefits as well as livelihood and empowerment indicators.  Together they provide a complete picture of the progress of the CBA programme in achieving its goals of enhancing adaptive capacity, and improving the resilience of ecosystems providing global environmental benefits in GEF focal areas.

### 1.  Community-level Awareness Raising

28.  VRA meetings will be preceded by awareness raising activities for the project’s target stakeholder community, establishing a scientifically grounded consensus as to the character of established and ongoing climate variability, as well as developing climate trends.  These activities should also focus on impacts from climate variability and change.  This will serve as the basis for VRA discussions, establishing an objective baseline of vulnerability, giving context to the VRA, and establishing the context necessary for the VRA discussions.  These activities will normally take place as the first part of the first VRA stakeholder meeting, and smoothly transition into measurement of the VRA indicators.  These activities should be highly context dependent, taking into account differing levels of education, literacy, pre-existing climate knowledge, and history of climate impacts.  However, the outcome in all cases will be a stakeholder body with a clear and common understanding of the climate risks that the project will seek to address.

### 2.  The Structure of the VRA

29.  The VRA is comprised of seven indicators, based on corresponding open-ended, perception-based questions, which in turn aggregate to serve as indicators of adaptive capacity.  (The composition of the seven indicators is informed by scientific assessments of climate risk.)  Local stakeholders will answer all questions on a 1 to 10 scale, generating qualitative data to be recorded on the sides of the H-form, in addition to the simple numerical score.  A simple average is used to convert participant’s answers into a VRA score that will be comparable across CBA projects.  However, a single VRA score is not meaningful; it becomes meaningful as it is measured at the pre and post-project stages.  The key quantitative output of the VRA is the percentage change from the baseline score.  The seven VRA indicators and corresponding questions are outlined below.

| APF Step | Indicator | Sample Question | Logic |
| --- | --- | --- | --- |
| Assessing current vulnerability | 1. Vulnerability of livelihood/welfare to existing climate change and/or climate variability. | How severe is the present impact of (climate risk) on your (climate-sensitive livelihood or welfare)? Example: How severe is the present impact of drought on farming in your community? (The choice of “drought” and “farming” would have already been dictated by the development of the project concept in this example). | Addresses present climate-related development issues – often the main climate concern of the community. Applicable to climate variability and/or climate change (depending on specific risk and community context). Prepares community for following questions that are specific to anthropogenic climate change by grounding that discussion in a framework that relates it to present impacts. |
| Assessing current vulnerability | 2. Efficacy of coping mechanisms in the face of current climate change/climate variability risks. | How effective are your mechanisms for dealing with (climate risk) presently? Example: What does the community currently do to limit the damage caused by cyclones, and how effective are these measures offsetting damage and reducing mortality? | During the first VRA meeting, this question will describes baseline adaptation to climate variability. During subsequent meetings, it will assess progress against that baseline. Applicable to climate variability and/or climate change (depending on specific risk and community context). As above, grounds community in present practices, preparing them to think about how changing conditions might impact those practices. |
| Assessing future climate risks | 3. Vulnerability of livelihood/welfare to developing climate change risks.* *Climate risks as based on country strategies, which in turn are based on National Communications and NAPAs | How severe would the impacts of (climate change risk be on (climate-sensitive livelihood or welfare)? Example: How severe would the impact of doubled frequency of meningitis epidemic years be on the health of your community? | Once present context of variability has been discussed, this question focuses the community on their perceptions of likely impacts of climate change. This question is based on “likely” impacts on sectors identified in project target, which in turn are based on CCPS. Allows the community to begin to consider long-term viability of livelihood practices in the face of climate change, leading to the following question. |
| Assessing future climate risks | 4. Ability of the community to respond to developing climate change risks. | To what degree is the community prepared to address (climate change risk), through (project intervention and current coping mechanisms) without a diminution in livelihood or wellbeing? Example: Will the community be able to address doubled soil salinity without a decrease in livelihoods or wellbeing? | This question compliments the previous one by focusing the community on potential actions to respond to CC. During the first VRA meeting, this question will measure baseline adaptive capacity. During subsequent VRA meetings, as answers to this question improve, this question measures progress against that baseline, influenced by the project intervention. |
| Formulating an adaptation strategy | 5. Magnitude of barriers (institutional, policy, technological, financial, etc) barriers to adaptation. | What are the barriers to adaptation, and how surmountable are they? Example: What stands in the way of more widespread use of drip irrigation, and how difficult will it be to overcome these barriers? | This question will qualify the above question, and focus it onto the needs of the community in successfully achieving adaptation. This question will identify policy barriers, forming useful lessons for the country and global programmes. This question will also measure unintended consequences, unexpected setbacks, and other barriers that were not identified during the project scoping phase. |
| Continuing the adaptation process | 6. Ability and willingness of the community to sustain the project intervention | To what degree do you think that (project intervention) will continue after the project concludes? Example: Will the community be able to continue stabilizing erosive hillsides with improved grasses after the conclusion of the project? | This question measures project sustainability and ownership, essential if adaptation to long-term climate change is to be successful. |
| Continuing the adaptation process | 7. Ability and capacity of community to continue the adaptation process, and to carry it beyond the specific project focus | To what degree will the community be able to go further in decreasing their vulnerability to (climate change risk)? Example: To what degree is the community able and willing to take other measures to adapt to sea-level rise beyond the measures taken by this project? | This question measures adaptive capacity more directly than other questions, as it seeks to determine to what extent communities will continue to adapt, and to what extent they feel that they are able to do so. |

30.  The VRA will be measured at least three times over the course of the project cycle – before project activities begin, at project conclusion, and at least once in the intervening period, as part of the required interim progress reporting (see attached “CBA Progress Report”).  This allows multiple VRA scores to be taken, making it possible to measure the percentage change in their values.

31.  The VRA will be measured in stakeholder meetings required of all projects.  The meeting participants will guide the VRA as well as project design, so it is crucial that they be inclusive of all project beneficiaries, and that the composition of the meetings be explicitly identified during each exercise on the relevant reporting form (i.e., Project Proposal, Progress Report, Final Report).  Grantees should have the capacity to successfully engage communities in the VRA, which is a highly participatory process, and should show sensitivity to gender, ethnicity, livelihood, and other social dynamics among the grantees.  This is crucial, because the product of the VRA – both in terms of the quantitative index described below and in terms of the qualitative data elicited in the process – is a large amount of data which will guide project design, implementation, and eventual lessons learned.

32.  It is crucial that all VRA materials be filed and submitted to the NC at project conclusion or at any interval during implementation, for use in consolidation of lessons learned at the conclusion of the project.

### 3.  The H-form

33.  The main tool to be used in conducting the VRA is the “H-form.”  The H-form is a tool for participatory evaluation, designed to develop a numerical score for a given question, as well as qualitative information giving the reasoning behind the resultant score.  It is normally done on a large piece of paper or a flipchart, though potential modifications include individual H-forms for all participants or for groups of participants, or a single small H-form on a clipboard, used by the meeting facilitator.

Figure A3-1:  Sample blank H-form

34.  The following is a generic procedure for using the H-form:

- Sketch the H-form on a large sheet of paper or on a page of a flip chart.

- Working with the participants, define the focus of the indicator-based question based on the project focus, and write it across the top of the middle upper section.  The questions will be formulated in such a way as to be answerable on a scale of 1-10.

- Ask participants to rank their answer to the question on a scale of 1 to 10.  10 is always favourable, whereas 1 is always unfavourable.  For example, if the question is “what is the magnitude of the impact of drought on your livelihood,” then an answer of 1 would mean that drought is a very serious problem while 10 would mean that drought is not a problem.  Depending on the size of the group, time constraints, or other factors, participants should come forward and place an X on the H-form.

- Those facilitating the VRA meeting should be highly sensitive to community power dynamics and differing levels of literacy, and this methodology should be modified accordingly to ensure equal voice to all participants.

- Facilitate a group discussion in which you ask the participants for their reasons behind their scores.  On the right and left hand sides of the H-form, jot down participants reasons for their favourable and unfavourable perceptions in the fields indicated.

- Depending on the degree of agreement within the group, guide the group to arrive on a consensus score, or simply average the community responses.  This is the final score.  The choice of whether to use a consensus-based approach or a simple average should depend upon community and group dynamics, and be guided by the local experience of the NGO, who are in turn selected by the NCCs in part for their experience with community projects.

- Lastly, ask the participants how the score might be improved, recording their replies in the central lower part of the form.

Figure A3-2:  Sample filled-in H-form

35.  While the numerical values are the important output of the H-form for the calculation of the VRA, the qualitative information recorded on the H-form provides an important record of stakeholder perspectives and opinions.  These data should guide project design and serve as a building block for project reporting and development of case studies and lessons learned.

### 4.  Calculating the Final VRA Score, Measuring Percentage Change

36.  The final VRA score from any one VRA meeting is simply the average of the scores of the seven questions.  In itself, the score is meaningless, as two different communities with objectively identical adaptive capacities might arrive at different scores based on the numbers chosen.  Therefore, the final VRA scores – upon which programme-wide M&E will rely – will be comprised of a percentage change from an initial VRA score with a subsequent measurement.  This quantity will be automatically calculated by the CBA database.

37.  Thus, as adaptive capacity increases through project interventions, VRA index scores are expected to increase.  By converting the difference between baseline and subsequent scores into a percentage, a VRA percentage score is arrived upon.

### 5.  The SGP Impact Assessment System and the SPA Criteria

38.  CBA projects will generate global environmental benefits but will also work to ensure that those benefits are resilient to climate change including variability.  Provision of global environmental benefits is expected to be supported via co-financing, while resilience-building activities are to be funded from the CBA programme, and in turn through the SPA.

39.  This requirement will be monitored separately from the VRA, as it has less to do with community perceptions of their own adaptive capacity than it does with more objective criteria.  The CBA will use the SGP IAS, which requires that each project adopt one or more indicators from one or more focal areas, plus indicators for livelihood and empowerment.  The only different aspect of IAS M&E for CBA projects will be in the METHODS and DESCRIPTION fields in the database.  It is expected that all CBA projects will describe within the database – and by extension on the CBA website – how the global environmental benefits achieved will be resilient to climate change including variability.  These indicator results and descriptions should support the “Project Description” in the database, which should also describe how GEBs achieved will be resilient to climate change including variability.

40.  Choice of appropriate indicators will occur with the initial VRA meeting at project inception, and be based on best fit with the focus of the project.  Measurements of indicators will be expected at the same time as subsequent VRA indicators are measured – with progress reports and at project conclusion.  Due to the design of the IAS, baseline indicator measurements are not possible.

## III.  ATTACHMENTS:

Country-level Guidelines

Attachment 1:  CBA Country Programme Strategy Template and Guidelines

Concept Documents

Attachment 2:  CBA Project Concept Template and Planning Grant Application

Attachment 3:  CBA Concept Review Form

Full Proposal Documents

Attachment 4:  CBA Full Proposal Template and Guidelines

Attachment 5:  CBA Full Proposal Review Form

Reporting Forms

Attachment 6:  CBA Project Progress Report

Attachment 7:  CBA Project Final Report and Lessons Learned Template

### Attachment 1:  CBA Country Programme Strategy Template and Guidelines

CBA Country Programme Strategy Template and Guidelines

Please use this template to construct an addendum to the SGP CPS, to focus on the CBA programme.  For guidance, please refer to the template guidelines below.

Bangladesh

- Overall CBA Country Programme Strategy (CCPS)

Summary:  include a short summary of the CCPS here

- Objectives and Impact Indicators:  Brief statement of objectives, and impacts indicators to be adopted by the country-level CBA programme.

Briefly state the objective(s) of the country CBA programme, and expected impact indicators.  One or two objectives should be adopted, and impact indicators chosen should correspond to each of those objectives.  Objectives and impact indicators should be chosen from the “menu” of objectives and impact indicators developed for the UNDP-GEF Adaptation portfolio in Thematic Area 6:  Natural Resources.  Table 1 summarizes these objectives and indicators.  Please see the UNDP-GEF adaptation website (www.undp.org/gef/adaptaiton) for the latest version of these indicators.  These indicators will be adopted for the national CBA programme, and will be achieved by supporting community projects.  Community projects will have a separate indicator system.

- Sectoral Focus:  Description of the sector(s) to be targeted by the CBA programme.

Targeted sector(s) should reflect national adaptation priorities.  These might be reflected in the National Communications to the UNFCCC, National Adaptation Programmes of Action, or in other relevant documents.  Choice of sector should also be compatible with country priorities listed in the CP/GCF/RCF.

Not all vulnerable sectors need be targeted for the purposes of the CBA programme.  The choice of sectors to be targeted represents a strategic and priority choice, to be made based on fit with other CBA criteria, as well as consultations with relevant stakeholders.

- Vulnerability Assessment:  Description of the vulnerability of the targeted sector(s) to climate change including variability.

Briefly describe threats to the chosen sector(s) – that are being or will be caused or significantly exacerbated by climate change including variability.  Note that GEF SPA funding is intended to improve the resilience of ecosystems to climate change including variability.  Therefore, threats to the sector involved must involve threats to the ecosystem upon which the sector is based.  Threats should be based on scientific impact assessments, such as National Communications to the UNFCCC, NAPAs, academic literature, or consulted expertise.

- Baseline-additionality reasoning:  Describe the current pressures to the target sector from non-climate threats, and the anticipated climate change risks.

Describe the current and anticipated non-climate change pressures to the target sector (focusing on the ecosystems upon which the sector relies, and pressures thereto).  Differentiate these non-climate change pressures from those emanating from climate change.  This element of the CBA country programme strategy is crucial, in that it defines what problems or components of problems will be eligible to be addressed by CBA projects.  CBA funding may only be released to projects where they address threats to ecosystems/communities that are driven by climate change, rather than baseline challenges.

- Focal Area(s):  Description of the GEF focal areas in which these strategies will deliver global environmental benefits, and a discussion of how these benefits will be made resilient to climate change.

CBA projects must deliver global environmental benefits in one or more GEF focal areas, and these benefits must be made resilient to climate change including variability.  Identify a focal area that CBA activities will focus upon, and describe potential risks to the sustainability of the global environmental benefits within this focal area that stem from climate change including variability.  For example, climate change may threaten sustainable land management practices, globally important biodiversity, or the viability of indigenous biodiversity.  All focal areas are eligible, but threats stemming from climate change to those focal area GEBs must be identified, to be mitigated by community projects.

Please only provide a rough sketch of country-level programme guidelines, allowing a very flexible range of community approaches to the country-level guidelines.  Note that all projects must improve natural resource management practices and/or improve ecosystem resilience in the face of climate change including variability.

- Local Priorities:  In addition to addressing the above requirements, description of additional local priorities that will guide project selection.

Specify any in-country priorities that will compliment global CBA criteria that will be used to guide project selection and prioritization, such as involvement of indigenous groups, women, incorporation of locally-specific financial considerations, consideration of local ecological knowledge, etc.

- Geographic Focus:  Description of the geographic region(s) of the country in which CBA activities will be focused, and how the selected region(s) aligns with sector specific vulnerability to climate change and other CBA requirements.

CBA projects must be focused in specific geographic areas where both adaptation and global environmental benefit requirements can be met simultaneously through NRM or ecosystem-focused projects.  In addition, CBA projects should have the potential to generate lessons to national stakeholders, so the region chosen should be representative of a significant portion of the country.  Lastly, issues of practicality should inform the siting of CBA activities, i.e. security, accessibility, etc.  Please provide a simple sketch, bounding the CBA area over a country map.  See figure 1 below for guidance.

- Community Project Typologies:  Description of the specific activities to be undertaken in the targeted sector(s) and explanation of how they contribute to the objective(s) of the CCPS.

Describe the types of community projects that will be funded to achieve reductions in vulnerability/increases in adaptive capacity in the targeted sector(s).  This should not be overly prescriptive, but should give a sense of the sorts of projects that will be compatible with the CCPS.  Examples of eligible sorts of projects should be provided, and should include a description of how they might address long-term climate change, and its effects on communities through the ecosystems upon which they rely.

- Policy Strategy:  Description of the strategy to be employed to involve and disseminate lessons learned to local authorities and national government.

The CBA national programme should aim to influence policy (on climate change risk management) based on the experiences of the community projects to prompt new policies or policy changes.  Describe the strategies to be used at the country level to involve government stakeholders and transmit best practices and other lessons identified by the CBA project into national policy.

- Development of the CBA team

- NCC Formulation:  Description of how the NCC has been or will be constituted.

The NCC consists of the SGP NSC, with one or more members added to provide expertise in climate change risk management if this expertise is not already present.  The NCC should also reflect stakeholders in climate change adaptation processes.  One of these NCC members should be a senior policymaker in a sector related to adaptation.  Inclusion of a representative of the national hydrological and meteorological services is also encouraged.  Describe pre-existing NSC expertise in adaptation, and/or who will be added to the NCC to meet the above requirements.

- Identification and Capacity Building of Potential NGO/CBO grantees

- NGO/CBO Identification: Description of the NGOs/CBOs to be engaged as partners in the CBA programme.

NGOs/CBOs should be selected to participate in the CBA based on their ability deliver community projects that fit within the country programme strategy.  I.e.: they must operate within the geographic focus of the CBA, they must be able to work with the sector targeted by the CBA, etc.  Please provide a short list of eligible NGOs/CBOs, and/or describe strategies to be used in recruiting them.

- NGO Capacity Building:  Description of CBA capacity building and networking activities for partnering NGOs/CBOs.

Shortly after the country programme strategy is completed, NGOs/CBOs should be engaged in capacity building activities related to the CBA.  The purpose of these activities should be to help the NGOs/CBOs to understand the requirements of the CBA programme, as well as the focus of national CBA activities (by targeted sector).  Outcomes should include improved understanding of project requirements, capacity for successful proposal writing, and introduction to CBA-specific M&E requirements (see M&E framework).

| TA6. NATURAL RESOURCES |
| --- |
| GOAL: Loss of natural resources and associated damage to livelihoods, ecosystems and economy reduced. cf. MDG Goal 7, Target 9: Integrate the principles of sustainable development into country policies and programmes; reverse loss of environmental resources |
| Objectives | Impact Indicators | Outcomes (examples) | Outcome Indicators (examples) |
| Exposure: Dependency on natural resources at risk as a result of climate change reduced. Vulnerability: Resilience of natural resources and livelihoods sensitive to climate change impacts enhanced. Adaptive Capacity: Institutional capacity to manage natural resources sustainably in the face of climate change enhanced. | Proportion of population heavily dependent on natural resources potentially threatened by climate change. Rate of loss of natural resource base for livelihoods determined to be negatively impacted by climate change. 2.1) VRA based on interviews with members of vulnerable communities. Livelihoods options better suited to climate change available to target community. 3.1) VRA based on information gathered from key stakeholders. VRA based on information gathered from policymakers and planners. | Livelihoods that reduce or remove dependence on threatened natural resources developed and piloted. Stresses on resources demonstrated to be at risk from climate change reduced. Sustainable resource management developed through new institutional frameworks and regulations. Information on potential long-term changes in climate and impacts on natural resources incorporated into resource management policies. | Awareness of potential impacts of climate change on natural resources in their countries/regions: QBS of resource managers/planners. Number of people relying on resources at risk to climate change impacts. Number of pilots of alternative livelihood activities to threatened resources/area or population participating. |

### Attachment 2:  CBA Project Concept Template and Planning Grant Application

CBA Project Concept Template and Planning Grant Application

Lines highlighted in grey should be adapted to the country context

OVERVIEW

1.  Preparation and submission of a Concept Paper is the first step in the application process for Community-Based Adaptation Programme (CBA) support.  A Concept Paper is a brief description of the idea for the project, which is reviewed by the CBA National Coordinator.  The National Coordinator can then discuss the idea with the proposing organization and others, and can advise you whether or not the idea can be considered for the CBA.

2.  The Concept Paper is intended to begin a dialogue between project proponents and the CBA programme to clarify and refine project ideas, before the investment by the proponent of substantial time and resources into fully elaborated proposal development.  In the case of successful concepts, the CBA will be able to provide small amounts of financial support after a Concept Paper has been accepted.  These Planning Grants are intended to help turn a concept into a full proposal, and can be used to fund community consultations and processes, consultants if needed, and other costs of project development.

3.  If you have any questions about the eligibility of your idea for CBA support, or about the preparation of the Concept Paper or Project Proposal, do not hesitate to contact the National Coordinator, Community-Based Adaptation Programme.

INSTRUCTIONS

4.  The concept should be written in straightforward narrative form.  It must be typed, single or double spaced, on one side of not more than two sheets, not including cover sheet, budget or planning grant application.  Any charts or diagrams will be counted as part of the page limit.

5.  Please be sure that the paper is easily readable.  Each page should have the name of the project on it, along with a page number and date.

6.  Submit one original of the Concept Paper to the National Coordinator.  Do not bind the document.  Keep a copy of your paper for your own records, as the one you submit may not be returned.

7.  In preparing the Concept Paper, you should follow the format provided below, briefly addressing the key factors impacting CBA eligibility: project purpose and intended adaptation, environmental and livelihood impacts, relevance to country and global CBA strategies, community participation, proponent capacity.

PROJECT CONCEPT FORMAT

Approx. 2 pages

General Information:

| Project title: | Name of Project |
| --- | --- |
| Project site: | The location of project site (as specific as possible) |
| Proponent/s: | Name of organization, address, email, phone, fax, and contact person/s |
| Project Partners: | List those who will provide other funding (cash or in-kind) for the project |
| Other Cooperating Agencies (if any): | List of organizations and/or agencies, private or government that you will work with to implement project. |
| Total Project Cost: | Full amount that you are using to implement the Project (US Dollars) |
| Amount Requested for funding: | Amount that you are requesting from the CBA Programme (US Dollars) |
| Local Counterpart: | How much will be provided by yourself and others besides CBA funding: Cash Amount:_________ In-Kind Amount: __________ |
| Project Duration | (Project lifespan as envisioned by the proponent) |

Project Description:

Rationale of the Project (~1/2 Page):

- Describe the objective of the proposed project, focusing on specific measures to improve adaptive capacity (the project objective should align with the overall objective of the CBA programme)

- Describe the context of the target community (livelihood, ethnicity, gender, geography, ecosystems, local government, etc)

- Describe the climate risks that this project seeks to address (i.e.: changing/variable climate parameters and their impacts)

Brief Project Description (1/2-1 page)

- Briefly state the overall project objective, and describe the activities to be used to support the objective

- Describe the benefits to local communities that the project will achieve

- Describe how the proposed project will improve ecosystem resilience to climate change including variability, or how the project will build capacity to implement natural resource management practices that will do the same

- Identify the GEF Operation programme that global environmental benefits will be achieved under

- Indicate real or potential barriers to project success, and actions that will be taken to remove these barriers, as applicable

NGO/CBO Background (~1/2 Page)

- Describe your organization’s mission, history, membership, general activities, and successful experiences

- Describe experience in climate adaptation of or similar community-based risk-reduction activities, if any

- Describe commitment for co-activities to compliment the proposed project activities

- Describe community/beneficiary participation in developing this concept paper

- Describe your experience in developing proposals and implementing projects funded by outside donors.  If none, describe your organization’s capacities in this regard

- Describe the organization’s total budget and primary sources of funding

Project Cost

- What is your best estimate of what the project will cost?

- What other potential or committed sources of support besides the CBA programme have been identified?  Include monetary support, and in-kind support (donated goods, services or labor).

- Tentatively indicate where funds are to be requested from the CBA, and where they are to be requested from other donors.  Keep in mind the following:

- CBA funding can only go to activities that are directly related to safeguarding global environmental benefits in GEF focal areas by increasing ecosystem resilience or improving natural resource management practices in the face of climate change including variability

- Co-financing is expected from all projects, both cash and in-kind, and will support the generation of global environmental benefits, as well as baseline community development needs

Attachments: 1) Sketch/map indicating location of the project. 2) Copy of Charter OR official letter from local government certifying your organization as a legitimate Community-Based Organization if not chartered.

Planning Grant Application:

Approved CBA concepts will be issued small planning grants (<$2000) to undertake baseline indicator measurements, and to conduct participatory project planning activities with target communities, fleshing out the loose project architecture described above.  The planning grant will also support the development of the full project proposal.  In general, the planning phase is expected to take less than 12 weeks, ideally averaging around 6 weeks.  Only in exceptional circumstances will grantees be given a four week extension by the NCC.

Planning Phase Description (less than 1 page)

- Describe the activities to be undertaken during the planning phase to collect baseline VRA data and co-design the project with the target community

- Describe the activities to be undertaken during the planning phase in support of the drafting of the full proposal

- Describe any outside technical assistance necessary

- Develop an indicative budget for activities to be completed during the planning phase.  Note that these funds will be subtracted from the overall grant amount awarded by the CBA.  Use the embedded spreadsheet if possible, or alternatively draft a similar table.

Table 1:  Budget worksheet for the planning phase.  If possible use the embedded excel spreadsheet, or alternatively draft a similar table

Banking information

- Indicate your bank’s name, as well as bank transfer information.

### Attachment 3:  CBA Concept Review Form

CBA Concept Review Form

To be filled out by the National Coordination Committee.  Answers should represent consensus positions to the extent possible.

Name of Project: __________________________

Name of Proponent: ________________________

Total Project Cost:

Total Requesting from CBA Programme:

1. Fit to Global Criteria:

UNDP-GEF Adaptation Thematic Area(s) (NC Fill out):

GEF Focal Area (NC Fill out):

GEF Operational Programme (NC Fill out):

- Is the concept eligible for funding under the CBA?

  - Is the concept compatible with the CBA country programme strategy?

  - Does the project address a legitimate risk stemming from climate change including variability?

  - Does the project strengthen ecosystem resilience to climate change including variability, or improve natural resource management practices in the face of climate change including variability?

  - Will the project achieve global environmental benefits under a GEF focal area?

  - Will those global environmental benefits be made resilient to climate change including variability?

- Does the risk present a serious problem for the community and/or for the ecosystem, and does the project address that problem in a viable manner?

2. Methodology and Rationale:

- Do the identified objective, outcomes, and supporting activities make sense and do they follow from one another?  Is the objective clear and support the CCPS? Are activities doable, measurable and support the outcomes?

3. Budget:

- Is the tentative total amount requested within the allowable range?

- Does the tentative budget effectively distinguish between CBA-fundable adaptation activities and those that must be supported through co-financing?

- Is the tentative budget cost effective and can it support the activities?

4. Proponent Capacity:

- Is proponent a legitimate NGO/CBO?

- Does the proponent have experience in successful community activities, or demonstrate the capacity to be successful?  Does the proponent have the co-activities and requisite professional time to implement the project successfully?

5.  Planning Phase:

- Do proposed planning activities support the rest of the project concept?

- Does the planning budget cost effective and support the activities?

6. Other Positive aspects of Project:

7. Other Negative aspects of Project:

8. Recommendation of the Committee:

_____ Reject

_____ Approve

_____Approve with Conditions (improvement)

State Conditions:

Signature:  ________________________		Date: ___________________

Spokesperson

National Coordination Committee

### Attachment 4:   CBA Full Proposal Template and Guidelines

CBA Full Proposal Template and Guidelines

Items highlighted in grey should be adapted to the national context

See guidelines at end of document for instructions for completing this proposal

PROPOSAL SUMMARY

- Project Title:  (should reflect nature of activities)

- Project Site:  (give exact location of project – region, village, etc)

- Proponent:  (name of NGO/CBO, brief background information on the organization)

- Authorized Representative:  (name and title of two or more people authorized to represent NGO in any transaction)

- Cooperating Organizations:  (name and contact information for project partners of the proponent)

- Start-Up Date:  (target date for project commencement)

- Project Period:  (duration of project)

- Total Project Cost:  (total cost, including CBA funding and co-financing)

- Amount Requested:  (amount requested from CBA programme)

- Brief Project Description (to become publicly accessible on the CBA website on project approval.  1-2 paragraphs.)

1.0 RATIONALE

Approx 2 pages

  - Community Context

1.2 	Climate Context

1.3 	Impacts Context

1.4  	Risks and Barriers

1.5	Project Approach

1.6	Initial VRA Analysis

2.0 COMMUNITY OWNERSHIP

Approx 2 Pages

2.1	Project Formulation

2.2	Project Implementation

2.3	Phase-Out Mechanism, Sustainability

3.0 PROPONENT DESCRIPTION

Approx 1 Page

3.1 	Organization’s background and capacity

4.0 PROJECT DESCRIPTION

4.1	Objective, Outcomes, Planned Activities and Tasks:

- Use the table format below, or an outline format.

| Project Objective: Statement to reflect the overall aim that is to be achieved. |
| --- |
| Outcome 1.0: Component of the project that if met, contributes to the Project Objective. |  |  |
|  | Activity 1.1: An activity that is to be undertaken to fulfill the outcome 1.0. |  |  |
|  |  | Task 1.1.1 – What you will do as part of the activity 1.1 |  |  |
|  |  | Task 1.1.2 – What you also will do as part of the activity 1.1 |  |  |
|  | Activity 1.2: Another activity that fulfill outcome 1.0 but different from Activity 1.1 |  |  |
|  |  | Task 1.2.1 – A task that is part of Activity 1.2 |  |  |
|  |  | Task 1.2.2 – Another task that is part of Activity 1.2 |  |  |
| Example Outcome 2.0: At least 3 communities earning income from Protected Area |  |  |
|  | Activity 2.1 Training of tour guides |  |  |
|  |  | Task 2.1.1 – Work with USP to develop training course |  |  |
|  |  | Task 2.1.2 – Identify 4 tour guide trainees from communities… |  |  |
|  |  | Task 2.1.3 – Undertake training course… |  |  |

4.2	Timetable

- Use the spreadsheet embedded below, or alternatively draft a similar table.  (Be sure to delete the example timeframe).

Sections 4.3 – 4.5 Approx 1.5 Pages

4.3 	Monitoring and Evaluation

4.4	Project Management

4.4.1	Management Structures

4.4.2	Relationship and Responsibilities of Proponent and Project Partners

5.0 PROJECT COSTS AND OTHER SOURCES OF FUNDING

5.1	Total Project Cost and Amount Requested:

6.0 EXHIBITS/ATTACHMENTS

6.1	Mandatory

- Copy of letter of approval of your project concept.

- Photocopy of charter and by-laws OR if not chartered, letter from state or local government certifying proponent as a legitimate community-based organization.

- Location map (Project Site).  This may be a very rough sketch over a country map.

- Latest audited financial statements if any OR explanation of why no audited statement is available.

- Brief curriculum vitae or résumé of project manager/coordinator and person in charge of accounting for the funds.  Letter from a partnering organization if one will assist in accounting for funds.

- Document/letter showing proof of approved funding (if the project will use counterpart funds from other donors).

- Photographs of community project development meeting and of the project area

- The H-forms from the initial VRA assessment (or high-quality photographs of the H-forms)

6.2	Optional

a) Topical outline of training modules or other capacity building activities

b) Organizational Chart of NGO/CBO

c) Other information you think would improve your proposal

Annex:  Full Proposal Guidelines

The numbered guidelines below serve as instructions for the correspondingly numbered elements of the proposal template above.  Please use them in the development of the full project concept.

1.1	Community Context

Describe the target/beneficiary community.  Be sure to address all of the following issues, where relevant or applicable.  Also, be sure to distinguish which elements of the community will be targeted (i.e.: gender, livelihood or other groups that are particularly vulnerable).

- Number of people

- Gender and age of target population

- Ethnicity or ethnicities

- Livelihood types and economic context

- Major social dynamics, including class or other social hierarchy

Furthermore, describe community knowledge of

1.2	Climate Context

Describe the climate of the region in which the target community is located.  While this does not need to be overly scientific, it should include the following elements:

- A brief description of the seasonality of the climate, giving approximate times of year for warm/cool or rainy/dry seasons

- A brief description of when during the year particular climate risks are most acute (i.e.: September for hurricanes, July for drought, February for floods, etc).

- A description of inter-annual patterns of variability and climate impacts thereof, such as El Nino/La Nina.

- A description of likely climate changes for the region, and recent manifestations of that change if applicable.  This should be based on scientific assessments of climate change risks where possible.

1.3	Impacts Context

Describe the impacts of the climate patterns described above on people’s livelihoods.  Where possible, this should be based on scientific assessments of climate change risks and likely impacts.  These could potentially include:

- Seasonally recurring impacts

- Risks that occur in certain years, such as agricultural droughts, flood risks, and dangerous hurricanes

- Risks that occur in longer-term cycles, such as long-term drought at the decadal scale.

- Likely livelihood impacts of climate change, such as the effects of sea-level rise on water supplies, or the effects of increased temperature on important crop varieties

- A description of which segments of the community are/will be most affected and why (focusing on gender, socio-economic class, livelihood type, etc)

1.4	Risks and Barriers

It is assumed that where measures to improve adaptive capacity or reduce vulnerability are known but not implemented by the community that there are barriers to their implementation.  Describe any barriers to implementation of project measures, and how they will be removed or managed.  Differentiate between external barriers and internal barriers (for example: national policy barriers versus local awareness barriers).  Describe how the project will remove capacity constraints from key adaptation activities.

Beyond known barriers, projects may be subject to internal or external risks.  These could include sub-optimal performance of a new application of a technology, or currency fluctuations that change the economics of a project.  Describe potential risks that the project faces, and how these risks will be managed.

1.5	Project Approach

Describe how the project will facilitate community adaptation to the phenomena described above.  Keep in mind the following criteria:

- Projects must choose an applicable GEF operational programme

- Projects must choose a UNDP-GEF Adaptation Thematic Area (i.e.: water, agriculture, health, disaster management, or coastal management)

- Projects must strengthen the resilience of global environmental benefits to climate change including variability in the focal areas in which GEF works.  This means that projects must generate global environmental benefits through co-financing while making those benefits resilient through CBA funding.

  - Projects must indicate which GEF focal area they will achieve these resilience benefits under.

- Projects must do so through making ecosystems more resilient to climate change including variability, or through improving natural resource management practices in the face of climate change including variability.

- Projects must have local benefits

- Projects must fit with the criteria elaborated in the CBA country programme strategy

Projects approaches should give a description in general terms of how these criteria will be met, while meeting community priorities.  A more detailed breakdown of project activities will be required in table form in step 4.1.

In addition, describe community awareness of climate change risks.  If this awareness is absent or incomplete, describe how the awareness of local stakeholders is to be raised.  Project beneficiaries should have an understanding of present and future climate regimes, based on scientific assessments from scientific literature and/or local scientific expertise.

1.6	Initial VRA Analysis

Use the embedded spreadsheet to record the results of the initial VRA analysis, if possible.  (Double-click on the spreadsheet to make it active).  Alternatively, construct a similar table with the same information.  Using the data recorded on the sides and bottom of the H-forms and drawing on community conversation surrounding the exercise, construct a narrative that describes issues and context raised by the meeting.  Be sure to include:

- Composition of the meeting

- Major agreements/disagreements of community members with regard to different VRA indicators

- Differences in perception between different sub-groups (eg: gender, ethnicity, livelihood type, etc)

- Other contextual information brought out by the VRA process

2.1	Project Formulation

Describe how the project was formulated, both in terms of the overall concept and in terms of its components.  Describe the roles of the proponent and the role of the community, how they worked together, and where the perspective of one informed the other.

2.2	Project Implementation

Describe how the community members will be engaged continuously throughout project implementation.  Community participation is important, as it will help ensure that the project takes locally important factors into account, while helping to ensure continuity of project impacts after project conclusion.

  - Project Sustainability and Phase-out

In the context of the CBA programme, sustainability refers to the situation where the impact of the community project can continue without follow-up funding from GEF.  Describe how your project will achieve this.  First, describe how the project will conclude, and how project activities will be ultimately transferred to the local community.  Then, describe how the impact will be sustainable, focusing on the following five elements:

- Social Sustainability: investing project beneficiaries into the project, ensuring that they will carry it forward after the departure of the grantee.  How will this be done?

- Financial Sustainability:  how will project costs be met after CBA funding ceases at the end of the project period?  Consider the lifespan of any technologies delivered, as well as the ongoing maintenance costs of any interventions, and place these in the context of the local community.  The local community should be able to meet any ongoing needs.

- Ecological Sustainability: any ecosystemic interventions carried out by the project must be self-sustaining, and not produce negative environmental externalities.  If a forest is planted or a wetland restored, these ecosystems must to a large extent be able to maintain their own viability without extensive human intervention.  Also, any ecosystemic interventions must not create environmental problems elsewhere.  Examples of this could include erosion caused by the planting of a non-native tree species.

- Economic Sustainability: if a project plays a role in developing alternative livelihoods for local people, it is important to show that these will be viable over the long term

- Institutional Sustainability: if a project requires that existing institutions collaborate or interact in new ways, it becomes imperative to show how this will continue after the conclusion of project financing.  Describe the incentives for the various institutions to collaborate during the post-project period.

  - Proponent Description

Describe your organization’s mission, history, membership, management, organizational structure and current programmes.  Describe your experience working with the target community, or with similar communities.  Finally, discuss your experience and/or capacity in adaptation to climate change including variability.

Indicate the organization’s total annual budget, and attach its last audited financial statement and an organizational budget, if applicable.  Describe the financial system and procedures being used by the proponent/organization.

4.1	Objective, Outcome, Planned Activities and Tasks

Using the table format, give a detailed description of precisely what the project objective is, what outcomes will be achieved to meet this objective, what activities will support these outcomes, and what tasks will be done as part of these activities.  All outcomes should be independently measurable, whereas the objective may be more abstract.  However, the outcomes must clearly and directly support the objective.  For example, if the objective is to increase the resilience of the community to extreme storms, than acceptable outcomes might include reforestation of a certain number of hectares with mangroves, protecting another number of hectares of land from soil erosion.  Activities and tasks should provide a well thought out description of precisely how you will go about achieving your outcomes.  Lastly, the objective must be clearly aligned with the objective of the CBA Country Programme Strategy.  Contact the CBA National Coordinator for further guidance.

4.2	Timetable

Using the embedded spreadsheet, indicate when the various activities and tasks will be completed.  These should be the same activities and tasks as listed in the table above.  The timetable should be realistic, and activities should be coordinated to support one another.  Use the  icon to fill in the blocks.

4.3	Monitoring and Evaluation

VRA:  Indicate when VRA meetings will be held over the course of the project, and how they will relate to plans for attainment of specific project outcomes.  For example, are meetings planned after the completion of certain project activities?

IAS:  Indicate which Impact Assessment System (IAS) indicators will be measured by the project – one or more indicators in one or more Global Environmental Benefit focal areas and one or more each of the livelihood and empowerment indicators.  Furthermore, indicate how the chosen indicators will be measured.

Keep in mind that all projects will be required to submit progress reports to access subsequent disbursements of project funds, and these reports will require measurement of IAS AND VRA indicators.  Indicate when these reports will take place.

4.4	Project Management

4.5.1	 Describe the management structures and functions of the proponent under this project.  Who will be responsible for executing project activities, who is he/she responsible to, and who will he/she be working with?  Include the name of project manager/coordinator and attach brief resume/CV.

4.5.2	Describe the relationship of any partnering organizations, if applicable, including the responsibilities of each partner and how they will work together with proponent to achieve the project objective.  Include technical assistance required and how it will be provided.

5.1	Total Project Cost and Amount Requested

Using the embedded spreadsheet, create a detailed budget for the whole of the project, indicating CBA funding and other sources of funding, including both cash and in-kind components.  Note that the budget is an integral part of the project proposal, and forms part of the binding contract between your organization and the GEF.  The following are a number of points to keep in mind when crafting the budget:

- CBA funding can only go to activities that increase the climate resilience of global environmental benefits generated by GEF projects.  Everything else must be covered by co-financing.  However, staff, technology, and other project activities or components that support this resilience-building will be fundable by the CBA, whereas activities that generate the global environmental benefits in the first place are not.  In situations where it is impossible to disentangle the GEB-generation activities from resilience-building activities, it is recommended that those budget lines be split equally between CBA and co-financing.

- Budgets may only include items directly relating to the activities described in the proposal.  Other associated costs must be met through other channels.

- Budgeted costs must be realistic – neither too large nor too small to support project activities.  This should be based on adequate research and experience.

- The budget should include all costs associated with managing and administering the project.  In particular, be sure to include the cost of monitoring and evaluation.

- “Indirect Costs” or administrative overhead are not funded by the CBA, and should not be part of the funding request.

- Remember that when you agree to accept CBA funds you are also agreeing to be accountable for how those funds are spent, and to make available all financial relevant records.  These may be independently audited, and may become public information

- Be sure that the figures contained in the Budget Information Sheet agree with those on the Proposal Cover Sheet and the text of the proposal itself.

- Add lines to the budget sheet by right-clicking on one of the numbers, and selecting “insert.”

- Consider dividing your budget among the following categories.  In practice, many of them may overlap, though you should be sure that your budget is inclusive of all project costs.

  - Personnel/Labour

  - Admin/Operational Expense

  - Equipment/Materials

  - Training/Seminars/Workshops

  - Contracts

  - Monitoring and Evaluation

  - Other Costs

6.1, 6.2	Attachments

In addition to the required attachments, attach anything that you believe would help strengthen or clarify your proposal.  Please do not include material that is discussed in the above proposal.

### Attachment 5:  CBA Full Proposal Review Form

CBA Full Proposal Review Form

(To be filled out by each participating NCC member)

Instructions:  Please answer each question, briefly giving justification or adding brief comments.  Funding decisions should be made by the NCC based on consensus.

| Name and Number of Project: |  |
| --- | --- |
| Name of Proponent: |  |
| Total Project Cost: |  |
| Total Requesting from CBA: |  |

1. Questions:  the project proposal must satisfy all of the criteria below to be successful.  An answer of NO in any of the following questions will require that the proposal be reformulated or rejected.

a)  Does the proposal address a legitimate climate risk facing the target community?

b)  Does the proposal meet the SPA criteria?  Does the proposed project enhance the resilience of global environmental benefits in the focal areas in which GEF works?  Does it do so through measures to improve ecosystem resilience or improve natural resource management practices in the face of climate change including variability?

c) Does the project fit with the priorities laid out in the country programme strategy?

d) Has the VRA been successfully completed, with both quantitative and qualitative elements provided?

e) Have appropriate IAS indicators been chosen, and has an appropriate plan for their measurement been established?

f) Is the budget appropriate?  Does it ask for less than $50,000 for the CBA programme, and does it distinguish between CBA and co-financing activities?

g)  Does the proposal have all of the required attachments?

2.  Scorecard:  using the table below, rate each of the components of the project on a scale of 1-10.  This will yield a final score, useful in comparing projects.  This scorecard exists solely to serve as a discussion aid for helping the national coordinating committee to discuss project proposals that meet the criteria above, and require evaluation on their other merits.

| Project Proposal Evaluation Scorecard | Score 1-10 |
| --- | --- |
| 1. Project displays a good understanding of climate risks and their impacts on the target community. |  |
| 2. Project approach is logical and feasible. |  |
| 3. The project objective is clear, is likely to be achieved through measurable outcomes, which in turn are effectively supported by appropriate activities and tasks. |  |
| 4. The monitoring and evaluation system fits global criteria, and is well developed and feasible. |  |
| 4. The work plan/timetable is well thought-out and realistic. |  |
| 5. The budget is well-thought-out, realistic, inclusive of all likely costs, and within CBA guidelines. |  |
| 6. The NGO shows the capacity to implement this project successfully. |  |

Comments:

Recommended for Approval?

__ YES

__ YES, provisionally (describe requirements below)

__ NO (state why, below)

### Attachment 6:  CBA Project Progress Report

CBA Project Progress Report

AND

GRANT DISBURSEMENT REQUEST

(to be completed by NGO/CBO Grant Recipient)

Lines highlighted in yellow should be adapted to the country context

Period Covered by this Report:  _______________________________________

(Month/Year to Month/Year)

| Project Title |  |
| --- | --- |
| Name of Person prepared and submit this report |  |
| Title of Person |  |
| NGO/CBO Name (Grant Recipient) |  |
| Address and other contact information |  |
| Location of Project (Country, State, Village) |  |
| Original Project Start Date |  |
| Original Project End Date |  |
| Changes (if any) in Project Start and End dates |  |

|  | US Dollar Amount |
| --- | --- |
| 1. CBA Total Grant Amount approved for this Project |  |
| 2. Total CBA Funds received to date under this Project |  |
| 3. Total CBA Funds spent to date (take the Total from Column 4 of Table 2. Cumulative Expenditure Report. See Page 3) |  |
| 4. Balance (total CBA funds received minus total CBA funds spent (2 minus 3)) |  |
| 5. Request for next Disbursement (Disbursement is made only upon approval of Report) |  |

Project Co-financing Received:

| Source of Funds (Donor Name) | Type of Co-financing (in-kind or Cash) | Total Amount in US Dollars |
| --- | --- | --- |

_________________________________			________________________

Authorized NGO/CBO Officer Signature						Date

Project Progress Reports should contain 3 Components:

Narrative Component – Grant Recipient reports on progress in implementing activities, problems/difficulties in implementing and any additional needs to improve the project by changing duration or activities of the Project.

Financial Component – Report specifically on how much money has been spent. The report is in the form of 2 tables:

- Table 1: Detailed Expenditure and,

- Table 2: Cumulative Expenditure.  It also includes your request to make any changes to the budget

Project Photographs – photographs of any community meetings, and of project processes and progress

This Project Progress Report must be sent preferably by e-mail but can be by fax or post/hand-delivered to:

PART I. Narrative Report

(Please add as much space as needed)

A.  Project Activities Implementation:

List the activities as shown in your approved project proposal.  List indicators under each activity as shown in your original project proposal.  Describe how you implemented the activity DURING THE REPORTING PERIOD by addressing your indicators.  For activities not addressed, just write “no activity” in third column.

| Activity/Task | Describe what was done for this activity during this period |
| --- | --- |

Please provide copies of any meeting/activity report or other material such as video, article, photo, or other outputs of the project.

B.  Problems or difficulties in project implementation:

List and describe the problems or difficulties you faced in implementing your activities AND what you did to address each of these problems/difficulties.

C.  Analysis/Assessment of implementation:

State your opinion as to the success of progress in implementing your activities.  Are you able to complete your activities and do you think you can finish activities successfully and on time.  If can or cannot, state why.

D.  Additional Needs:

From your analysis, do you need additional technical assistance?  If so, describe.

Do you need to revise your activities or project duration?  If so, which activities and how much more time is required?

E.  Knowledge Management:

Please give details of mandatory subsequent measurements of IAS and VRA indicators.  Please give updated values for all numerical fields, and descriptions of context and methodology, as per the instructions in the CBA toolkit.  You may use the form below for the VRA indicators.  Include the new H-forms, or high-quality photographs/copies of them with this report.

F.  Additional Remarks:

State anything (positive or negative) you wish to bring to attention of NCC that relates to or may have an impact on the implementation of your project.

PART II.  Financial Report

(Please add as much space as you need)

Table 1: Expenditure Report.  This table lists all of your spending.  Copies of invoices and receipts must be attached to this report.  Please add as many lines as necessary.

| Date of Receipt | Receipt or Invoice Number | Description of Expenditure | Amount of Receipt/Invoice (US Dollars) |
| --- | --- | --- | --- |
|  |  | Total | (add all above) |

Table 2: Cumulative Expenditure Report

| Column 1 | Column 2 | Column 3 | Column 4 | Column 5 |
| --- | --- | --- | --- | --- |
| Budget Category | Approved Budget | Total Expenditure (this period) | Cumulative Expenditures to date | Balance remaining for category |
| Total | (add all above) | (add all above) | (add all above) | (add all above) |

Column 1 and Column 2 are taken from your approved budget.

Column 3 is taken from your Table 1 above.  It is expenditure ONLY FOR THIS PERIOD

Column 4 is total of expenditure for this period PLUS ALL PREVIOUS PERIODS under this Project.

Column 5 reflects how much you have left to spend.  Take Column 4 and subtract from Column 2.  This Column 5 SHOULD NEVER have an amount below Zero (negative balance).

Request for Budget Revision:

Indicate here if you want to get authorization for increasing any budget line and which line (s) should be decreased as a result.  Please note that Approved Budget should be maintained at the same level so BUDGET INCREASE and BUDGET DECREASE columns must be the same amount in Table 3.

Table 3:  Budget Revision

| Budget Category | Approved Budget | Budget Increase | Budget Decrease | State your Justification for the Increase |
| --- | --- | --- | --- | --- |
| Total |  |  |  |  |

### Attachment 7:  CBA Final Grantee Report and Lessons Learned Template

CBA Final Grantee Report and Lessons Learned Template

(to be completed by NGO/CBO Grant Recipient)

Lines highlighted in yellow should be adapted to the country context

| Project Title |  |
| --- | --- |
| Name of Person prepared and submit this report |  |
| Title of Person |  |
| NGO/CBO Name (Grant Recipient) |  |
| Address |  |
| Location of Project (Country, State, Village) |  |
| Actual Project Start Date |  |
| Actual Project End Date |  |

|  | US Dollar Amount |
| --- | --- |
| 1. CBA Total Grant Amount approved for this Project |  |
| 2. Total CBA Funds received under this Project |  |
| 3. Total CBA Funds spent |  |
| 4. Balance (total CBA funds received minus total CBA funds spent (2 minus 3)) |  |
| 5. Request for final Disbursement (Disbursement is made only upon approval of Report) |  |

Project Co-financing Received:

| Source of Funds (Donor Name) | Type of Co-financing (in-kind or Cash) | Total Amount in US Dollars |
| --- | --- | --- |

_________________________________					________________________

Authorized NGO/CBO Officer Signature				Date

This Project Final Report must be sent preferably by e-mail but can be by fax or post/hand-delivered to:

Project Progress Reports should contain 4 Components:

Narrative Component – Grant Recipient reports on progress in implementing activities, problems/difficulties in implementing and any additional needs to improve the project by changing duration or activities of the Project.

Financial Component – Report specifically on how much money has been spent. The report is in the form of 2 tables:

- Table 1: Detailed Expenditure and,

- Table 2: Cumulative Expenditure.  It also includes your request to make any changes to the budget

CBA Global Lessons Learned Template – for transmission of project lessons into the UNDP-GEF Adaptation learning mechanism.  Photographs required.

PART I. Narrative Report

(Please add as much space as needed)

A.  Project Objective and Outputs:

- Describe the objective, outcomes and activities that were or were not successfully completed.  Where objective, outcomes and activities were not completed, discuss why.

- List benefits realized for and by the beneficiaries during implementation.  Also include indirect benefits.

- Has the project achieved its objective(s)?

B.  Obstacles and Deficiencies in project implementation:

- If objective and outcomes were not met, describe why not and describe the principal obstacles

- Describe the deficiencies of the project (elements of the project that caused it not to work, or elements that could be designed better in the future).

C.  Assessment of Impact:

- Indicate the final VRA score in the table below:

- Indicate the percentage change from the baseline VRA score taken at the beginning of the project.

- Describe the qualitative portions of the latest VRA, focusing on community perceptions of how their vulnerability has changed

- List and describe the IAS measurements taken over the course of the project, and give one paragraph of context on each of those measurements.

D. Future Plans

- What are your plans (if any) to continue, expand or replicate activities of the project.

E.  Additional Remarks:

- State anything (positive or negative) you wish to bring to the attention of National Coordination Committee that relates to or may have an impact on the implementation of your project.

PART II.  Financial Report

(Please add as much space as you need)

Table 1: Expenditure Report.  This table lists all of your spending.  Copies of invoices and receipts must be attached to this report.  Please add as many lines as necessary.

| Date of Receipt | Receipt or Invoice Number | Description of Expenditure | Amount of Receipt/Invoice (US Dollars) |
| --- | --- | --- | --- |
|  |  | Total | (add all above) |

Table 2: Cumulative Expenditure Report

| Column 1 | Column 2 | Column 3 | Column 4 | Column 5 |
| --- | --- | --- | --- | --- |
| Budget Category | Approved Budget | Total Expenditure (this period) | Cumulative Expenditures to date | Balance remaining for category |
| Total | (add all above) | (add all above) | (add all above) | (add all above) |

Column 1 and Column 2 are taken from your approved budget.

Column 3 is taken from your Table 1 above.  It is expenditure ONLY FOR THIS PERIOD

Column 4 is total of expenditure for this period PLUS ALL PREVIOUS PERIODS under this Project.

Column 5 reflects how much you have left to spend.  Take Column 4 and subtract from Column 2.  This Column 5 SHOULD NEVER have an amount below Zero (negative balance).

Part III:  Community-Based Adaptation Global Lessons Learned Template

Instructions:  This template is an information gathering tool for knowledge management and identification of lessons learned at the global level.  Please answer the questions below, focusing on project lessons that have the potential to be useful to others interested in community-based adaptation around the world.  Please note that this template will provide much of the basis for the identification of projects to be highlighted through a publication of project case studies at the global level.

Under each of the following sections provide a short description of the approaches and methodologies that the project applied and the key lessons learned.

Please focus on main challenges, issues and good practices that other projects should be aware of:

Lessons on Methodologies:

Climate change impact and vulnerability assessment

Provide a concise description of the impact and vulnerability assessment process:  How effective was the VRA process in establishing community perceptions of risk?  Was the process clear, simple, and conducive to participatory assessment?  Were community perceptions of risk congruent with those described in the National Communication to the UNFCCC and the National Communications, and/or the CBA country programme strategy?

Assessment of adaptation measures

Provide a concise description of the approach of the NGO/CBO to the co-design of adaptation measures with the target community:  How did people’s adaptive capacity change?  How was this evinced?  How have their coping mechanisms and/or livelihoods changed?    Were community practices that worsen vulnerability identified for action?  Have project activities been tested by extreme events, and if so, how did they fare?

Partnerships

Describe the roles of any significant project partners:  how was co-financing used?  In cash?  In kind?  How did partnership bring new resources, experience, or connections to the project?

Lessons on Process:

Stakeholder Involvement

Provide a concise description of the project’s stakeholder engagement strategy:  What stakeholders were involved in the project besides local people?  How does the project identify stakeholders?  What roles did different groups of stakeholders play, and how did they interact?  At the local level, how was equity between different groups (i.e. gender, age, livelihood type) ensured?

Policy dialogue

Describe the policy components of this project:  How were local communities and CBA projects involved in influencing government policy?  Was policy change targeted at local, regional, or national government? Were there any notable outcomes or ongoing processes?

Institutional and community capacity building

Describe main approaches to capacity building for adaptation: Did local communities understand future climate threats from the outset or require training?  Did the project partners in government or other sectors require training to effectively understand community adaptation?  How have community attitudes changed through the course of the process? Have attitudes of project partners changed through the course of the process?

Tools and approaches for mainstreaming

Describe main entry points and methods for mainstreaming climate change and adaptation needs: Have lessons from this project been integrated into local, regional or national decision-making structures?  Have laws, regulations, or other policies changed to take adaptation into account?  Has this project identified priority sectors and/or specific legislative changes that it can recommend implementing in the face of climate change including variability?

Lessons on Outcomes:

Impacts – Adaptation

Describe progress on adaptation-related targets and indicators: what are the main results of the project?  Short-term impacts?  Long-term impacts?

Impacts – Global Environmental Benefits

Describe progress on targets and indicators relating to global environmental benefits:  what are the main results of the project?  Short-term impacts?  Long-term impacts?

Impacts – Local Benefits

Describe local benefits not covered above:  what are the livelihood, health, educational, awareness, or empowerment impacts of the project?  Short-term impacts?  Long-term impacts?

Sustainability

Provide a short description of sustainability of project outcomes: how will the project impacts maintain themselves after the project period?

Innovation

Describe how the project introduces innovation in achieving adaptation needs: what about this project is new?  Have new practices been introduced at the community level?  Do people have new skills, or have new government policies been created in the context of adaptation?

Replication

Describe main elements of the project’s replication plan:  Have other local communities spontaneously taken on elements of this project?  How will successful elements of this project be spread elsewhere?

Lessons on Operations:

Execution modality

Provide a short description of the project execution modality: Has the project implementation plan been successful? Why or why not?

Project implementation infrastructure

Provide a short description of the project implementation structure: how has the community been organized to implement the project?  What is the relationship like between the community and the NGO/CBO?  How has the project been led?

Main recommendations to contribute to other community-based adaptation projects:

1.

2.

3.

Please complete the contact information for your NGO/CBO)

| Name of NGO/CBO |  |
| --- | --- |
| Name of contact person |  |
| Address |  |
| City, Country |  |
| Phone |  |
| Fax |  |
| E-mail |  |
| Website |  |

Please, enclose PICTURES of "before" and "after", if available; or pictures that show success indicators or positive impact of the project.

Please provide a list of other sources of information about the project, such as publications, websites, or other media:

# Annex 4:  Examples of CBA Projects

CBA projects will address local stakeholder driven priority adaptation to climate change needs. Priorities will be based on findings in National Communications to the UNFCCC, as well as in National Adaptation Programmes of Action (NAPAs).  Broadly, proposals may fall into two categories:

- Projects that increase the adaptive capacity of communities, by engaging in and building capacity for ecosystem and natural resource management, or

- Projects that increase the resilience of ecosystems and natural resources directly, thus reducing the climatic vulnerability of communities that are dependent on those resources or on ecosystem goods and services.

All projects will simultaneously generate global environmental benefits – in the contexts both of improved national resource management, as well as in the context of increasing the resilience of globally important ecosystems to climate change.  Strategic partnerships with stakeholders in governments, bilateral organizations or others will provide co-financing to meet baseline development needs – doing tasks that should be done regardless of climate change – creating the conditions necessary for GEF funding to be effective.  In the process of increasing adaptive capacity of communities and/or ecosystems to climate change, SPA resources should also be used to ensure that global environmental benefits are secured in the context of anticipated climate change impacts.

Projects will be community driven and community designed, and will be selected based upon the degree to which global environmental benefits intersect with community adaptation priorities.  Project design and monitoring and evaluation systems will emphasize this, and procedures will be instituted to capture and diffuse lessons learned to stakeholders at regional, national and global levels.

While projects will be community driven and designed, exercises carried out during PDF-B have identified the following potential projects the PDF-B countries:

# Annex 5:  UNDP Responses to Comments by Germany, Switzerland, France and the United States on the Community Based Adaptation Programme (PIMS 3508)

| Comment | Responses |
| --- | --- |
| Comment from Germany: Generic Programme: The proposed CBA Programme covering 10 countries constitutes rather an UNDP/CBA Facility than a programme specifying what will be actually done with the requested GEF Resources. Most of the description is therefore rather generic, defining a process of identifying adaptation as opposed to describing and analyzing these measures directly. This limits the scope for comments to the process and the proposed organizational arrangements. | Guidance from Council on “GEF Assistance to Address Adaptation” (GEF/C.23/Inf.8/Rev.1, May 11, 2004) as outlined in paragraph 23 of the CBA Executive Summary states: “Recognizing that small communities are often the most severely affected, yet the least equipped to deal with the impacts of climate change, it is proposed that up to 10% of the resources under the strategic priority will be allocated to the Small Grants Programme which will work with the GEF Secretariat and the Implementing Agencies to pilot community adaptation initiatives through its existing small grant programmes. The SGP will: (i) develop community based capacity and tools to respond to the adverse impacts of climate change; (ii) finance diverse community-based adaptation projects in a number of selected countries; and (iii) capture and disseminate lessons learned at the community level.” Therefore, implicit in Council guidance on the SPA is the following: Council considers that the SGP mechanisms, together with input from the GEF Secretariat and the IA, is an effective conduit to facilitate adaptation to climate change at the community level; Projects funded under the SPA must deliver global benefits in a GEF focal area as well as improvements in adaptive capacity of communities and/or ecosystems to climate change. Following Council guidance on the SPA, UNDP, has partnered with GEF SGP, and proposed a framework to generate, select, develop, implement and monitor community-based projects that not only improve the resiliency of communities (and by direct extension, ecosystems) to climate change, but also deliver global benefits. As recommended by Council guidance on the SPA, the use of the existing global GEF SGP mechanism for identifying, developing, implementing and monitoring community based adaptation projects (para 2, Executive Summary) avoids the creation of a new facility. The selection of 10 countries for the CBA programme is based on key criteria such as vulnerability to climate change, diversity of ecosystems covered through the programme, SGP experience and capacity in working in different countries, among others (for example, balanced regional distribution). Based on UNDP/BCPR criteria for vulnerability to climate change, Bangladesh, Bolivia, Guatemala, Morocco, Niger, and Vietnam are classified as high risk countries to climate change impacts, while Jamaica, Kazakhstan, Namibia, Samoa are classified as medium risk. One country (Bangladesh) is also included to provide lessons on how CBA projects can be implemented in countries where SGP is not active. This is important in the context of developing UNDP’s portfolio of adaptation projects in countries where established institutional arrangements may not be available to support project implementation. In addition, as outlined in para. 30-60 of the Executive Summary, the proposal actually outlines criteria for selecting sites (para. 33 including need to address global benefits issues), screening criteria for the approval of project proposals (para 34(a—g)-36), modality of selection (through existing SGP national selection committees in addition to oversight by the project management team and implementation (through Community Based Organizations; para 37-40)) and monitoring (at the project and programme level; para. 83-96). By definition, the eligibility criteria for global benefits will resemble those in typical GEF focal areas and will be distinct from projects funded under the SCCF and LDCF. The Executive Summary also outlines (para. 78-82) a systematic mechanism for ensuring that the SGP mechanism delivers global environmental benefits and improvements in adaptive capacity (including ecosystem resilience) as required by the Council guidance on the SPA. The systematic mechanism involves oversight at the national level as well as from HQ (SGP) as is common practice in all SGP projects. In this case, however, there is the additional but complementary oversight that will be provided by UNDP/GEF/Climate Change & Adaptation Unit (CC-A) to ensure that projects proposed using the existing SGP national steering committees deliver improvements in adaptive capacity as well as global benefits in a relevant focal area. The guidelines outlined in the CBA proposal (para. 34 of the Executive Summary) include a series of criteria for M&E including that each project must track global environmental benefits. Attachment 1 of the Project Document suggests the use of Council accepted indicators for assessing global benefits in biodiversity, international waters and climate change. Furthermore, the project proposal screening criteria (para. 34 of the Executive Summary) will not permit the selection of proposals which do not deliver global benefits (see further details below). Annex A of the Executive Summary further describes the incremental cost analysis for global benefits, as well as for the adaptation benefits. This response to the Council guidance on SPA is packaged beyond the detail normally required for SGP replenishment and is consistent with UNDP’s internal programming procedures for adaptation projects. Examples of project types that will improve adaptive capacity to climate change and realize global benefits (see Annex 1; see also attachment 2 of the UNDP Project document). Based on preparatory work in four pilot countries, examples of projects that are, or not, likely to qualify for SPA funding are outlined in Annex 2). Action: Clarification of the rationale for the selection of 10 countries is outlined in para. 11 and 12 of the Executive Summary; List of projects likely to qualify (or not) for SPA funding under CBA included in Annex C3 of the Executive Summary and Annex 4 of the Project Document. |
| Comment from Germany Implementation Structure: The implications of the 10 country approach are, that the overall project structure is relatively heavy with plenty of potentially costly UNDP involvement without clarity of the value added of this approach (pp. 26- 29). It is critical that the bulk of the resources actually go into actual implementation practical adaptation initiatives and not into process and implementation structure. | It is not the intention of the CBA programme to have any additional structure for implementing CBA projects in the 10 countries. The CBA programme (as outlined in para. 37 and 78-82 of the Executive Summary) uses a decentralized existing GEF SGP infrastructure (including existing national steering committee, existing national coordinator, and existing office space, etc). No significant additional costs are likely to be involved in terms of UNDP involvement. The only additional resource is the voluntary contribution made by a national specialist on climate change and adaptation as part of the national steering committee (as is standard practice within the GEF/SGP structure). The CBA will use existing infrastructures (i.e. GEF SGP mechanisms). The proposed budget for the CBA (see Executive Summary, para. 98; see also Annex 3 below), indicates that 86% of the GEF allocated SPA funds will be used for the implementation of CBA projects in the 10 countries. This will be in the form of grants for implementing CBA projects. 8% of the SPA allocation will be used for developing a framework, criteria, knowledge, capacity, forming partnerships, raising co-financing, and other preparatory and implementation costs (including M&E of adaptive capacity). The remaining 6% will cover execution fees, which will use channels already established for the GEF SGP. Moreover, in contrast to conventional GEF Full Size projects, the CBA programme will not incur additional administrative costs (including for standard M&E practices, salaries of National Coordinators etc) given that this is already covered by GEF SGP’s global budget. Action: Indicative Budget for CBA Programme included (see page 26) of the Executive Summary Detailed budget included in section III of the project document. |
| Comment from Germany Evaluation and Results: The benefits of what the document calls “a programmatic approach” are not entirely clear given that replicability and upscaling of projects in adaptation to climate change are limited by the site specificity of any climate adaptation problem (reference is made to STAP Review of Barry Smits, p. 54). While considerable room in the text is devoted to the issue of monitoring and evaluation it is not clearly spelled out how this will be done in cost effective and meaningful way. The importance of evaluation cannot be overstated as the CBA is being introduced as “pilot approach” which will only make sense if there is a chance for meaningful results beyond the initial cases. The document claims CBA is “a results-based approach” with “results based management.” What that actually means beyond having a “Goal, Objective, and a set of Outcomes” (p. 13) is not spelled out in the document. Great care is required to apply a coherent monitoring and evaluation system in order to have meaningful results. | We agree with Council comments that the reference to a “programmatic approach” lacks the necessary clarity for a proposal such as this. We also agree with the comment that replicability and up-scaling of the projects in adaptation will be limited by site specificity. The revised Executive Summary and UNDP Project Document now refer to the CBA Programme as a strategic approach. As outlined in paragraphs 17-19 and 24-26 of the Executive Summary, a “strategic approach” permits a consistent long–term strategy to address climate change to be adopted at the programme level. Instead of the alternative ad-hoc approach, which is having a set of distinct CBA projects each addressing overlapping priorities or realizing global benefits in a single or variety of focal area in a number of different countries, a systematic approach to adaptation based on country driven priorities is more conducive to cost-effectively addressing climate change impacts and global benefits in practice. In addition, as the CBA Programme will generate lessons on adaptation to climate change, a strategic approach permits lessons to be captured in a more organized, balanced and coherent way and is likely to be more useful when up-scaling adaptation to climate change projects (keeping in mind context specific details) within a country or across new countries. The CBA programme is designed to reflect the national priorities (based on national communications, etc) for adaptation to climate change. The advantage of using the GEF-SGP modality, and a strategic approach is to facilitate a national priority set of adaptation responses as opposed to a set of ad-hoc community projects. This is the intention of developing a Country Programme Strategy (CPS) for improving adaptive capacity of ecosystems/communities in each of the countries. The CPS will, in turn, guide the design, implementation and analysis of a portfolio of CBA projects. A strategic approach, that utilizes the existing GEF-SGP infrastructure permits a coherent and strategic approach to underpin the selection of CBA projects based on criteria that includes vulnerability to climate change (as articulated in the national communications) and priority global environmental benefits. Since adaptation is currently defined very broadly, it is the intention of this programme to provide a more organized approach to CBA. The CBA Program is designed to use existing GEF-SGP M&E indicators (for monitoring global benefits—see Annex 4) as well as a CBA specific M&E approach for measuring improvements in adaptive capacity (note: the latter approach has been approved by STAP reviewer). The details of how the monitoring will be done in a cost effective way is outlined in the UNDP Project Document (pages 31-36). This includes details of the approach (based on UNDP-GEF’s Adaptation Policy Frameworks approach), responsibilities and key milestones, programme monitoring reporting, etc. The UNDP Project Document also outlines the anticipated lessons that are likely to emerge from the implementation of the CBA including the type of lessons on temporal scale of adaptations, best practices in integrating climate change concerns into development and/or project design, sharing knowledge etc. A coherent structure is presented for monitoring and evaluation to guide the implementation of the CBA projects in each of the 10 countries. On the issue of a results-based approach, para. 12-60 in the Executive Summary provides a detailed explanation of what the results based approach/management entails, what is expected and how the results will be achieved. This detail is in fact reinforced with additional details in the UNDP Project Document. Action: Reference to Programmatic Approach is clarified. Based on work by UNDP on developing an M&E framework for its adaptation portfolio, including SPA funded projects, an updated M&E framework is attached in Annex 2 of the Project Document, and country level guidelines on CBA M&E have been formulated and attached in annex 3 of the project document. In addition, project development guidelines will also be included. |
| Comment from Germany Dissemination: As Pilot Programme in community based adaptation little effort has been invested into information dissemination on the expected lessons and also in terms of reaching out to communities. Only standard dissemination methods are listed and little creativity (new media apart from websites, radio) is apparent from the document (p. 15). | The fundamental purpose of the CBA programme is to generate lessons. Each project will generate lessons on project design, using monitoring and evaluation and best practices on adaptation to climate change including delivery of global benefits. Rigorous evaluations, over and above conventional PIRs, will enable the GEF and UNDP (as well as other implementing agencies) to learn how to strengthen the adaptation portfolio. As outlined in para 49, lessons (positive and negative) on methods to increase capacity of communities to adapt to climate change, including variability, will be compiled and disseminating to key stakeholders (at the local and global level). The target audiences will include both communities engaged in CBA projects and policy makers, and the mechanism for dissemination will differ for these two audiences. This process will also feed into the international exchange of lessons. As outlined in the UNDP Project document (pages 35-37), linkage with existing information sharing networks, in particular, GEF- SGP mechanisms, together with UNDP-GEF’s Adaptation Learning Mechanism will drive the learning process. The CBA will be analysed in the context of the entire GEF portfolio. The UNDP/GEF's Adaptation Learning Mechanism (ALM) has been launched to facilitate the learning process from GEF’s adaptation portfolio. Under the direction of the Task Force on Climate Change and Adaptation (which includes GEFSEC and the other IAs), lessons learned from projects will be classified into the following criteria, including, (a) the temporal scale of climate change that the adaptation measures address; (b) whether it address single/multiple sectoral issues and/or socio-economic issues? (c) Whether the measures enhance development activities or ecosystems (or both)? (d) Best practices in integrating adaptation into national and local development policy? (e) Best practices in project design and implementation mechanisms? (e) how to prioritize adaptation options (strategies/policies or operations); (f) the scope of the adaptation project (local, sub-regional, national to sub-regional scales); (g) and capacity development approaches on adaptation, including engaging key stakeholders on adaptation. While not exhaustive, these types of lessons will be invaluable for the GEF family as adaptation projects become a priority. The method of dissemination of lessons learned is context specific and will be determined with input from the national steering committee in each country, with guidance from the global project management unit including the ALM Project Management Team at UNDP/GEF. Action: A template for guiding and capturing lessons based on the finalization of a current draft version is included under Annex 3, Attachment 7 of the project document. |
| Comment from Germany Incremental Costs: Operational Guidelines for the Strategic Priority “Piloting an Operational Approach to Adaptation” (SPA) foresee projects are eligible that “generate both local and (development-focused) and global benefits …if their benefits are considered primarily global in nature…” (Para 6, page 2). The “incremental cost analysis” (pp 32-33) in the submitted document does not contain any specific analysis due to the generic character of the document. It develops generic scenarios much like a financing mechanism. No reference is made how this mechanism ensures adhering to the “double-increment” criterion in the SPA guidelines. | The SPA guidelines defines the “double-increment” as (a) the incremental cost for improvements in global benefit, and (b) a second incremental cost associated with reducing vulnerability to climate change of communities and/or ecosystems,. The incremental cost matrix attached to the executive summary outlines the double-increment explicitly. The reference to how program will adhere to the “double-increment” criterion, is outlined in para 33-34. As outlined, a multi-step process guided by the principles of UNDP-GEF’s Adaptation Policy Frameworks (APF) will be relied on to first identify those regions of highest vulnerability to climate change, including variability, and regions having high potential to deliver global environmental benefits. In addition, projects will be first screened for delivering global environmental benefits based on Council accepted standards for the GEF focal areas Projects will then be screened for the second increment of delivering improvements in adaptive capacity. As outlined in para. 34, the responsibility of assessing the eligibility of CBA project proposals for funding will be assessed by the National Coordinating Committee on the basis of nationally-developed criteria relating to (a) climate change vulnerability; (b) addressing the adaptive capacity or resilience of a community to climate change including variability; (c) assessment of community vulnerabilities; (d) cross-scale policy potential; (e) Monitoring criteria (including description of the monitoring baseline and activities to monitor indicators of vulnerability); (f) Global environmental benefits; and (g) other priorities at the country level. Action: Examples of projects that will adhere to the concept of double increment are presented in Annex 4 of the project document. Project development guidelines are included in Annex 3 of the Project Document. |
| Comment from Germany Global Environmental Benefits: The generic character of the proposal also means that the question whether the projects results in global environmental benefits is being discussed on an abstract level. On this basis it is not possible to assess whether in fact this proposal will result in actual global benefits | GEF-SGP projects must deliver GEB as is standard practice. GEF Council, by allocating 10% of SPA resources for the implementation of community based adaptation projects through an IA (in this case, UNDP) and the GEF- Small Grants Programme has conveyed its confidence that SPA resources will be used for projects that will deliver both improvements in global benefits as well as adaptive capacity to climate change. This proposal has clearly articulated (para. 34 together with para. 102), in its design that CBA project proposals are subject to approval for implementation by the national steering committee, with oversight by the global project team including UNDP/GEF/CC-A and the SGP (at HQ), whether specific criteria are met. Regular consultations between the global team and GEFSEC will be useful in ensuring that CBA project proposals that are selected adhere to the relevant criteria of deliver global benefits as well as improvements in adaptive capacity. The mechanisms for ensuring that the selected CBA project proposals deliver global benefits as well as improvements in adaptive capacity are therefore in place and the institutional responsibilities are clearly defined. Action: Examples of projects that will adhere to the concept of double increment are presented in Annex 4. Project development guidelines have been included in Annex 3 of the Project Document |
| Comment from Switzerland 1. The executive summary and the project document outlining key steps and requirements are rather difficult to digest – even for specialists in the matter. The STAP reviewer points out the same problem. Many of the STAP reviewer’s comments are still valid for the final documents submitted to GEF: Excellent practical adaptation objectives of the programme could be at risk because of so far regrettably onerous, inefficient, and ineffective requirements for monitoring, evaluation, and reporting. | Agreed. Based on work by UNDP on developing an M&E framework for its’ adaptation portfolio, including SPA funded projects, an updated M&E framework will be circulated at the time of CEO endorsement. In addition, project development guidelines will also be included. Action: M&E and Project Development Guidelines included as annex 2. |
| 2. The complexity also may have an impact on the transaction cost generated at country level. This in particular as the modalities of co-financing are not clear yet. Co-financing does in practice lead to an increase of complexity at the implementation stage. | As per SGP requirements and operating procedures, 1:1 co-financing will be secured prior to the commencement of CBA projects. Since CBA will be implemented by UNDP in collaboration with SGP, the CBA will benefit from the installed capacity of and synergies with SGP at local, national and global levels. This will include SGP’s financial management, human resource management, knowledge management and impact assessment systems. Cost effectiveness will be achieved through the SGP disbursement mechanism. |
| Comment from Switzerland 3. This complexity is partly the consequence of guiding principles issued by the GEF on adaptation and incrementality (GEF/C.23/Inf8/rev1) with regard to global benefits. The programme should fit into the priorities laid out by the host countries in their initial national communication. The priorities of host governments and communities typically focus on enhancing coping capacity in terms of local development. This dilemma could possibly be overcome by short listing at the national level sectoral interventions which generate global environmental benefits in terms of e.g. biodiversity, land management, desertification based on the stressed resource base prevailing on eligible geographical areas. This could possibly reduce the M&E requirements to be applied to local level organizations and hence lead to a reduction of transaction cost. The global benefits are materialized in practice in a sustainable manner only if the programme is successfully implemented in development terms, and hence the local community does adapt the improvements in resource management during the operation and maintenance phase. | Agreed. Priority adaptation projects will be based on inputs such as the country’s National Communications to the UNFCC and potential projects that improve adaptive capacity will be filtered to identify those that deliver global benefits. |
| Comment from Switzerland 4. The programme implemented in NAPA countries may generate lessons on the manner in which local communities can successfully be integrated in an adaptation policy framework. Lessons learned with regard to the complementarities of the NAPA process and the CBA through the small grant programme would be highly welcome. | Agreed. Linkages to UNDP’s Adaptation Learning Mechanism have already been made. A template for guiding and capturing lessons based on the finalisation of a current draft version will be included prior to CEO endorsement. |
| Comment from Switzerland 5. We support the project and recommend it for approval by the GEF Council taking into consideration above comments. We trust in the implementing agency to further improve the final project document in the light of the comments of the STAP review and the complementary observations submitted by us. | We thank the Swiss Government for supporting the CBA initiative and look forward to further guidance. |
| Comment from France The project aims at exploring the issues of adaptation (i.e. impact, risk, vulnerability) to the climate change in various context of community areas (around 100 in total ) in ten different countries (Bolivia, Kazakhstan, Bangladesh, Morocco, Niger, Vietnam, Samoa, etc). The project is monitored by UNDP-GEF in conjunction with national coordinators in the countries, NGOs and communities. Beyond the support to specific projects (soils degradation, water, agriculture, etc), the expected outcomes are: adaptation country program strategy, national adaptation policies applied to community adaptation, international cooperation and capitalization. The governments and NGOs are deemed to co finance the project (4, 52 M$). Opinion: the project is an ambitious one. It is difficult (i) to make the difference between certain development issues and climate change and adaptation issues and (ii) to identify the experts in the fields of adaptation who are able to tackle the multiples issues. The coordination of around 100 projects throughout 10 countries is a real challenge of organization, control, and consolidation. However we suggest to clarify how many experts should be necessary and for what purposes to get significant results | The CBA Programme, implemented by UNDP in partnership with SGP, will benefit from the installed capacity of, and synergies with, the SGP at the local, national and global levels. This existing capacity will be augmented by an additional expert on climate change and adaptation to assist in selecting, developing and implementing adaptation to climate change projects. The CBA Programme will also benefit from already existing SGP financial management mechanisms, human resources, and knowledge management tools. UNDP-GEF’s Climate Change Adaptation team will provide the additional expertise, including input from other IAs and GEFSEC. As the project is linked to UNDP’s Adaptation Learning Mechanism, the CBA Programme stands to also gain from the experience and expertise of a wider community of professionals and communities working on climate change adaptation projects. We thank the French Government for the favourable opinion on the CBA Proposal and look forward to additional guidance. |
| Comment from the United States 1. This project proposes to create a new GEF program of funding small grants to communities and NGOs in the project countries for community-based adaptation using the model and some of the established mechanisms of the small grants program. What criteria were used to select the countries? | Countries were initially selected based on geographic representation (choosing countries from as many different regions as possible: Asia, Africa, etc.) and on predominant or unique ecoregions or biomes e.g. Jamaica - small island; Bolivia - mountains; Kazakhstan - steppe, etc. As well, we chose countries that had strong SGP Country Programmes (e.g. Niger, Bolivia) or promising new ones (Samoa, Jamaica). A "strong programme" is one that has a capable SGP National Coordinator, an engaged SGP National Steering Committee, and strong support from the UNDP Country Office. |
| Comment from the United States 2. What criteria will be used in selecting projects and who will make these decisions? | Technical criteria for project selection will be based: on evidence that climate change is a key driver of vulnerability proposed adaptations address climatic vulnerability proposed adaptation address long-term climate, and not current climate variability will be adapted to the specific conditions of each country's community based adaptation focus. Each country (through the SGP National Steering Committee) will formulate a CBA country strategy which will have a geographic focus (watershed, ecosystem, etc.) that has been selected based on analyses of vulnerability to climate change, presence of global environmental values (BD, LD, etc.), and potential for successful planning, programming and implementation of the CBA Country Programme (existence of sufficient community capacities, potential for partnerships with other organizations and donors, etc.). Once the criteria for project selection are adapted and codified, the project selection process will be carried out by each National Steering Committee with oversight by UNDP (through CDAC, in collaboration with SGP) who will monitor technical quality, coherence with the CBA Country Programme, etc. The project selection and management process will conform to SGP’s standards and practices, including utilization of the database and monitoring, evaluation and reporting procedures. |
| Comment from the United States 3. How are these projects different from what is currently funded under the small grants program? | These projects will differ from those currently funded under the SGP in that they will address community or ecosystem adaptation to climate change as a primary focus, with a significant emphasis on generating global environmental benefits consistent with the policies of the Strategic Priority on Adaptation (SPA). "Regular" SGP projects do not address adaptation but rather they focus solely on generating global benefits in the context of improving local environmental benefits, livelihoods and community empowerment. It should be noted that the CBA will be implemented by UNDP as an integral or functional part of the SGP and, as such, the CBA will benefit from the installed capacity of and synergies with the SGP at local, national and global levels. This will include SGP's financial management, human resource management, knowledge management and impact assessment systems. Cost effectiveness will be achieved through use of the SGP disbursement mechanism. |

# Annex 6:  UNDP Responses to Comments by the UNDP Project Appraisal Committee

| Comment | Response |
| --- | --- |
| Ove Bjerregaard, 1/10/2007 It is unclear how the ten countries were chosen. | The ten CBA countries were chosen based on their ability to provide lessons on adaptation to climate change, and thus desired to create the best mix to satisfy the following criteria: The existence of a strong SGP country programmes in 9 of the countries involved A desire to pilot the programme in a country where SGP is not active (Bangladesh) A desire to include a diversity of different climatic regimes, ecosystem types, and sectoral risks A desire to include a diversity of socioeconomic settings A desire to include countries that are exposed to varying levels of risk from climate change including variability |
| Ove Bjerregaard, 1/10/2007 What will be piloted in the ten countries, and what are some examples of old efforts and current concerns among beneficiaries and stakeholders? | Each of the ten countries will prepare a CBA Country Programme Strategy (CCPS), which will lay the framework for the development of a portfolio of 8-20 community projects. In addition, the CCPS will describe existing efforts (including constraints) in community-based adaptation as part of the identification of the adaptation baseline, while stakeholder consultations at the national and local level will ensure congruence with beneficiary concerns and priorities. See the CCPS Template and Guidelines (annex 3, section 3, attachment 1) for more details. |
| Ove Bjerregaard, 1/10/2007 The document is not user-friendly. | It is agreed that the document is quite long and dense in places. To remedy this problem, Annex 3 “CBA Programme Country-Level Toolkit” was drafted, in order to provide a straightforward guide to the ground-level implementation of the CBA programme. |
| Maxx Dilley, 1/19/2007 1) Institutionalization and sustainability -- I was particularly pleased to see substantial participation of relevant ministries on the national coordinating committee in the Bangladesh example. It is also good to see the multi-scale approach, of linking community work with national policies and processes. | CBA is intended to be structured in such a way as to harmonize top-down and bottom up adaptation processes. |
| Maxx Dilley, 1/19/2007 2) Evidence-based assessments -- One notably omitted stakeholder, however, at least in the Bangladesh case, is the hydrological and meteorological services. The participation of the national meteorological and hydrological services is needed because they have (or should have) data on climate variability and trends, as well as climate expertise. The VRA methodology in annex two appears to be largely (exclusively?) perception based. Perception, while very important, is a notoriously poor way to gauge climate conditions and their impacts. What are the actual climate trends and variability patterns? What can be said scientifically about probable future climates. This data should be made available to communities as part of the discussion. The same is true about climate impacts. It is important to establish not just what people think climate fluctuations are doing to agricultural production, health, etc. but also to review the scientific evidence as well. | We agree that hydrological and meteorological services have an important role to play in developing national CBA programmes, and have emphasized this point with the addition of text in the programme and project development frameworks, as well as in the CCPS guidelines. With regard to use of perception versus objective climate data – emphasis has been added to the project development framework to ensure that all projects place their interventions into the context of scientific assessments of climate change, climate variability, and climate impacts. However, much of this work will occur at the national programme level, during the development of the CCPS. Given that CCPSs will focus all projects onto one sector and geographic area, and assess climate risks to these, it is not envisioned that there will be a large degree of heterogeneity in the project-level objective risk assessments. However, the project proposal guidelines have been amended to ensure that scientific assessments of risk and vulnerability are included in project development. We agree that scientifically based data is important in measuring adaptation to climate change, and we believe that it compliments perceptual approaches such as that of the VRA, by grounding perceptions within an objective framework. |
| Maxx Dilley, 1/19/2007 3) Gender – There is little reference to gender in the project. Working at the community level is a chance to find out the extent to which climate affects the outcomes experienced by men and women differently. It would be good to include gender stratification in all the community project designs and to have some gender-sensitive indicators. | We agree that gender dynamics will affect exposure to climate risk, and have taken measures to ensure that projects identify the community sub-groups that are the focus of the projects. These might be based on gender, ethnicity, livelihood type, or socio-economic status. VRA measurements, as reported in the project proposals, progress reports and final reports, will explicitly address meeting composition to ensure that discussants are representative of the project’s target audience, the gender composition of which will have been explicitly spelled out in advance. |
| Maxx Dilley, 1/19/2007 4) Budget – the budget is quite vague (what, I wonder, are "contractual services?"). For the institutional capacity development and sustainability reasons mentioned above I think it is important to have as much of the work as possible done by local/national institutions. And not on a fee-for-services basis but rather using the project funding to enable them to carry out the work consistent with their respective mandates. Any other arrangement (reliance on consultants or buying off the local institutions from their "real work" to do projects) means that when the project is over they go onto the next one and nothing lasting is left behind. So more detail on implementation arrangements that show which agency will be doing what parts of the project in each country would at some point be nice to have. | The vast majority of the funding for the CBA Programme will go to the NGOs and CBOs implementing community projects under the national CBA programmes. These budgets will be quite detailed, and provide a high degree of transparency for how community adaptation funds are to be spent. See the project proposal template (annex 3, section 3, attachment 4) for further details. An operational budget – based on the budget included herein – will be finalized during the inception workshop. Non-project costs will be largely related to travel, reporting, and a small amount of administrative support to country programmes. In total, 86% of the total funds will go to programmes (outcomes 1 and 2). With regard to implementation arrangements: beyond some oversight of the country programmes from UNDP, all of the work in CBA will be carried out by local institutions. The CBA NCC will be composed of national stakeholders, the national coordinator is in all cases a local professional, and those actually implementing the projects are local NGOs. UNDP’s role is simply that of facilitator. |
| Lenni Montiel, 1/22/07 It is important to highlight the fact that substantively the project seems to be complex. That complexity is reflected as well in the management arrangements. Therefore coordination and communication within the different components and countries participating in the project will be crucial. The project document seems to address these issues. | While the framework developed in the project document is quite extensive, the concept for the CBA programme is actually rather simple, consisting of the three layers of the global programme, national programmes, and local projects. Communication between the global level and the local projects is facilitated by the National Coordinators, while cross-country lesson sharing is facilitated by UNDP under outcome 3. Also, note that as part of outcome 3, the CBA programme will document at least one example of cross-country lesson sharing. |
| Lenni Montiel, 1/22/07 Contributions to environmental governance. The project is very good at highlighting the role that sound organization and preparedness of small communities have in facing natural disasters and the impact of climate change at local levels. This is particularly relevant for the case of small communities that tend to be located in rural or remote areas. In this sense, the outputs and results of the project could definitely make very good contributions to the area of “environmental governance” in small communities. This angle of the project could be exploited further as part of its expected impact. | The CBA is committed to promoting environmental governance through its transmission of policy lessons to stakeholders government as part of outcome 2. By the completion of the CBA, the programme is expected to have documented 8 examples of policy change based on lessons generated from community projects across the countries in which it is present. This will be done through engagement of policymakers in the NCC, and their inclusion in topical seminars, to be driven by the NCs. |
| Lenni Montiel, 1/22/07 Involvement of local authorities or local governments in the project. During implementation, the project could explore, analyze and systematize the important role that local government, and in many cases also traditional local authorities, play in the mobilization and adaptation of responses of local communities to the preparedness to and the management of natural disasters. Wide dissemination of lessons learnt in this area could also be very useful and relevant for the overall work of UNDP in the ground. This is particularly relevant for cases where historically the management of natural disasters have involved local government efforts. The involvement of local government and their interaction may also be very relevant from the perspective of sustainability of financial and technical efforts. As we discussed over the telephone a great opportunity to do this would be during the preparation of the national project strategies by country. | This point is well taken. Given the geographical focus of each CCPS, a plan for local stakeholder identification and involvement makes sense at the country programme level. A requirement that CCPS’s do so has been included in the CCPS template and guidelines. |

# Annex 7:  UNDP Response to GEFSec Review, April 2006

| GEFSec Comment | UNDP Response |
| --- | --- |
| The project design section, as required by standard GEF guidelines, is missing. That section generally includes the project components and the incremental cost reasoning, including baseline and GEF alternative scenario. The incremental cost reasoning is described, and satisfactorily explained, in Annex A: Incremental cost analysis. The approach described in Annex A is satisfactory and the methodology is solid. It is also understood that each baseline cannot be known a priori for each project (in a program including 70 to 100 projects). However, the project executive summary would significantly improve with the inclusion of a project design section with project components, incremental cost reasoning, goals, and objectives. | It is true that the Executive Summary did not precisely follow GEF guidance. However, GEF guidance (http://thegef.org/Operational_Policies/Eligibility_Criteria/Annex_FP_-_G_Project_Exec_Summary_Template_and_prep_guidelines.doc) states that the Project Summary should “Describe project rationale, objectives, outputs/outcomes activities. Describe key indicators, assumptions, and risks (from logframe)”. The only mention of incremental costs in the guidance is in Annex A, where it was described in the original Executive Summary. Thus, the departure from GEF guidance lay in the fact that the original Executive Summary took 11 pages (pages 6 to 15) to describe what the guidance indicated should be 1 page. The incremental reasoning has now been added to the text (see new paragraphs 15-26); although this has caused an even greater deviation from GEF guidance by substantially lengthening a section that already exceeded the guidance by 10 times. The comment “the project executive summary would significantly improve with the inclusion of a project design section with project components, incremental cost reasoning, goals, and objectives” is not understood. All of these elements were present, with the exception of incremental cost reasoning (as per GEF guidance). February 2007, UNDP Adds: After minor revisions, paragraphs on incremental costs can now be found in paragraphs 10-22 of the executive summary, rather than 15-26. |
| With respect to indicators: Indicators for GEBs are listed in Annex 1 (missing), and indicators for V&A are described in Annex 2 … This section (M&E) is too long in the project brief and too short in the executive summary. It would be very useful to synthesize the long chapter on indicators focusing only on the key elements and refer to them in the executive summary. This project will be particularly vulnerable to criticisms, due to its broad scope and programmatic approach, if the discussion on indicators is not sufficiently clear. | The Indicators for GEB were, in fact, present. They were in a section labeled “Attachment 1”. Originally labeled “Annex 1”, the change was made to avoid confusion of having Annex 1 to an Annex. However, the corresponding change in the text was missed. This has now been changed. The M&E section in the Executive Summary has been lengthened (see new paragraphs 85-96) even though the existing text on Program and Policy Conformity was already 4 pages long, exceeding GEF guidance by double. February 2007, UNDP Adds: After minor revisions, the executive summary section on Monitoring and Evaluation can now be found in paragraphs 79-92, rather than 85-96 Also, GEB will be measured using the SGP Impact Assessment System. For more information, consult Annex 2 of the UNDP Project Document. |
| There is a discrepancy between the project text (page 20) where the co-financing is $1,131,283, while in the cover page the co-financing is $4,525,140. Please clarify which is the real figure and include a table specifying who are the co-financiers in the executive summary. | The discrepancy has been removed – the correct figure is $4,525,140. A Table has been added to the Executive Summary. February 2007, UNDP Adds: Committed co-financing currently totals $470,527. Approximately $550,000 is anticipated after project inception at the level of CBA country portfolios, in addition to $3,000,000 from the sum of local-co-financings of CBA community projects. This is all in addition to co-financing to be secured at the FSP level. |
| It is still unclear how the non-SGP countries will overcome the difficulty of not having an established system in place. Will they be economically penalized? Please clarify. | Experience gained during the PDF-B indicated that implementing the CBA in non-SGP countries is very difficult. An explanation has been added to paragraph 37 of the Executive Summary and 53 in the project document. February 2007, UNDP Adds: In the executive summary, this paragraph is now number 31, while it is now paragraph 37 of the project document. The only non-SGP country for the CBA pilot project will be Bangladesh. In that case, CBA will be implemented by the Comprehensive Disaster Management Project, removing the need to devote additional resources to replicate SGP mechanisms. |
| In particular include in the revision a mechanism for quality control on proposals to be provided by SGP/CDAC and the posting of the approved proposals – for 5 days (no objection basis) from GEF + IA; SGP and CDAC to provide guidance on shaping project proposals so that SPA criteria are met. | The mechanism to be used by CDAC/SGP for quality control of proposals is described below and in the Project Executive Summary on pp 8-9. Quality control of local level proposals is critical to the success of CBA, however, it is equally important to guarantee the strengths of a decentralized programme management system. To ensure quality of CBA projects, established SGP procedures will be strengthened based on the following six points: A Country Programme Strategy will be developed that clearly spells out Impacts, Outcomes and potential Outputs. As part of the CBA project, NCs will be trained by CDAC/SGP in Country Strategy development and implementation, and NSCs will be thoroughly briefed and trained in CPS formulation. CPS Outputs will consist of projects either singly or in multiples. The Outputs will not be identified in the CPS a priori much beyond a sort of generic description since projects must be demand-driven. However, by identifying them at least generically and in the context of the CPS geographic focus and other contextual elements, this will provide the basic set of project eligibility criteria to be used by the National Steering Committee in line with the global criteria. These criteria take the global, more generic criteria and ground them in local context. CDAC/SGP provide technical assistance to NCs/NSCs in CPS development. CDAC/SPG reviews and approves the Country Strategies, paying particular attention to results-based, strategic logic, including impact indicators and M&E. All CPS are posted on the CBA page of the SGP website. National Coordinators help CBOs/NGOs identify and formulate eligible proposals based on the global eligibility criteria and local contextual criteria and priorities. As part of the CBA project, NCs are trained by CDAC/SGP in adaptation project development and implementation. Projects are reviewed and endorsed by the NSC based on the CPS and eligibility criteria and sent to CDAC/SGP for no-objections approval. Project data is entered into the SGP database where it is monitored systematically by the dbase manager and CDAC/SGP. All CPS and general project information is made publicly available on the SGP/CBA website. CDAC/SGP monitors project formulation and implementation and evaluates impacts. CBA reports are provided periodically and/or as requested to the full Programme Team. CBA reports are also formally provided to GEF as part of the annual PIR. Lessons learned and other reports are provided to GEF as part of the CBA’s M&E. Throughout the project and programme cycles, CDAC/SGP provides technical assistance, troubleshooting, capacity building, and other services to NCs, NSCs and partners to ensure project and programme quality. A five-day, no-objections review by the full Programme Team (GEFSec, IAs, et al) of as many as 200 individual projects is unlikely to realistically provide the quality assurance that is required, but it will introduce a centralized approval layer that is more likely to cause delays in project processing. This review step is not needed in light of the process described above in which quality of project formulation and implementation is an integral part of the programme management system. February 2007, UNDP Adds: After minor revisions, this section can now be found on pages 7-8, rather than 8-9. |
| The consistency between the effort to reduce vulnerability/increase adaptive capacity and the generation of GEBs must be substantiated in a convincing way. | This is explained in paragraphs 15-20 February 2007, UNDP Adds: After minor revisions, this can now be found in paragraphs 10-15 of the executive summary, rather than 15-20. See also Annex 2 of the UNDP project document. |
| There are many typos. Please edit. | One typo was located in paragraph 15 of Annex A of the Executive Summary “a CPPs”, now corrected to “a CPPS”. In the project document 6 typos were located: Paragraph 23 “Comercialization”, now corrected to “Commercialization”. Paragraph 41 of Annex 1.1 had “andean” instead of “Andean”. Paragraph 42 had “adaptative” instead of “adaptive”. Paragraph 8 of Annex 1.3 had “Insfrastructure” instead of “Infrastructure”. Example 3 in Attachment 2 to Annex 3 had “affluents” instead of “effluents” Attachment 3 to Annex 3 had “taget” instead of “target” |

Annex 8:  Responses to STAP Reviewer’s Report, February 2006

| STAP Reviewer Comment | Response |
| --- | --- |
| There may be difficulties in achieving the outcomes in the 2 year time frame (the Executive Summary indicates 2 years for the “full-sized project”, the Project Document refers to a 5 year collaboration). | This is true. Earlier documentation proposed a 2-year time-scale, but during the PDF-B, the decision was made to change to a 5- year programme, for the same reasons outlined by the reviewer. In some places the text was not changed, but has now been changed to be consistent in describing a 5-year programme. |
| The management structures are generally in order, so long as the country teams include appropriate government agencies (beyond climate and environment departments, to include resource management, community development and sector agencies) and meaningful representation of communities and non-government organizations. | The SGP modality guarantees meaningful representation of communities, and requires cross-sectoral representation. National teams will be reminded of the principles of the SGP modality. |
| The document is convoluted to the point that it is extremely difficult to follow. | The documentation follows GEF guidelines in terms of structure |
| There is much more detailed direction on all kinds of M&E than there is on adaptation itself. Even those sections supposedly addressing “Implementation” | It is difficult to provide detailed guidance on implementation, as the implementation details will vary from project to project (to be determined by the communities themselves, based on guidance provided by the National Coordination Committee). However, much of the M&E needs to be consistent across projects and countries – hence greater direction is possible. |
| The requirements for M&E and data bases etc are not consistent throughout the document | The reviewer doesn’t really specify the inconsistencies. However, it may be the fact that there are two levels of M&E necessary for the CBA … the programme level and the individual project level that creates the impression of inconsistency, as the means and objectives of monitoring are different at the two levels. The text has been checked to ensure that this distinction is clear |
| The numeric vulnerability index (or adaptive capacity index) serves no useful purpose … it would not be a reasonable basis for evaluating the success or otherwise of the programme, and it would not be helpful to others hoping to learn from the experience in order that they can see how and why and in what way this project has enhanced adaptive capacity. | The reviewer does not explain why he feels the vulnerability index serves no useful purpose. It is a method to capture the views of community members regarding changes in their own vulnerability, and as such would seem to be particularly relevant, and suitable for measuring impact in terms of enhancing adaptive capacity. It is also based on analogous methods used the measure changes at the community level, for example, in terms of threats to biodiversity, as explained in the text. An overall programme level indicator requires an index, but the point is well taken and will be used (see below). |
| Information such as: most of the households in the community now have safe potable water (whereas hardly anyone did prior), and that 30% of households have expanded their livelihood base to some degree (mainly into – crops or -), with sustainable income sources, adaptation strategies (type a and e) have already been adopted by (5) non-beneficiaries on their own accord. This sort of information is relevant to the programme objective, directly indicates outcomes relative to the objective, deals with real phenomena, is easily understood, and provides information on the nature of improvements in adaptive capacity and reductions of vulnerability. This type of evaluation is not only relevant and informative, but it can be done efficiently, with modest time and resources. | Such indicators will certainly be used in the CBA – the documentation emphasizes that project specific indicators will be used where possible and feasible. However, there are numerous problems with such indicators. Firstly, they may or may not require modest time and resources. Where they do, that’s fine, but in many cases substantial resources would be required. Secondly, the examples quoted by the reviewer include terms such as “to some degree”, and “sustainable income sources”, which are very difficult to quantify. Thirdly, notwithstanding the fact that the indicators will be designed through community participation, there is a risk that they do not actually measure adaptive capacity. For example, households may have expanded their livelihood base, but still feel that they have lower adaptive capacity (their opinion on what constitutes adaptive capacity may have changed form the design phase). In contrast, the vulnerability index proposed (and discussed in the previous response) accounts for this risk. |
| At the national level the CBA is largely managed and undertaken through national government agencies. | Actually, the SGP modality requires that the CBA is managed through a national agency, which may be governmental or non-governmental, and guided by the National Coordination Committee, in which a majority of members are non-governmental. As the reviewer notes, the choice of agency to manage the programme at the national level will differ from country to country, and will be appropriate to each country. |
| A related challenge is the willingness of national agencies to allow resources to flow to communities, rather than be employed in the agencies ... there is no guarantee that anything different will occur in communities. There needs to be a check that communities are substantially involved that they have a significant role, and that resources are available to them to promote adaptation in areas that they identify as important | As above, the CBA modality effectively neutralizes this risk. |
| The detailed guidelines for selection of regions and communities (based on heroic assumption that such crude aggregate spatial indicators can actually identify particularly vulnerable communities) … | The guidelines are actually for selection of the region within the country where the CBA will operate. This IS based on the best spatial indicators of vulnerability available (which admittedly may be crude). There is no attempt to select communities within these regions based on differences in vulnerability (except insofar that documents such as the NAPA or SNC may identify particularly vulnerable sectors, such as pastoralism). |
| The programme refers to the need to document adaptations and outcomes so they can be replicated elsewhere. Certainly, the process followed to engage stakeholders, identify community-relevant vulnerabilities, relate to national policies, initiate adaptation activities, integrate them, etc. is replicable. But it is inconsistent (and flawed) to expect that many particular adaptation initiatives are replicable or transferable. | The intent is to document experiences so as to replicate the process. Documentation of experiences may also serve to increase the “universe” of adaptation options available to communities. This is based on experience gained through the SGP. |
| …Elsewhere (e.g. para 82) the GEB are presented as the primary objective. | The text has been checked and modified. The paragraph in question actually says that the type of GEBs (and local benefits) secured through the CBA will be similar to those secured through the SGP. The intent is to present increasing adaptive capacity and securing GEBs as joint goals, consistent with Council guidance on the CBA |
| If the primary “screening” of communities and activities in the CBA is to be according to potential to contribute to GEBs via initiatives focused on biodiversity, land degradation, etc., then say so in the CBA, and structure the programme accordingly, and do not claim that it is focusing on the particularly vulnerable communities nor on the full suite of initiatives that may reduce vulnerability. On the other hand, if the CBA is aiming to focus on reducing vulnerability of communities by enhancing the capacity of people to live sustainably in a changing environment (as in its goal and objective), then pursue this consistently, and show the contribution to GEB as an additional condition to community selection and project activities. | As above, the increase in adaptive capacity and achievement of GEBs are both used in screening regions where the CBA will operate. This is explained in the Figure following paragraph 29 in the Executive Summary and 39 in the UNDP prodoc. |

Endnotes

# Footnotes

All countries with SGP national Programmes have ratified the United Nations Framework Convention on Climate Change (UNFCCC) and/or the Convention on Biological Diversity (CBD) and have met the relevant eligibility criteria for technical assistance from UNDP.

All hereafter calculated on a pre-execution basis.

Ahmed, A.U. et. Al., (1999), ‘Vulnerability of Forest Ecosystems of Bangladesh to Climate Change,’ in S. Haque et al. (eds), 1999, Vulnerability and Adaptation to Climate Change for Bangladesh (Kluwer Academic Publishers), Dordrecht, The Netherlands.

Mitchell, T.D., Carter, T.R., Jones, P.D., Hulme,M., New, M., 2003: A comprehensive set of high-resolution grids of monthly climate for Europe and the globe: the observed record (1901-2000) and 16 scenarios (2001-2100). Journal of Climate: submitted.

IPCC 2007.  “Climate Change 2007:  The Physical Science Basis:  Summary for Policymakers.”  IPCC:  Geneva, Switzerland.

Details on specific legislative issues can be found in Bangladesh’s PRSP: Unlocking the Potential, National Strategy for Accelerated Poverty Reduction.  General Economics Division, Bangladesh, 2004.

Alternatively, they can work to ensure that existing GEBs from other GEF-funded projects will be resilient to climate change, though it is expected that fewer CBA projects will work to reinforce the benefits garnered from past projects.

Please follow instructions under each section and note that the italicized questions that follow are not exhaustive and only provide some initial guidance. It is also not obligatory to respond to all questions – please respond only to those that are relevant. Descriptions under each section should not exceed two paragraphs or 150 words.

# Endnotes

UNFCCC.  Compendium of Decision Tools to Evaluate Strategies for Adaptation to Climate Change.  http://unfccc.int/adaptation/methodologies_for/vulnerability_and_adaptation/items/2674.php.  Accessed 15 November, 2006.

Richard Margoluis and Nick Salafsky. Is Our Project Succeeding: A Guide to Threat Reduction Assessment for Conservation. Biodiversity Support Programme, Washington DC (www.BSPonline.org).

UNFCCC, ibid.

UNFCCC, ibid

Margoulis and Salafsky, ibid

Margoulis and Salafsky, ibid

Margoulis and Salafsky, ibid

UNFCCC, ibid.

# Text boxes

Brief description

It is increasingly recognized that small communities are likely to be the most severely affected by climate change impacts and yet are least equipped to cope and adapt. This pilot project is designed to implement community-based projects that seek to enhance the resiliency of communities, and/or the ecosystems on which they rely, to climate change impacts. It will essentially create small-scale ‘project/policy laboratories’ and generate knowledge about how to achieve adaptation at the local level.  Ten participating countries (Bangladesh, Bolivia, Guatemala, Jamaica, Kazakhstan, Morocco, Namibia, Niger, Samoa, and Vietnam) will each develop, plan and implement a portfolio of 8-20 community-level adaptation projects.  Lessons learned from community projects will then be leveraged to promote replication of successful community practices, and integration of lessons learned into policies that promote increased community adaptive capacity.  This project will assist in responding to GEF’s internal needs for concrete experience with local-scale climate change adaptation, as well as the growing needs of countries for ground-level experience and clear policy lessons.

Total budget:			 $9,050,280

Allocated resources:		 $4,525,140

- Government			 $400,000

- Project-level co-financing*	 $4,125,140

Programme Period:  2007-2011

Programme Component: _________

Project Title: Community Based Adaptation (CBA)

Project ID: PIMS 3508 CC/Adaptation Community Based Adaptation (CBA)

Project Duration:	5 years

Niger

- Adapting land-management practices to defend against climate change-induced water stress

- Global environmental benefits under the land degradation focal area

Climate change in the central Sahel is expected to enhance inter-annual precipitation variability, increased temperatures, and consequentially increased vulnerability to water stress.  Land degradation is also a major issue in the region, stemming both from climatic as well as non-climatic factors.  In Niger, drought risk and land degradation intersect to impact the lives of many.  An example of a CBA project in a region of Niger vulnerable to climate change could focus on (a) building capacity of communities to understand the likely long term risks of climate change on their livelihood options; and (b) implementing specific measures such as the diffusion of improved seeds, agroforestry, or improved water management in regions that are identified as particularly vulnerable to climate hazards.

Partnerships could be forged to help communities to reverse presently existing land degradation, while SPA funds will support measures to the build resilience of those measures to climate change – maintaining global environmental benefits while also supporting increases in community adaptive capacity.

It is important to recognize however that not all solutions to community-level climate challenges will be found at the local level.  Often times the causes of vulnerability or barriers to coping are found at societal levels and may depend on social and economic realities or government policies. As such, that the project will also address systemic issues through policy dialogue with relevant stakeholders, helping to avoid policy maladaptations such as disincentives for soil conservation or land stewardship

Samoa

- Improved defense against climate change-induced storm surges and coastal erosion

- Global environmental benefits under the biodiversity focal area

Scientific assessments suggest that Samoan coastlines will be increasingly vulnerable to both sea level rise and increased intensity of storm surges.  These dual hazards threaten enhanced coastal erosion and consequent reductions in biodiversity – chiefly from mangrove ecosystems.  This degradation will exacerbate the vulnerability of local communities to already increasing climate hazards, as the mangroves had previously protected the coast as well as absorbed much of the force of storm surges.

An example of a CBA project in this context would involve engaging a community in a vulnerable region of Samoa to strengthen coastal defenses through mangrove reforestation.  Beyond the design and implementation of mangrove replanting schemes, communities will be involved in capacity development – not only to understand future climate risks, but to develop improved natural resource management procedures, specifically designed to sustain the ecosystem and the livelihoods that depend upon it.

Project partnerships will address baseline development needs such as improvement in market conditions for the sale of products from mangroves, infrastructure requirements that are necessary to strengthen coastal defenses and so on. SPA funding will concentrate on the elements of the NRM aspects of the project that increase community and ecosystem adaptive capacity and resilience to climate change.

Bolivia

- Helping farmers to adapt their agro-ecosystems to climate change

- Global environmental benefits under the biodiversity focal area

Increasingly strong scientific evidence shows that along with polar regions, mountainous areas will experience larger degrees of temperature rise than elsewhere on the planet.  This is particularly evident in the Andes Mountains, which have experienced alarming rates of glacial retreat and treeline advance, affecting water availability and livelihood possibilities.  While cultivable zones may expand, water availability may change and the risk of floods may increase.  A potential CBA project in Bolivia might work with communities to understand the changes that have already taken place and build capacity to adapt to coming changes including variability through improved management practices.  These measures would strengthen management of globally important agro-biodiversity, such as indigenous potato and quinoa varieties.

SPA funding could be used to build capacity and implement measures to adapt traditional agro-ecosystems to changing climate including different patterns of variability, while partnerships could support the linkage of these communities into selective markets (green, organic, fair trade, etc).  Lessons generated from this programme will have a particular significance to other centers of agricultural biodiversity around the world, in terms of adaptation to climate change futures, as well as in terms of profiting from agricultural biodiversity through the tapping of alternative markets.

Bangladesh

- Prevention of climate change-induced saltwater intrusion to coastal freshwater resources

- Global environmental benefits under the land degradation focal area

In low-lying coastal environments, climate change is likely to pose serious risks to freshwater supplies through sea-level rise.  Much of Bangladesh is vulnerable to these effects, and a CBA project funded by the GEF could support community activities to protect freshwater supplies from salinisation due to seawater intrusion. GEF funds will empower communities to assess the threat of climate change on freshwater resources – building on pre-existing work at the national level – and implement activities to protect freshwater supplies.

These measures could attempt to manage groundwater levels and improve drainage, providing global benefits in terms of land degradation (through salinization) avoided.  SPA funding would support elements of the project that increase adaptive capacity to climate change and provide global environmental benefits, while partnerships could cover systems to bring this water to homes and to agriculture for improved agricultural production and for sanitation and domestic uses.

Beyond monitoring and evaluation at the project level, lessons learned at the programme level will ensure that lessons generated from this project will be united with potential users in governments, NGO’s, communities or other stakeholders within Bangladesh and around the world, guiding policy project design far beyond the reach of the community involved.

Map 1:  Disaster risk map of Bangladesh, with the CBA pilot region highlighted.

Figure 1:  A hypothetical country, showing areas where vulnerability to climate change including variability intersects with areas where global environmental benefits might be achieved.