request for project preparation grant (PPG)

Project Type:

the GEF Trust Fund

Submission date:	12 June 2008

Re-submission date:

GEF Project ID: 3627

GEF Agency  Project ID:

Country(ies): Vietnam

Project Title: Promotion of Sustainable Forest and Land Management in the Vietnam Uplands

GEF Agency(ies):

Other Executing partner(s): Department of Forestry, Ministry of Agriculture and Rural Development, Vietnam

GEF Focal Area(s): ,

GEF-4 Strategic program(s): LD-SP2, BD-SP4, BD-SP5

name of parent/program/umbrella project (if applicable): Vietnam Country Program Framework for Sustainable Forest Land Management (CPFSFLM)

GEF Fees Advance Request:	USD 10,000

a.   Project preparation Timeframe

| Start date of PPG | July 2008 |
| --- | --- |
| Completion date of PPG | July 2009 |
| CEO Endorsement/Approval of project | July 2009 |

b.   project preparation activities ($)

| Describe the PPG activities and justifications: The project preparation will comprise a number of steps including rapid asssessment and scoping exercise to verify the selection of the project sites and the scope of activities. This will be followed by more in depth assesments of the biodiversity, SLM and SFM needs and opportunities as well as socio-economic assessments of the project sites, including stakeholder consultations to ensure adequate engagement of local communities and other key stakeholders in the project areas. Formulation of the proposal will include development of the institutional framework and financing plan, and also detailed formulation of outputs and indicators as well as meeting other requirements for GEF and Co-funding project design.The preparation of the GEF project will be integrated with the preparation of the associated IFAD loan (see full details in Annex B, below). |
| --- |
| List project preparation activities | Output of the PPG activities | Project Preparation (a) | Co-financing (b) | Total C = a + b |
|  |  | PPG |  |  |
| 1. Assessment and scoping, data collection, revision of relevant studies, institutional analysis | Comprehensive analysis of the situation and indicative project options | 29,428 | 29,000 | 58,428 |
| 2. Identification of project sites and interventions, preparation of project strategy and evaluation of alternatives, including consultations and validation with national stakeholders and other actors | Project strategy prepared (logical framework and project implementation plan) | 36,103 | 32,000 | 68,103 |
| 3. Project development | Full project document prepared and ready for submission to the GEF | 31,695 | 42,500 | 74,195 |
| 4. Project formulation management | Coordination, management and supervision of work and consultants | 0 | 12,500 | 12,500 |
| Contingencies |  | 3,300 | 3,500 | 6,800 |
| Total project preparation financing | 100,000 | 119,500 | 219,500 |

C.  PPG  requested by agency(ies), focal area(s) and country(ies)

| GEF Agency | Focal Area | Country Name/ Global | (in $) |
| --- | --- | --- | --- |
|  |  |  | PPG (a) | Agency Fee (b) | Total c = a + b |
|  |  | Vietnam | 20,000 | 2,000 | 22,000 |
|  |  | Vietnam | 80,000 | 8,000 | 88,000 |
| Total PPG Requested | 100,000 | 10,000 | 110,000 |

D.   PPG Budget Request

| Cost Items | Total Estimated Person Weeks for GEF Grant (PW) | GEF ($) | Co-financing ($) | Total ($) |
| --- | --- | --- | --- | --- |
| Local consultants * | 24 | 19,350 | 10,000 | 29,350 |
| International consultants* | 21 | 48,750 | 58,500 | 107,250 |
| Travel |  | 21,100 | 25,000 | 46,100 |
| Consultations and validation |  | 7,500 | 10,000 | 17,500 |
| Project formulation management |  | 0 | 12,500 | 12,500 |
| Contingencies |  | 3,300 | 3,500 | 6,800 |
| Total PPG Budget |  | 100,000 | 119,500 | 219,500 |

*   A separate Annex A for Consultant cost details should be included in this PPG Request.

E.   GEF Agency(ies) Certification

| This request has been prepared in accordance with GEF policies and procedures and meets the GEF criteria for project identification and preparation. |
| --- |
| Ms. Khalida Bouzar Coordinator, GECC/PMD IFAD | Mr. Jesús Quintana Project Contact Person, PMD IFAD |
| Date: 12 June 2008 | Tel.: +39.5459.2210 Email: j.quintana@ifad.org |
| Please do not forget to copy the IFAD/GECC Registry on all official communications,GECCregistry@ifad.org |

Annex A:  Consultants Financed by the Project Preparation Grant (PPG)

| Position Titles | $/ Person Wk* | Est’d PWs** | Tasks to be performed |
| --- | --- | --- | --- |
| L O C A L |
| Biodiversity/Forest Management Specialist | 900 | 9.0 | 1. Undertaking the review of policies and practices related to Biodiversity and forest management; 2. Coordinating the scoping and selection of the project sites, 3. Undertaking assessments at the project sites to determine areas for project intervention; 4. Contributing to the formulation of respective aspects of the project; 5. Facilitating consultations with relevant technical agencies and specialists. |
| Environmental Services Specialist | 750 | 4.0 | 1. Contributing to the scoping of the project, assessment of project sites and identification of pilot activities; 2. Undertaking the development of forest certification and/or environmental services schemes as appropriate; 3. Contributing to relevent parts of the project design |
| Community Development Specialist | 750 | 5.0 | 1. Supporting the site assessment and selection; 2. Assessing the options for community development in the targeted project sites; 3. Developing the design of community forestry and conservation aspects for inclusion in the project design; 4. Facilitating consultations with local communities and other stakeholders |
| Institutional and Capacity Building Specialist | 750 | 6.0 | 1. Facilitating liaison with key institutions and agencies; 2. Analyzing and assessing the institutional set-up in the Vietnamese forest sector with focus on community-based forest rehabilitation and management; 3. Identifying key issues strengths and weaknessess in relation with forest management, enforcement, monitoring and control, and associated capacity building needs; 4. Developing the institutional framework and implementation plan for project implementation; 5. Organising consultations with other bilateral or multilateral institutions in the country working on relevant activities. |
| I N T E R N A T I O N A L |
| Team Leader, GEF Specialist | 2,500 | 10.0 | 1. 1. Providing overall coordination of GEF project formulation; 2. Guiding the institutional analysis and capacity asssessment; 3. Overseeing project scoping and selection of project sites; 4. Facilitating the detailed project formulation including the development of the logical framework and detailed interventions; 5. Ensuring the compliance with GEF project design requirements; 6. Assessing the sustainability of the project; 7. Ensuring integration between the design of GEF and co-financed activities; 8. Ensuring appropriate linkages with related GEF agencies and interventions |
| Natural Resource Management Specialist (land degradation, water conservation, forest management) | 2,250 | 6.0 | 1. Overseeing natural resource and site assessments; 2. Contributing to selection of sites and interventions; 3. Providing input and guidance to the strategic reveiws by local team members; 4. Guiding the design of the SLM, biodiversity and forest conservation related elements; 5. Providing specific technical inputs to the design of specific elements of the project |
| Climate Change Expert | 2,250 | 1.0 | 1. Reviewing climate change related risks and recommend options for integrating climate change into project design |
| Specialist, project monitoring & evaluation and financial aspects | 2,000 | 4.0 | 1. Developing of M&E Plan; 2. Reviewing and guiding on modalities for financing community based forest management; 3. Preparing detailed project cost tables; 4. Assisting in the preparation of grant administration modalities; 5. Facilitating co-financing arrangements |

*   Or person month, if applicable. Please indicate clearly.  ** Provide weeks or months as appropriate that corresponds to the rate provided in the previous column.

Annex B

Project preparation activities

The proposed activities are described in more detail below:

Activity 1. Assessment and scoping, data collection, review of relevant studies and institutional analysis

Under this activity a rapid review and analysis will be made of existing information related to the proposed project interventions and focal areas in conjunction with key stakeholders. Sub-steps will include:

- Review of relevant policies and practices related to community-based forest management and rehabilitation in Vietnam

- Preliminary Review and analysis of institutional arrangements at national and provincial ( in the target province) level  to determine indicative strengths and weaknesses and priorities for capacity building

- Review of experience and lessons learned from other similar interventions over the past 5 years

- Confirmation of the scope and nature of the project intervention in conjunction with key stakeholders including the preliminary  identification of candidate project sites and interventions

The output of this activity will be a report with a comprehensive analysis of the situation and indicative project options.

Activity 2. Identification of project sites and interventions, preparation of project strategy and evaluation of alternatives

This activity will comprise the following sub- activities:

- Development of project strategy including identification of indicative interventions and site selection criteria

- Rapid assessment of candidate project sites according to biodiversity, SLM, socio-economic, forest management, community development and other criteria.

- Selection of sites through consultative process with stakeholders including local government and communities

- Evaluation of alternative sites and intervention options and selection of most cost effective and environmentally sound options in line with global, national and local stakeholder priorities

- Other necessary consultations and validation with national stakeholders and other actors

The output will be a project strategy (including an indicative project logical framework and project implementation plan)

Activity 3. Project development

The project development activity will include the following sub-activities:

- Elaboration of a range of technical working documents on different aspects of the project building on Activity 2 including detailed description of interventions and project sites and institutional arrangements

- Refinement of the project logical framework and implementation plan

- Development of project institutional arrangements to ensure smooth project implementation and sustainability.

- Evaluation of climate change and other risks and integrate into project design

- Development of budget and financing plan including facilitation of local, provincial and national co-financing  and integration with arrangements for associated IFAD loan

- Development of M&E system to be integrated as far as possible with national and provincial M&E arrangements.

The output will be a full project document prepared and ready for submission to the GEF. IFAD will cover the costs associated with writing the proposal.

Activity 4. Project formulation management

The project formulation management will include the coordination, management and supervision of the consultants necessary for the implementation of the PPG and project design process and the associated costs will be fully met by IFAD.