request for project preparation grant (PPG)

Project Type:

the GEF Trust Fund

Submission date:  October 13, 2008

Re-submission date:

GEFSEC Project ID:

GEF Agency  Project ID:

Country(ies): GLOBAL (with pilot sites in Chile, Vietnam, Trinidad and Tobago, Gariep river basin (South Africa and Lesotho, transboundary))

Project Title: Project for Ecosystem Services (ProEcoServ)

GEF Agency(ies): UNEP

Other Executing partner(s): UNEP-DEPI in cooperation with National Governments, and the MA SGA follow-up network

GEF Focal Area(s): Biodiversity

GEF-4 Strategic program(s): BD-SP4; BD-SP5

name of parent/program/umbrella project:  N/A

a.   Project preparation Timeframe

| Start date | 1st February 2008 |
| --- | --- |
| Completion date | 31st May 2009 |

b.   project preparation activities ($)

| Describe the PPG activities: To advance the preparation for the Programme on Ecosystem Services (ProEcoServ), which aims to integrate the sustainable use of biological resources and ecosystem services into national decision making and development approaches in Chile, Vietnam, Trinidad and Tobago, and the Gariep river basin in South Africa and Lesotho |
| --- |
| List project preparation activities | GEF Grant | Co-financing | Total |
| 1. Pre-assessment in each country/region through desk/field studies and coordination with the national SGA networks. Specific activities include: (a) Review and re-confirm findings of and changes to the prior sub-global assessments, incl. existing environmental and development policy frameworks/planning and budgetary processes as well as stakeholder groups in each country/region (b) Conduct rapid needs assessment in each country/region on capacity building for decision makers, users and beneficiaries of ecosystem services as well as intermediaries | 29,500 | 21,500 | 51,000 |
| 2. Develop project proposal, by bringing together all the key stakeholders of different countries/region. Specific activities include: (a) Conduct stakeholder workshop (in one selected country/region e.g. South Africa for key stakeholders from all countries/regions) for presenting the results of pre-assessments as well as project concept to the key stakeholders, receiving their inputs to the proposal through consultations, and ensuring consistency and complementary among the countries/region (b) Further develop the project proposal by integrating the results of the inception stakeholder workshops into full project proposal including project monitoring and evaluation system. | 37,500 | 23,500 | 61,000 |
| Total project preparation financing | 67,000 | 45,000 | 112,000 |

c.   PPG Budget Requesting Finance by GEF

| Cost Items | Total Estimated Person Weeks (PW) | GEF ($) | Co-financing ($) | Total ($) |
| --- | --- | --- | --- | --- |
| Local consultants * | 30 | 26,500 | 18,500 | 45,000 |
| International consultants* | 6 | 13,000 | 5,000 | 18,000 |
| Travel |  | 27,500 | 21,500 | 49,000 |
| Total PPG Budget |  | 67,000 | 45,000 | 112,000 |

*  Split between local and international consultants might be indicative and subject to the procurement guidelines of the 
            Agencies.  Additional information regarding consultants should be provided in Annex A.

d.   GEF Agency(ies) Certification

| This request has been prepared in accordance with GEF policies and procedures and meets the GEF criteria for project identification and preparation. |
| --- |
| Maryam Niamir Fuller, Director DGEF/UNEP GEF Agency Coordinator | Project Contact Person Gabriel Labbate |
| Date: October 13, 2008 | Tel. and Email:+ (507) 305-3168 gabriel.labbate@pnuma.org |

Annex A

Consultants Financed by the Project Preparation Grant (PPG)

| Position Titles | $/ Person Week | Estimated PWs | Tasks to be performed |
| --- | --- | --- | --- |
| Local |  |  |  |
| 2 SGA experts from Chile | 1,500 | 6 | Conduct pre-assessment in their country, contribute to full project proposal |
| 2 SGA experts from Vietnam | 1,500 | 6 | Conduct pre-assessment in their country, contribute to full project proposal |
| 2 SGA experts from Trinidad and Tobago | 1,500 | 6 | Conduct pre-assessment in their country, contribute to full project proposal |
| 2 SGA experts from South Africa | 1,500 | 6 | Conduct pre-assessment in their country, contribute to full project proposal |
| 2 SGA experts from Lesotho | 1,500 | 6 | Conduct pre-assessment in their country, contribute to full project proposal |
| International |  |  |  |
| Environmental economist | 2,500 | 4,5 | Coordinate project preparation activities, conduct stakeholder workshop, and integrate results into final project proposal. |
| Environmental scientist | 2,250 | 3 | Support project preparation activities, conduct stakeholder workshop; provide input to final project proposal. |

# Footnotes

Project ID number will be assigned initially by GEFSEC.  If  PIF has been submitted earlier, use the same ID number as PIF.